## Floor-wise
Row Labels | Total Drgs | Submitted | Approved
Above Roof | 1 | 1 | 1
Basement | 8 | 8 | 8
Common | 12 | 12 | 11
Detail Drawings | 20 | 19 | 19
Eighth Floor | 11 | 11 | 11
Existing Building | 24 | 18 | 18
External | 5 | 5 | 5
Fifth Floor | 7 | 7 | 7
First Floor | 7 | 7 | 7
Fourth Floor | 7 | 7 | 7
Ground Floor | 7 | 7 | 7
Ninth floor | 10 | 10 | 10
Overall Plan, Elevations & Sections | 9 | 9 | 9
Roof Floor | 7 | 7 | 7
Second Floor | 7 | 7 | 7
Seventh Floor | 7 | 7 | 7
Sixth Floor | 7 | 7 | 7
Tenth Floor | 16 | 16 | 16
Terrace floor | 4 | 4 | 4
Third Floor | 7 | 7 | 7
Grand Total | 183 | 176 | 175
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## S-Curve Wkly
[10 empty] | Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals
Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | 2025-05-05 | 0% | 0% | 0.4237% | 0%
2025-03-03 | 7.65% | 8.197% | 0% | 0% | 2025-02-03 | 0% | 0% | 0% | 0% | 2025-05-12 | 6.356% | 0% | 0.8475% | 0%
2025-03-10 | 9.29% | 10.38% | 0% | 2.186% | 2025-02-10 | 0% | 0% | 0% | 0% | 2025-05-19 | 6.356% | 5.932% | 0.8475% | 0%
2025-03-17 | 9.29% | 10.38% | 0% | 2.186% | 2025-02-17 | 0% | 0% | 0% | 0% | 2025-05-26 | 11.86% | 5.932% | 11.86% | 8.051%
2025-03-24 | 11.48% | 14.75% | 7.104% | 8.197% | 2025-02-24 | 0% | 0% | 0% | 0% | 2025-06-02 | 11.86% | 5.932% | 15.25% | 19.92%
2025-03-31 | 22.4% | 20.77% | 8.197% | 8.197% | 2025-03-03 | 13.82% | 13.82% | 0% | 0% | 2025-06-09 | 18.64% | 5.932% | 19.92% | 19.92%
2025-04-07 | 22.95% | 25.14% | 10.38% | 8.197% | 2025-03-10 | 13.82% | 14.63% | 0% | 0% | 2025-06-16 | 19.92% | 11.44% | 20.76% | 19.92%
2025-04-14 | 22.95% | 25.68% | 19.13% | 8.197% | 2025-03-17 | 13.82% | 14.63% | 0% | 0% | 2025-06-23 | 31.78% | 11.44% | 22.03% | 19.92%
2025-04-21 | 22.95% | 25.68% | 21.31% | 9.836% | 2025-03-24 | 13.82% | 14.63% | 2.439% | 13.82% | 2025-06-30 | 31.78% | 17.37% | 27.54% | 19.92%
2025-04-28 | 22.95% | 26.23% | 23.5% | 9.836% | 2025-03-31 | 17.89% | 17.89% | 13.82% | 13.82% | 2025-07-07 | 40.25% | 23.31% | 27.97% | 25.85%
2025-05-05 | 22.95% | 26.23% | 24.04% | 9.836% | 2025-04-07 | 23.58% | 22.76% | 13.82% | 13.82% | 2025-07-14 | 41.53% | 23.31% | 39.41% | 25.85%
2025-05-12 | 26.78% | 26.23% | 24.04% | 10.38% | 2025-04-14 | 25.2% | 26.02% | 13.82% | 13.82% | 2025-07-21 | 42.8% | 24.15% | 39.41% | 25.85%
2025-05-19 | 26.78% | 27.32% | 24.04% | 10.38% | 2025-04-21 | 25.2% | 26.02% | 13.82% | 13.82% | 2025-07-28 | 42.8% | 24.15% | 50.42% | 25.85%
2025-05-26 | 31.69% | 27.32% | 27.87% | 15.3% | 2025-04-28 | 25.2% | 26.02% | 17.89% | 15.45% | 2025-08-04 | 42.8% | 24.15% | 50.42% | 25.85%
2025-06-02 | 31.69% | 27.32% | 27.87% | 22.95% | 2025-05-05 | 30.08% | 26.02% | 23.58% | 15.45% | 2025-08-11 | 42.8% | 24.15% | 61.02% | 25.85%
2025-06-09 | 35.52% | 30.05% | 31.69% | 22.95% | 2025-05-12 | 33.33% | 29.27% | 25.2% | 15.45% | 2025-08-18 | 42.8% | 24.15% | 61.02% | 25.85%
2025-06-16 | 36.61% | 33.88% | 31.69% | 22.95% | 2025-05-19 | 38.21% | 32.52% | 25.2% | 15.45% | 2025-08-25 | 42.8% | 37.29% | 61.02% | 27.12%
2025-06-23 | 45.9% | 34.43% | 32.79% | 22.95% | 2025-05-26 | 41.46% | 32.52% | 25.2% | 15.45% | 2025-09-01 | 42.8% | 37.29% | 61.02% | 27.12%
2025-06-30 | 45.9% | 41.53% | 36.61% | 23.5% | 2025-06-02 | 42.28% | 35.77% | 30.08% | 15.45% | 2025-09-08 | 42.8% | 42.8% | 61.02% | 27.12%
2025-07-07 | 53.55% | 45.36% | 36.61% | 27.32% | 2025-06-09 | 43.09% | 37.4% | 33.33% | 15.45% | 2025-09-15 | 42.8% | 42.8% | 61.02% | 27.12%
2025-07-14 | 53.55% | 45.36% | 45.36% | 27.32% | 2025-06-16 | 43.09% | 38.21% | 38.21% | 15.45% | 2025-09-22 | 42.8% | 42.8% | 61.02% | 27.12%
2025-07-21 | 57.38% | 45.36% | 46.99% | 27.32% | 2025-06-23 | 43.9% | 42.28% | 41.46% | 15.45% | 2025-09-29 | 42.8% | 42.8% | 61.02% | 27.12%
2025-07-28 | 57.38% | 45.36% | 54.64% | 27.32% | 2025-06-30 | 43.9% | 42.28% | 42.28% | 17.89% | 2025-10-06 | 42.8% | 43.64% | 61.02% | 27.12%
2025-08-04 | 57.38% | 45.36% | 54.64% | 27.32% | 2025-07-07 | 43.9% | 44.72% | 43.09% | 19.51% | 2025-10-13 | 42.8% | 43.64% | 61.02% | 50.85%
2025-08-11 | 57.38% | 45.36% | 57.92% | 27.32% | 2025-07-14 | 43.9% | 44.72% | 43.09% | 21.95% | 2025-10-20 | 48.73% | 43.64% | 61.02% | 50.85%
2025-08-18 | 57.38% | 45.36% | 60.66% | 27.32% | 2025-07-21 | 43.9% | 45.53% | 43.9% | 21.95% | 2025-10-27 | 54.66% | 49.58% | 61.02% | 56.78%
2025-08-25 | 57.38% | 56.28% | 60.66% | 30.6% | 2025-07-28 | 44.72% | 46.34% | 43.9% | 21.95% | 2025-11-03 | 54.66% | 59.32% | 66.95% | 56.78%
2025-09-01 | 57.38% | 56.28% | 60.66% | 30.6% | 2025-08-04 | 44.72% | 46.34% | 43.9% | 21.95% | 2025-11-10 | 66.1% | 71.61% | 72.88% | 56.78%
2025-09-08 | 57.38% | 60.11% | 60.66% | 36.61% | 2025-08-11 | 44.72% | 46.34% | 43.9% | 23.58% | 2025-11-17 | 66.1% | 72.03% | 72.88% | 56.78%
2025-09-15 | 57.38% | 60.11% | 60.66% | 36.61% | 2025-08-18 | 44.72% | 46.34% | 43.9% | 23.58% | 2025-11-24 | 66.53% | 72.88% | 78.39% | 56.78%
2025-09-22 | 57.38% | 60.11% | 60.66% | 36.61% | 2025-08-25 | 44.72% | 47.15% | 44.72% | 23.58% | 2025-12-01 | 66.53% | 72.88% | 78.39% | 74.15%
2025-09-29 | 57.38% | 60.11% | 60.66% | 36.61% | 2025-09-01 | 44.72% | 47.15% | 44.72% | 23.58% | 2025-12-08 | 66.53% | 72.88% | 78.81% | 74.15%
2025-10-06 | 57.92% | 61.2% | 60.66% | 36.61% | 2025-09-08 | 44.72% | 47.15% | 44.72% | 41.46% | 2025-12-15 | 67.37% | 72.88% | 78.81% | 74.15%
2025-10-13 | 57.92% | 61.2% | 61.75% | 48.63% | 2025-09-15 | 44.72% | 47.15% | 44.72% | 41.46% | 2025-12-22 | 67.37% | 72.88% | 79.24% | 74.15%
2025-10-20 | 61.75% | 61.2% | 61.75% | 48.63% | 2025-09-22 | 44.72% | 47.15% | 44.72% | 41.46% | 2025-12-29 | 68.64% | 72.88% | 79.24% | 74.15%
2025-10-27 | 65.57% | 65.03% | 61.75% | 52.46% | 2025-09-29 | 44.72% | 47.15% | 44.72% | 42.28% | 2026-01-05 | 68.64% | 72.88% | 79.66% | 74.15%
2025-11-03 | 65.57% | 68.85% | 65.57% | 52.46% | 2025-10-06 | 44.72% | 47.15% | 44.72% | 42.28% | 2026-01-12 | 68.64% | 72.88% | 79.66% | 74.15%
2025-11-10 | 72.13% | 74.32% | 69.95% | 52.46% | 2025-10-13 | 46.34% | 48.78% | 44.72% | 42.28% | 2026-01-19 | 68.64% | 72.88% | 79.66% | 74.15%
2025-11-17 | 72.13% | 74.86% | 69.95% | 52.46% | 2025-10-20 | 47.97% | 53.66% | 44.72% | 43.9% | 2026-01-26 | 68.64% | 72.88% | 80.08% | 74.15%
2025-11-24 | 74.32% | 75.41% | 73.77% | 52.46% | 2025-10-27 | 49.59% | 53.66% | 44.72% | 45.53% | 2026-02-02 | 68.64% | 73.73% | 80.08% | 74.58%
2025-12-01 | 74.32% | 75.96% | 73.77% | 64.48% | 2025-11-03 | 50.41% | 56.1% | 44.72% | 45.53% | 2026-02-09 | 68.64% | 73.73% | 80.08% | 74.58%
2025-12-08 | 75.41% | 79.78% | 73.77% | 69.4% | 2025-11-10 | 56.91% | 60.98% | 55.28% | 49.59% | 2026-02-16 | 68.64% | 73.73% | 80.08% | 84.75%
2025-12-15 | 77.05% | 81.97% | 74.32% | 75.41% | 2025-11-17 | 56.91% | 64.23% | 55.28% | 49.59% | 2026-02-23 | 68.64% | 73.73% | 80.08% | 86.86%
2025-12-22 | 77.6% | 81.97% | 75.96% | 75.41% | 2025-11-24 | 65.04% | 72.36% | 55.28% | 49.59% | 2026-03-02 | 68.64% | 74.58% | 80.08% | 88.14%
2025-12-29 | 86.89% | 82.51% | 76.5% | 75.41% | 2025-12-01 | 74.8% | 80.49% | 55.28% | 58.54% | 2026-03-09 | 68.64% | 74.58% | 80.08% | 88.14%
2026-01-05 | 86.89% | 82.51% | 77.05% | 75.96% | 2025-12-08 | 84.55% | 88.62% | 61.79% | 78.05% | 2026-03-16 | 68.64% | 74.58% | 80.08% | 88.14%
2026-01-12 | 86.89% | 83.61% | 78.14% | 75.96% | 2025-12-15 | 93.5% | 92.68% | 61.79% | 86.18% | 2026-03-23 | 68.64% | 75.42% | 80.08% | 88.14%
2026-01-19 | 86.89% | 85.79% | 81.97% | 75.96% | 2025-12-22 | 98.37% | 92.68% | 71.54% | 86.18% | 2026-03-30 | 68.64% | 75.42% | 80.08% | 88.14%
2026-01-26 | 86.89% | 85.79% | 86.89% | 75.96% | 2025-12-29 | 100% | 92.68% | 80.49% | 86.18% | 2026-04-06 | 68.64% | 75.42% | 80.08% | 88.14%
2026-02-02 | 93.44% | 92.35% | 86.89% | 75.96% | 2026-01-05 | 100% | 93.5% | 89.43% | 89.43% | 2026-04-13 | 68.64% | 75.85% | 80.08% | 88.14%
2026-02-09 | 93.44% | 93.44% | 86.89% | 75.96% | 2026-01-12 | 100% | 93.5% | 93.5% | 89.43% | 2026-04-20 | 68.64% | 75.85% | 80.08% | 89.83%
2026-02-16 | 93.44% | 93.44% | 86.89% | 84.15% | 2026-01-19 | 100% | 94.31% | 98.37% | 89.43% | 2026-04-27 | 68.64% | 75.85% | 80.08% | 89.83%
2026-02-23 | 100% | 93.44% | 86.89% | 84.15% | 2026-01-26 | 100% | 94.31% | 100% | 89.43% | Grand Total
Grand Total |  |  |  |  | 2026-02-02 | 100% | 94.31% | 100% | 89.43%
[5 empty] | 2026-02-09 | 100% | 94.31% | 100% | 89.43%
[5 empty] | 2026-02-16 | 100% | 94.31% | 100% | 89.43%
[5 empty] | 2026-02-23 | 100% | 94.31% | 100% | 89.43%
[5 empty] | 2026-03-02 | 100% | 96.75% | 100% | 89.43%
[5 empty] | 2026-03-09 | 100% | 99.19% | 100% | 89.43%
[5 empty] | 2026-03-16 | 100% | 99.19% | 100% | 89.43%
[5 empty] | 2026-03-23 | 100% | 99.19% | 100% | 89.43%
[5 empty] | 2026-03-30 | 100% | 99.19% | 100% | 89.43%
[5 empty] | 2026-04-06 | 100% | 100% | 100% | 89.43%
[5 empty] | 2026-04-13 | 100% | 100% | 100% | 89.43%
[5 empty] | 2026-04-20 | 100% | 100% | 100% | 98.37%
[5 empty] | 2026-04-27 | 100% | 100% | 100% | 98.37%
[5 empty] | 2026-05-04 | 100% | 100% | 100% | 98.37%
[5 empty] | 2026-05-11 | 100% | 100% | 100% | 100%
[5 empty] | 2026-05-18 | 100% | 100% | 100% | 100%
[5 empty] | 2026-05-25 | 100% | 100% | 100% | 100%
Grand Total
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.

## S-Curve Monthly
Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals
2025-02-01 | 0% | 0% | 0% | 0% | 2025-03-01 | 13.82% | 14.63% | 13.82% | 13.82% | 2025-02-01 | 0% | 0% | 0% | 0%
2025-03-01 | 20.22% | 14.75% | 8.197% | 8.197% | 2025-04-01 | 25.2% | 26.02% | 13.82% | 13.82% | 2025-03-01 | 30.08% | 9.322% | 0% | 0.4237%
2025-04-01 | 22.95% | 25.68% | 21.31% | 9.836% | 2025-05-01 | 41.46% | 32.52% | 25.2% | 15.45% | 2025-04-01 | 31.36% | 24.15% | 19.92% | 4.661%
2025-05-01 | 31.69% | 27.32% | 24.04% | 15.3% | 2025-06-01 | 43.9% | 42.28% | 41.46% | 15.45% | 2025-05-01 | 43.22% | 30.08% | 26.69% | 12.71%
2025-06-01 | 45.9% | 34.43% | 32.79% | 22.95% | 2025-07-01 | 43.9% | 45.53% | 43.9% | 21.95% | 2025-06-01 | 63.14% | 35.59% | 41.95% | 24.58%
2025-07-01 | 57.38% | 45.36% | 47.54% | 27.32% | 2025-08-01 | 44.72% | 47.15% | 44.72% | 23.58% | 2025-07-01 | 74.15% | 48.31% | 59.32% | 30.51%
2025-08-01 | 57.38% | 56.28% | 60.66% | 30.6% | 2025-09-01 | 44.72% | 47.15% | 44.72% | 41.46% | 2025-08-01 | 74.15% | 61.44% | 80.93% | 31.78%
2025-09-01 | 57.38% | 60.11% | 60.66% | 36.61% | 2025-10-01 | 49.59% | 53.66% | 44.72% | 45.53% | 2025-09-01 | 74.15% | 66.95% | 80.93% | 31.78%
2025-10-01 | 65.57% | 65.03% | 61.75% | 52.46% | 2025-11-01 | 65.04% | 72.36% | 55.28% | 49.59% | 2025-10-01 | 86.02% | 73.73% | 80.93% | 61.44%
2025-11-01 | 74.32% | 75.41% | 73.77% | 52.46% | 2025-12-01 | 100% | 92.68% | 75.61% | 86.18% | 2025-11-01 | 97.88% | 97.03% | 98.31% | 61.44%
2025-12-01 | 86.89% | 82.51% | 75.96% | 75.41% | 2026-01-01 | 100% | 94.31% | 100% | 89.43% | 2025-12-01 | 100% | 97.03% | 99.15% | 78.81%
2026-01-01 | 86.89% | 85.79% | 86.89% | 75.96% | Grand Total |  |  |  |  | Grand Total
2026-02-01 | 100% | 93.44% | 86.89% | 84.15%
2026-03-01 | 100% | 94.54% | 100% | 84.15%
Grand Total
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.

## DB
Row Labels | Count of DRG ID
Architecture | 123
MEP | 236
Structural | 183
Grand Total | 542
Row Labels | Count of DRG ID | Count of Actual Submission to Client | Count of Actual Approval Date | Discipline | Submission Status | Approval Status
Architecture | 123 | 123 | 123 | Architecture | 100% | 100%
MEP | 236 | 236 | 223 | MEP | 100% | 94.49%
Structural | 183 | 176 | 175 | Structural | 96.17% | 95.63%
Grand Total | 542 | 535 | 521
Speedometer | Value | Pointer | Value
Start | 0 | Value | 95.6284
Initial | 30 | Pointer | 2
Mid | 40 | End | 102.3716
End | 30
Max | 100
Discipline | (All)
Row Labels | Total DRG ID | Submitted | Approved
Electrical | 79 | 79 | 76
ELV | 65 | 65 | 56
Existing Building | 24 | 18 | 18
Fire | 46 | 46 | 46
HVAC | 76 | 76 | 75
MEP | 26 | 26 | 26
New Building | 180 | 179 | 179
PHE | 46 | 46 | 45
Grand Total | 542 | 535 | 521
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Master_Data
S.no | Discipline | Category | DRG ID | Description | MDL Title | Responsible Person | 1st Submission Plan | 1st Submission Plan (Before changes in scope) | Actual Submission to Client | Revised Submission date (Plan) | Actual Revised submission | Planned Approval Date | Actual Approval Date | Planned Hard copy Sub.dates | Actual Hard copy sub.dates | Dependency
1 | MEP | PHE | WLH/KEC/SIEC/SEWAGE/BASEMENT/00 | Basement | PHE BASEMENT SEWARAGE FLOOR PLAN | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-04 | 2025-04-19 | 2025-05-31 | 2025-04-26
2 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/BASEMENT/00 | Basement | SANITARY & DRAINAGE BASEMENT CIELING PLAN | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-04 | 2025-04-19 | 2025-05-31 | 2025-04-26
3 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/GF FL/00 | Ground Floor | PHE WATER SUPPLY GROUND FLOOR PLAN | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
4 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/GF FL/00 | Ground Floor | SANITARY & DRAINAGE GROUND CIELING PLAN | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
5 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/1ST FL/00 | First Floor | PHE WATER SUPPLY 1ST FLOOR PLAN | Aashish | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
6 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/1ST FL/00 | First Floor | SANITARY & DRAINAGE 1ST CIELING PLAN | Aashish | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
7 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/2ND FL/00 | Second Floor | PHE WATER SUPPLY 2ND FLOOR PLAN | Aashish | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 | 2025-04-04 | 2025-11-13 | 2025-12-04 | 2025-11-20
8 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/2ND FL/00 | Second Floor | SANITARY & DRAINAGE 2ND CIELING PLAN | Aashish | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 | 2025-04-04 | 2025-11-13 | 2025-12-04 | 2025-11-20
9 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/3RD FL/00 | Third Floor | PHE WATER SUPPLY 3RD FLOOR PLAN | Aashish | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
10 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/3RD FL/00 | Third Floor | SANITARY & DRAINAGE 3RD CIELING PLAN | Aashish | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
11 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/4TH FL/00 | Fourth Floor | PHE WATER SUPPLY 4TH FLOOR PLAN | Aashish | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 | 2025-04-04 | 2025-05-27 | 2025-06-04 | 2025-06-03
12 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/4TH FL/00 | Fourth Floor | SANITARY & DRAINAGE 4TH CIELING PLAN | Aashish | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 | 2025-04-04 | 2025-06-01 | 2025-06-04 | 2025-06-08
13 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/5TH FL/00 | Fifth Floor | PHE WATER SUPPLY 5TH FLOOR PLAN | Aashish | 2025-05-29 | 2025-05-29 | 2025-07-02 | 2025-06-10 | 2025-08-08 | 2025-06-17 | 2025-10-16 | 2025-06-24
14 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/5TH FL/00 | Fifth Floor | SANITARY & DRAINAGE 5TH CIELING PLAN | Aashish | 2025-05-29 | 2025-05-29 | 2025-07-02 | 2025-06-10 | 2025-08-08 | 2025-06-17 | 2025-10-16 | 2025-06-24
15 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/6TH FL/00 | Sixth Floor | PHE WATER SUPPLY 6TH FLOOR PLAN | Aashish | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
16 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/6TH FL/00 | Sixth Floor | SANITARY & DRAINAGE 6TH CIELING PLAN | Aashish | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
17 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/7TH FL/00 | Seventh Floor | PHE WATER SUPPLY 7TH FLOOR PLAN | Aashish | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
18 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/7TH FL/00 | Seventh Floor | SANITARY & DRAINAGE 7TH CIELING PLAN | Aashish | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
19 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/8TH FL/00 | Eighth Floor | GFC PHE WATER SUPPLY 8TH FLOOR PLAN | Aashish | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
20 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/8TH FL/00 | Eighth Floor | SANITARY & DRAINAGE 8TH CIELING PLAN | Aashish | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
21 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/9TH FL/00 | Ninth floor | PHE WATER SUPPLY 9th FLOOR PLAN | Aashish | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
22 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/9TH FL/00 | Ninth floor | SANITARY & DRAINAGE 9th CIELING PLAN | Aashish | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
23 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/10TH FL/00 | Tenth Floor | PHE WATER SUPPLY 10th FLOOR PLAN | Aashish | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
24 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/10TH FL/00 | Tenth Floor | SANITARY & DRAINAGE 10th CIELING PLAN | Aashish | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
25 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/TERRACE FL/00 | Terrace floor | PHE WATER SUPPLY TERRACE PLAN | Aashish | 2025-11-15 | 2025-07-28 | 2025-11-13 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
26 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/TRRRACE FL/00 | Terrace floor | SANITARY & DRAINAGE TERRACE PLAN | Aashish | 2025-11-15 | 2025-07-28 | 2025-11-13 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
27 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/MUMTY TERRACE FL/00 | Terrace floor | SANITARY & DRAINAGE MUMTY TERRACE PLAN | Aashish | 2025-11-15 | 2025-07-28 | 2025-11-25 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
28 | MEP | PHE | WLH/KEC/SIEC/PHE/INFRA/EXTSEWERAGE/00 | External | PHE EXTERNAL SEWERAGE LAYOUT | Aashish | 2025-03-15 | 2025-03-15 | 2025-11-05 | 2025-05-22 | 2025-09-02 | 2025-05-29 | 2026-02-18 | 2025-06-05
29 | MEP | PHE | WLH/KEC/SIEC/PHE/INFRA/00 | External | PHE EXTERNAL CO-ORDINATED LAYOUT | Aashish | 2025-03-15 | 2025-03-15 | 2025-11-05 | 2025-05-22 | 2025-09-02 | 2025-05-29 | 2026-02-18 | 2025-06-05
30 | MEP | PHE | WLH/KEC/SIEC/PHE/INFRA WATER SUPPLY/00 | External | PHE INFRASTRUCTURE WATER SUPPLY LAYOUT | Aashish | 2025-03-15 | 2025-03-15 | 2025-11-05 | 2025-05-22 | 2025-09-02 | 2025-05-29 | 2026-02-18 | 2025-06-05
31 | MEP | PHE | WLH/KEC/SIEC/PHE/INFRA/EXTSTORMWATER/00 | External | PHE EXTERNAL STORM WATER LAYOUT | Aashish | 2025-03-15 | 2025-03-15 | 2025-11-05 | 2025-05-22 | 2025-09-02 | 2025-05-29 | 2026-02-18 | 2025-06-05
32 | MEP | PHE | WLH/KEC/SIEC/PHE/INFRA/RECHARGE BOREWELL00 | External | PHE EXTERNAL RECHARGE BOREWELL DRAWING | Aashish | 2025-03-15 | 2025-03-15 | 2025-11-05 | 2025-05-22 | 2025-09-02 | 2025-05-29 | 2026-02-18 | 2025-06-05
33 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY SLD/00 | Common | WATER SUPPLY SINGLE LINE DIAGRAM | Aashish | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-05-22 | 2025-09-02 | 2025-05-29 | 2026-02-27 | 2025-06-05
34 | MEP | PHE | WLH/KEC/SIEC/SANITARY DRAINAGE/SLD/00 | Common | SANITARY DRAINAGE SINGLE LINE DIAGRAM | Aashish | 2025-06-18 | 2025-06-18 | 2025-08-29 | 2025-05-22 |  | 2025-06-25 | 2025-08-29 | 2025-07-02
35 | MEP | PHE | WLH/KEC/SIEC/RAIN WATER DRAINAGE/SLD/00 | Common | RAINWATER DRAINAGE SINGLE LINE DIAGRAM | Aashish | 2025-06-18 | 2025-06-18 | 2025-08-29 | 2025-05-22 |  | 2025-06-25 | 2025-08-29 | 2025-07-02
36 | MEP | PHE | WLH/KEC/SIEC/OWT/PHE/00 | Common | OVERHEAD WATER TANK & EQUIPMENT ROOM DETAILS | Aashish | 2025-06-18 | #REF! | 2025-11-25 | #REF! |  | 2025-06-25 |  | 2025-07-02
37 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/BASEMENT/DEWATERING/00 | Basement | BASEMENT DEWATERING LAYOUT | Aashish | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-05-22 |  | 2025-05-29 | 2025-05-31 | 2025-06-05
38 | MEP | PHE | WLH/KEC/SIEC/PHE/CONST. DETAILS/00 | Common | PHE TYPICAL STANDARD CONSTRUCTION DETAILS | Aashish | 2025-03-15 | 2025-03-15 | 2025-08-29 | 2025-05-22 |  | 2025-05-29 | 2025-08-29 | 2025-06-05
39 | MEP | PHE | WLH/KEC/SIEC/WATER SUPPLY/EXTERNAL/00 | Common | PHE WATER SUPPLY EXTERNAL LAYOUT | Aashish | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-05-22 | 2025-09-02 | 2025-05-29 | 2026-02-18 | 2025-06-05
40 | MEP | PHE | WLH/KEC/SIEC/PHE/BASEMENT TOILET/00 | Basement | PHE BASEMENT TOILET SEWAGE LAYOUT | Aashish | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-05-22 |  | 2025-05-29 | 2025-05-31 | 2025-06-05
41 | MEP | PHE | WLH/KEC/SIEC/DRAINAGE/SUMP DETAIL/00 | Common | PHE SUMP DETAILS LAYOUT | Aashish | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-05-22 |  | 2025-05-29 | 2025-05-31 | 2025-06-05
42 | MEP | PHE | WLH/KEC/STP/BASEMENT/00 | Common | STP DESIGN DRAWINGS | Aashish | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-04-01 | 2025-03-15 | 2025-04-14 | 2025-04-14 | 2025-04-21
43 | MEP | PHE | WLH/KEC/STP/SCHEMATIC | Common | STP DESIGN SCHEMATIC | Aashish | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-04-01 | 2025-03-15 | 2025-04-10 | 2025-04-10 | 2025-04-17
44 | MEP | PHE | WLH/KEC/ETP/SCHEMATIC | Common | ETP DESIGN SCHEMATIC | Aashish | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-04-01 | 2025-03-15 | 2025-04-10 | 2025-04-10 | 2025-04-17
45 | MEP | PHE | WLH/KEC/ETP/BASEMENT/00 | Common | ETP DESIGN DRAWINGS | Aashish | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-04-01 | 2025-03-15 | 2025-04-10 | 2025-04-10 | 2025-04-17
46 | MEP | PHE | WLH/KEC/SIEC/PHE/IRRIGATION/00 | External | IRRIGATION LAYOUT | Aashish | 2025-03-15 | 2025-03-15 | 2025-11-05 | 2025-05-22 | 2025-09-02 | 2025-05-29 | 2026-02-18 | 2025-06-05
47 | MEP | Electrical | WLH/KEC/SIEC/ELEC/INFRA/00 | External | ELECTRICAL INFRASTRUCTURE LAYOUT | T Surya | 2025-03-15 | 2025-03-15 | 2025-11-05 | 2025-05-22 | 2025-08-29 | 2025-06-02 | 2026-03-06 | 2025-06-09
48 | MEP | Electrical | WLH/KEC/SIEC/ELEC/DG/00 | External | ELECTRICAL DG SET DRAWING WITH DG STACK | T Surya | 2025-12-31 | 2025-03-15 | 2026-02-02 | 2025-05-22 | 2025-04-07 | 2025-06-02 | 2026-03-06 | 2025-06-09 |  | Dependent on DG Vendor
49 | MEP | Electrical | WLH/KEC/SIEC/ELEC/EXTERNAL LIGHTING/00 | External | ELECTRICAL EXTERNAL LIGHTING LAYOUT | T Surya | 2025-07-15 | 2025-07-15 | 2025-11-10 | 2025-07-31 |  | 2025-08-11 |  | 2025-08-18
50 | MEP | Electrical | WLH/KEC/SIEC/ELEC/SUBSTATION/00 | External | ELECTRICAL SUBSTATION LAYOUT | T Surya | 2025-06-15 | 2025-06-15 | 2025-11-05 | 2025-07-01 | 2025-08-29 | 2025-07-10 | 2026-03-06 | 2025-07-17
51 | MEP | Electrical | WLH/KEC/SIEC/ELEC/EARTHING GRID SCHEMATIC/00 | Common | EARTHING GRID SCHEMATIC LAYOUT | T Surya | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-05-22 | 2025-08-29 | 2025-06-02 |  | 2025-06-09
52 | MEP | Electrical | WLH/KEC/SIEC/ELECTRICAL/DBR/00 | Common | ELECTRICAL DBR COMMENTARY | T Surya | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-05-22 | 2025-04-04 | 2025-06-02 | 2025-05-31 | 2025-06-09
53 | MEP | Electrical | WLH/KEC/SIEC/ELEC/MUMTY TERRACE SOLAR/00 | Above Roof | ELECTRICAL SOLAR SYSTEM F PLAN | T Surya | 2025-07-15 | 2025-07-15 | 2025-11-10 | 2025-07-31 | 2025-04-04 | 2025-08-11 | 2026-02-06 | 2025-08-18
54 | MEP | Electrical | WLH/KEC/SIEC/ELEC/EQUIPMENT & EARTHING/00 | Common | ELECTRICAL EQUIPMENT LAYOUT WITH EARTHING LAYOUT | T Surya | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-05-22 | 2025-04-04 | 2025-06-02 | 2026-02-27 | 2025-06-09
55 | MEP | Electrical | WLH/KEC/SIEC/ELEC/HEIGHT SCHEDULE/00 | Common | TYPICAL ELECTRICAL INSTALLATION DETAILS WITH HEIGHT SCHEDULE | T Surya | 2025-07-15 | 2025-07-15 | 2025-03-15 | 2025-07-31 | 2025-04-04 | 2025-08-11 | 2025-05-31 | 2025-08-18
56 | MEP | Electrical | WLH/KEC/SIEC/ELEC/EXTCT/00 | Common | ELECTRICAL EXTERNAL CABLE TRAY LAYOUT | T Surya | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-05-22 | 2025-08-29 | 2025-06-02 | 2026-02-27 | 2025-06-09
57 | MEP | Electrical | WLH/KEC/SIEC/ELEC/MAIN ROOM DETAILED LAYOUT/00 | Common | MAIN ELECTRICAL ROOM DETAILED LAYOUT | T Surya | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-05-22 | 2025-08-29 | 2025-06-02 | 2026-02-27 | 2025-06-09
58 | MEP | Electrical | WLH/KEC/SIEC/ELEC/UPS/00 | Common | ELECTRICAL UPS DRAWING | T Surya | 2025-12-31 | 2025-05-15 | 2026-02-02 | 2026-01-16 |  | 2026-01-27 | 2026-02-27 | 2026-02-03 |  | Vendor shortlisted, PO to be release
59 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/BASEMENT/01 | Basement | POWER LAYOUT WITH SLD BASEMNET PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-04 | 2025-04-19 | 2025-05-31 | 2025-04-26
60 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/BASEMENT/02 | Basement | POWER LAYOUT WITH SLD BASEMNET PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-04 | 2025-04-19 | 2025-05-31 | 2025-04-26
61 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/BASEMENT/03 | Basement | POWER LAYOUT WITH SLD BASEMNET PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-04 | 2025-04-19 | 2025-05-31 | 2025-04-26
62 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/BASEMENT/00 | Basement | LIGHTING LAYOUT WITH SLD BASEMENT PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-07 | 2025-04-19 | 2025-05-31 | 2025-04-26
63 | MEP | Electrical | WLH/KEC/SIEC/ELEC/BASEMENT/00 | Basement | ELECTRICAL BASEMENT CABLE TRAY LAYOUT | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-04-07 | 2025-04-19 | 2025-05-31 | 2025-04-26
64 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/GR FL/01 | Ground Floor | POWER LAYOUT WITH SLD GROUND FLOOR PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
65 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/GR FL/02 | Ground Floor | POWER LAYOUT WITH SLD GROUND FLOOR PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
66 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/GR FL/03 | Ground Floor | POWER LAYOUT WITH SLD GROUND FLOOR PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
67 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/GR FL/00 | Ground Floor | LIGHTING LAYOUT WITH SLD GROUND FLOOR PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
68 | MEP | Electrical | WLH/KEC/SIEC/ELEC/GFCT/00 | Ground Floor | ELECTRICAL GROUND FLOOR CABLE TRAY LAYOUT | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
69 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/1ST FL/01 | First Floor | POWER LAYOUT WITH SLD 1ST FLOOR PLAN | T Surya | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
70 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/1ST FL/02 | First Floor | POWER LAYOUT WITH SLD 1ST FLOOR PLAN | T Surya | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
71 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/1ST FL/03 | First Floor | POWER LAYOUT WITH SLD 1ST FLOOR PLAN | T Surya | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
72 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/1ST FL/00 | First Floor | LIGHTING LAYOUT WITH SLD 1ST FLOOR PLAN | T Surya | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
73 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWERCONDUIT/2ND FL/01 | Second Floor | POWER LAYOUT WITH SLD 2ND FLOOR PLAN | T Surya | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
74 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWERCONDUIT/2ND FL/02 | Second Floor | POWER LAYOUT WITH SLD 2ND FLOOR PLAN | T Surya | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
75 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWERCONDUIT/2ND FL/03 | Second Floor | POWER LAYOUT WITH SLD 2ND FLOOR PLAN | T Surya | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
76 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/2ND FL/00 | Second Floor | LIGHTING LAYOUT WITH SLD 2ND FLOOR PLAN | T Surya | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
77 | MEP | Electrical | WLH/KEC/SIEC/ELEC/2NDCT/00 | Second Floor | ELECTRICAL 2ND FLOOR CABLE TRAY LAYOUT | T Surya | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
78 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/3RD FL/01 | Third Floor | POWER LAYOUT WITH SLD 3RD FLOOR PLAN | T Surya | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
79 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/3RD FL/02 | Third Floor | POWER LAYOUT WITH SLD 3RD FLOOR PLAN | T Surya | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
80 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/3RD FL/03 | Third Floor | POWER LAYOUT WITH SLD 3RD FLOOR PLAN | T Surya | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
81 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/3RD FL/00 | Third Floor | LIGHTING LAYOUT WITH SLD 3RD FLOOR PLAN | T Surya | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
82 | MEP | Electrical | WLH/KEC/SIEC/ELEC/3RDCT/00 | Third Floor | ELECTRICAL 3RD FLOOR CABLE TRAY LAYOUT | T Surya | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
83 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/4TH FL/01 | Fourth Floor | POWER LAYOUT WITH SLD 4TH FLOOR PLAN | T Surya | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
84 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/4TH FL/02 | Fourth Floor | POWER LAYOUT WITH SLD 4TH FLOOR PLAN | T Surya | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
85 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/4TH FL/03 | Fourth Floor | POWER LAYOUT WITH SLD 4TH FLOOR PLAN | T Surya | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
86 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/4TH FL/00 | Fourth Floor | LIGHTING LAYOUT WITH SLD 4TH FLOOR PLAN | T Surya | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
87 | MEP | Electrical | WLH/KEC/SIEC/ELEC/4THCT/00 | Fourth Floor | ELECTRICAL 4TH FLOOR CABLE TRAY LAYOUT | T Surya | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
88 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/5TH FL/01 | Fifth Floor | POWER LAYOUT WITH SLD 5TH FLOOR PLAN | T Surya | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
89 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/5TH FL/02 | Fifth Floor | POWER LAYOUT WITH SLD 5TH FLOOR PLAN | T Surya | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
90 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/5TH FL/03 | Fifth Floor | POWER LAYOUT WITH SLD 5TH FLOOR PLAN | T Surya | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
91 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/5TH FL/00 | Fifth Floor | LIGHTING LAYOUT WITH SLD 5TH FLOOR PLAN | T Surya | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
92 | MEP | Electrical | WLH/KEC/SIEC/ELEC/5THCT/00 | Fifth Floor | ELECTRICAL 5TH FLOOR CABLE TRAY LAYOUT | T Surya | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
93 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/6TH FL/01 | Sixth Floor | POWER LAYOUT WITH SLD 6TH FLOOR PLAN | T Surya | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
94 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/6TH FL/02 | Sixth Floor | POWER LAYOUT WITH SLD 6TH FLOOR PLAN | T Surya | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
95 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/6TH FL/03 | Sixth Floor | POWER LAYOUT WITH SLD 6TH FLOOR PLAN | T Surya | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
96 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/6TH FL/00 | Sixth Floor | LIGHTING LAYOUT WITH SLD 6TH FLOOR PLAN | T Surya | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
97 | MEP | Electrical | WLH/KEC/SIEC/ELEC/6THCT/00 | Sixth Floor | ELECTRICAL 6TH FLOOR CABLE TRAY LAYOUT | T Surya | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
98 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/7TH FL/01 | Seventh Floor | POWER LAYOUT WITH SLD 7TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
99 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/7TH FL/02 | Seventh Floor | POWER LAYOUT WITH SLD 7TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
100 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/7TH FL/03 | Seventh Floor | POWER LAYOUT WITH SLD 7TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
101 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/7TH FL/00 | Seventh Floor | LIGHTING LAYOUT WITH SLD 7TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
102 | MEP | Electrical | WLH/KEC/SIEC/ELEC/7THCT/00 | Seventh Floor | ELECTRICAL 7TH FLOOR CABLE TRAY LAYOUT | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
103 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/8TH FL/01 | Eighth Floor | POWER LAYOUT WITH SLD 8TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
104 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/8TH FL/02 | Eighth Floor | POWER LAYOUT WITH SLD 8TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
105 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/8TH FL/03 | Eighth Floor | POWER LAYOUT WITH SLD 8TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
106 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/8TH FL/00 | Eighth Floor | LIGHTING LAYOUT WITH SLD 8TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
107 | MEP | Electrical | WLH/KEC/SIEC/ELEC/8THCT/00 | Eighth Floor | ELECTRICAL 8TH FLOOR CABLE TRAY LAYOUT | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
108 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/9TH FL/01 | Ninth floor | POWER LAYOUT WITH SLD 9TH FLOOR PLAN | T Surya | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
109 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/9TH FL/02 | Ninth floor | POWER LAYOUT WITH SLD 9TH FLOOR PLAN | T Surya | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
110 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/9TH FL/03 | Ninth floor | POWER LAYOUT WITH SLD 9TH FLOOR PLAN | T Surya | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
111 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/9TH FL/00 | Ninth floor | LIGHTING LAYOUT WITH SLD 9TH FLOOR PLAN | T Surya | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
112 | MEP | Electrical | WLH/KEC/SIEC/ELEC/9TH CT/00 | Ninth floor | ELECTRICAL 9TH FLOOR CABLE TRAY LAYOUT | T Surya | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
113 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/10TH FL/01 | Tenth Floor | POWER LAYOUT WITH SLD 10TH FLOOR PLAN | T Surya | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
114 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/10TH FL/02 | Tenth Floor | POWER LAYOUT WITH SLD 10TH FLOOR PLAN | T Surya | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
115 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/10TH FL/03 | Tenth Floor | POWER LAYOUT WITH SLD 10TH FLOOR PLAN | T Surya | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
116 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/10TH FL/00 | Tenth Floor | LIGHTING LAYOUT WITH SLD 10TH FLOOR PLAN | T Surya | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
117 | MEP | Electrical | WLH/KEC/SIEC/ELEC/10THCT/00 | Tenth Floor | ELECTRICAL 10TH FLOOR CABLE TRAY LAYOUT | T Surya | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
118 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER/TERRACE/00 | Terrace floor | POWER LAYOUT WITH SLD TERRACE FLOOR PLAN | T Surya | 2025-11-15 | 2025-07-28 | 2025-11-13 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
119 | MEP | Electrical | WLH/KEC/SIEC/ELEC/POWER CONDUIT/TERRACE FL/00 | Terrace floor | POWER LAYOUT WITH SLD TERRACE FLOOR PLAN | T Surya | 2025-11-15 | 2025-07-28 | 2025-11-13 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
120 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/TERRACE FL/00 | Terrace floor | LIGHTING LAYOUT WITH SLD TERRACE FLOOR PLAN | T Surya | 2025-11-15 | 2025-07-28 | 2025-11-13 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
121 | MEP | Electrical | WLH/KEC/SIEC/ELEC/TERRACECT/00 | Terrace floor | ELECTRICAL TERRACE CABLE TRAY LAYOUT | T Surya | 2025-11-15 | 2025-07-28 | 2025-11-13 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
122 | MEP | Electrical | WLH/KEC/SIEC/ELEC/SCHEMATIC DIAGRAM/00 | Common | ELECTRICAL SINGLE LINE DIAGRAM | T Surya | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-28 | 2025-04-16 | 2025-05-05 | 2025-05-31 | 2025-05-12
123 | MEP | Electrical | WLH/KEC/SIEC/ELEC/LT ARRESTOR/00 | Terrace floor | LAYOUT OF LIGHTNING ARRESTOR | T Surya | 2025-07-25 | 2025-07-25 | 2025-10-10 | 2025-08-06 |  | 2025-08-13 | 2026-02-18 | 2025-08-20
124 | MEP | Electrical | WLH/KEC/SIEC/ELEC/AVIATION/00 | Terrace floor | LAYOUT OF AVIATION OBSTRUCTION LIGHT | T Surya | 2025-07-25 | 2025-07-25 | 2025-10-10 | 2025-08-06 |  | 2025-08-13 | 2026-02-18 | 2025-08-20
125 | MEP | Electrical | WLH/KEC/SIEC/ELEC/EXTPOWER/00 | External | ELECTRICAL EXTERNAL POWER LAYOUT | T Surya | 2025-07-25 | 2025-07-25 | 2025-11-10 | 2025-08-06 |  | 2025-08-13 |  | 2025-08-20
126 | MEP | ELV | WLH/KEC/SIEC/ELV/INFRA/00 | External | ELV INFRASTRUCTURE LAYOUT | T Surya | 2025-03-15 | 2025-03-15 | 2025-07-23 | 2025-04-01 |  | 2025-04-10 | 2026-04-20 | 2025-04-17
127 | MEP | ELV | WLH/KEC/SIEC/ELV/CCTV/00 | External | ELV CCTV LAYOUT | T Surya | 2025-11-30 | 2025-03-15 | 2025-11-10 | 2025-12-16 |  | 2025-12-25 | 2026-04-20 | 2026-01-01
128 | MEP | ELV | WLH/KEC/SIEC/ELV/DBR/00 | Common | ELV DBR COMMENTARY | T Surya | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-04-16 |  | 2025-04-25 | 2025-03-31 | 2025-05-02
129 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/GR FL/00 | Ground Floor | RODENT REPELLENT SYSTEM GR FLOOR | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 |  | 2025-04-22 | 2025-06-04 | 2025-04-29
130 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/1ST FL/00 | First Floor | RODENT REPELLENT SYSTEM 1ST FLOOR | T Surya | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
131 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/2ND FL/00 | Second Floor | RODENT REPELLENT SYSTEM 2ND FLOOR | T Surya | 2025-10-30 | 2025-03-31 | 2025-11-05 | 2025-04-12 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
132 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/3RD FL/00 | Third Floor | RODENT REPELLENT SYSTEM 3RD FLOOR | T Surya | 2025-10-25 | 2025-03-31 | 2025-10-28 | 2025-11-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
133 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/4TH FL/00 | Fourth Floor | RODENT REPELLENT SYSTEM 4TH FLOOR | T Surya | 2025-03-31 | 2025-03-31 | 2025-05-19 | 2025-04-16 |  | 2025-04-25 | 2025-06-04 | 2025-05-02
134 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/5TH FL/00 | Fifth Floor | RODENT REPELLENT SYSTEM 5TH FLOOR | T Surya | 2025-03-31 | 2025-03-31 | 2025-07-02 | 2025-04-16 |  | 2025-04-25 | 2025-10-16 | 2025-05-02
135 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/6TH FL/00 | Sixth Floor | RODENT REPELLENT SYSTEM 6TH FLOOR | T Surya | 2025-03-31 | 2025-03-31 | 2025-07-09 | 2025-04-16 |  | 2025-04-25 | 2025-10-16 | 2025-05-02
136 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/7TH FL/00 | Seventh Floor | RODENT REPELLENT SYSTEM 7TH FLOOR | T Surya | 2025-03-31 | 2025-03-31 | 2025-08-27 | 2025-04-16 |  | 2025-04-25 | 2025-10-16 | 2025-05-02
137 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/8TH FL/00 | Eighth Floor | RODENT REPELLENT SYSTEM 8TH FLOOR | T Surya | 2025-03-31 | 2025-03-31 | 2025-08-30 | 2025-04-16 |  | 2025-04-25 | 2025-10-29 | 2025-05-02
138 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/9TH FL/00 | Ninth floor | RODENT REPELLENT SYSTEM 9TH FLOOR | T Surya | 2025-03-31 | 2025-03-31 | 2025-07-23 | 2025-04-16 |  | 2025-04-25 | 2025-07-12 | 2025-05-02
139 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/10TH FL/00 | Tenth Floor | RODENT REPELLENT SYSTEM 10TH FLOOR | T Surya | 2025-03-31 | 2025-03-31 | 2025-09-10 | 2025-04-16 |  | 2025-04-25 | 2025-10-16 | 2025-05-02
140 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/TERRACE FL/00 | Terrace floor | RODENT REPELLENT SYSTEM TERRACE FLOOR | T Surya | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-12-02 |  | 2025-12-11 | 2025-10-16 | 2025-12-18
141 | MEP | ELV | WLH/KEC/SIEC/RODENT REPELLENT SYSTEM SLD/ELV/00 | Common | RODENT REPELLENT SYSTEM SLD | T Surya | 2025-12-15 | 2025-03-31 | 2026-03-23 | 2025-12-31 |  | 2026-01-09 |  | 2026-01-16 |  | Dependent on JCI
142 | MEP | ELV | WLH/KEC/SIEC/ELV SLD/00 | Common | ELV NETWORK ARCHITECTURE | T Surya | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-07-31 |  | 2025-08-11 |  | 2025-08-18
143 | MEP | ELV | WLH/KEC/SIEC/ELV/NURSE CALLING SLD/00 | Common | ELV NURSE CALLING SCHEMATIC DIAGRAM | T Surya | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-07-31 |  | 2025-08-11 |  | 2025-08-18
144 | MEP | ELV | WLH/KEC/SIEC/ELV/OPD CALLING SLD/00 | Common | ELV OPD CALLING SCHEMATIC DIAGRAM | T Surya | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-07-31 |  | 2025-08-11 | 2026-04-20 | 2025-08-18
145 | MEP | ELV | WLH/KEC/SIEC/ELV/BMS IO SUMMARY & SLD/00 | Common | ELV BMS IO SUMMARY & SCHEMATIC DIAGRAM | T Surya | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-07-31 |  | 2025-08-11 |  | 2025-08-18
146 | MEP | ELV | WLH/KEC/SIEC/ELV/CCTV SLD/00 | Common | ELV CCTV SCHEMATIC DIAGRAM | T Surya | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-07-31 |  | 2025-08-11 |  | 2025-08-18
147 | MEP | ELV | WLH/KEC/SIEC/ACCESS CONTROL SCHEMATIC/ELV/BASEMENT/00 | Common | ACCESS CONTROL SCHEMATIC PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-04-12 |  | 2025-04-19 | 2026-04-20 | 2025-04-26
148 | MEP | ELV | WLH/KEC/SIEC/ELV/BASEMENT/00 | Basement | Elv Layout BASEMENT PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-04 | 2025-04-19 | 2025-05-31 | 2025-04-26
149 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/BASEMENT/00 | Basement | BMS SYSTEM BASEMENT PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-04 | 2025-04-19 | 2025-05-31 | 2025-04-26
150 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/BASEMENT/00 | Basement | Wi-Fi Heat map BASEMENT PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-04 | 2025-04-19 | 2025-05-31 | 2025-04-26
151 | MEP | ELV | WLH/KEC/SIEC/ELV/GF FL/00 | Ground Floor | ELV Layout GROUND FLOOR PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-04-04 | 2025-04-19 | 2025-06-04 | 2025-04-26
152 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/GF FL/00 | Ground Floor | Wi-Fi Heat map GROUND FLOOR PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 |  | 2025-04-19 | 2025-06-04 | 2025-04-26
153 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/GF FL/00 | Ground Floor | BMS SYSTEM GROUND FLOOR PLAN | T Surya | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 |  | 2025-04-19 | 2025-06-04 | 2025-04-26
154 | MEP | ELV | WLH/KEC/SIEC/ELV/1ST FL/00 | First Floor | ELV Layout 1ST FLOOR PLAN | T Surya | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
155 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/1ST FL/00 | First Floor | Wi-Fi Heat map 1ST FLOOR PLAN | T Surya | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 |  | 2025-11-29 | 2025-12-04 | 2025-12-06
156 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/1ST FL/00 | First Floor | BMS SYSTEM 1ST FLOOR PLAN | T Surya | 2025-11-15 | 2025-04-10 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
157 | MEP | ELV | WLH/KEC/SIEC/ELV/2ND FL/00 | Second Floor | ELV Layout 2ND FLOOR PLAN | T Surya | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
158 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/2ND FL/00 | Second Floor | Wi-Fi Heat map 2ND FLOOR PLAN | T Surya | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
159 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/2ND FL/00 | Second Floor | BMS SYSTEM 2ND FLOOR PLAN | T Surya | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
160 | MEP | ELV | WLH/KEC/SIEC/ELV/3RD FL/00 | Third Floor | ELV Layout 3RD FLOOR PLAN | T Surya | 2025-10-25 | 2025-04-26 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
161 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/3RD FL/00 | Third Floor | Wi-Fi Heat map 3RD FLOOR PLAN | T Surya | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
162 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/3RD FL/00 | Third Floor | BMS SYSTEM 3RD FLOOR PLAN | T Surya | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
163 | MEP | ELV | WLH/KEC/SIEC/ELV/4TH FL/00 | Fourth Floor | ELV Layout 4TH FLOOR PLAN | T Surya | 2025-04-29 | 2025-04-29 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
164 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/4TH FL/00 | Fourth Floor | Wi-Fi Heat map 4TH FLOOR PLAN | T Surya | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
165 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/4TH FL/00 | Fourth Floor | BMS SYSTEM 4TH FLOOR PLAN | T Surya | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
166 | MEP | ELV | WLH/KEC/SIEC/ELV/5TH FL/00 | Fifth Floor | ELV Layout 5TH FLOOR PLAN | T Surya | 2025-05-13 | 2025-05-13 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
167 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/5TH FL/00 | Fifth Floor | Wi-Fi Heat map 5TH FLOOR PLAN | T Surya | 2025-05-13 | 2025-05-13 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
168 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/5TH FL/00 | Fifth Floor | BMS SYSTEM 5TH FLOOR PLAN | T Surya | 2025-05-13 | 2025-05-13 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
169 | MEP | ELV | WLH/KEC/SIEC/ELV/6TH FL/00 | Sixth Floor | ELV Layout 6TH FLOOR PLAN | T Surya | 2025-05-27 | 2025-05-27 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
170 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/6TH FL/00 | Sixth Floor | Wi-Fi Heat map 6TH FLOOR PLAN | T Surya | 2025-05-27 | 2025-05-27 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
171 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/6TH FL/00 | Sixth Floor | BMS SYSTEM 6TH FLOOR PLAN | T Surya | 2025-05-27 | 2025-05-27 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
172 | MEP | ELV | WLH/KEC/SIEC/ELV/7TH FL/00 | Seventh Floor | ELV Layout 7TH FLOOR PLAN | T Surya | 2025-06-13 | 2025-06-13 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
173 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/7TH FL/00 | Seventh Floor | Wi-Fi Heat map 7TH FLOOR PLAN | T Surya | 2025-06-13 | 2025-06-13 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
174 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/7TH FL/00 | Seventh Floor | BMS SYSTEM 7TH FLOOR PLAN | T Surya | 2025-06-13 | 2025-06-13 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
175 | MEP | ELV | WLH/KEC/SIEC/AV SYSTEM/ELV/7TH FL/00 | Seventh Floor | AUDIO VISUAL SYSTEM 7TH FLOOR | T Surya | 2025-06-13 | 2025-06-13 | 2026-03-05 | 2025-07-11 |  | 2025-07-18 |  | 2025-07-25 |  | Dependent on JCI, site team to arrange meeting with client & vendor
176 | MEP | ELV | WLH/KEC/SIEC/ELV/8TH FL/00 | Eighth Floor | ELV Layout 8TH FLOOR PLAN | T Surya | 2025-06-13 | 2025-06-13 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
177 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/8TH FL/00 | Eighth Floor | Wi-Fi Heat map 8TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
178 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/8TH FL/00 | Eighth Floor | BMS SYSTEM 8TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
179 | MEP | ELV | WLH/KEC/SIEC/ELV/9TH FL/00 | Ninth floor | ELV Layout 9TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
180 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/9TH FL/00 | Ninth floor | Wi-Fi Heat map 9TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
181 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/9TH FL/00 | Ninth floor | BMS SYSTEM 9TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
182 | MEP | ELV | WLH/KEC/SIEC/ELV/10TH FL/00 | Tenth Floor | ELV Layout 10TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
183 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/10TH FL/00 | Tenth Floor | Wi-Fi Heat map 10TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
184 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/10TH FL/00 | Tenth Floor | BMS SYSTEM 10TH FLOOR PLAN | T Surya | 2025-06-29 | 2025-06-29 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
185 | MEP | ELV | WLH/KEC/SIEC/AV SYSTEM/ELV/10TH FL/00 | Tenth Floor | AUDIO VISUAL SYSTEM 10TH FLOOR | T Surya | 2025-07-13 | 2025-07-13 | 2026-03-05 | 2025-07-25 |  | 2025-08-01 |  | 2025-08-08 |  | Dependent on JCI, site team to arrange meeting with client & vendor
186 | MEP | ELV | WLH/KEC/SIEC/Heat map/ELV/TERRACE/00 | Terrace floor | Wi-Fi Heat map TERRACE PLAN | T Surya | 2025-11-15 | 2025-07-13 | 2025-11-13 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
187 | MEP | ELV | WLH/KEC/SIEC/ELV/TERRACE/00 | Terrace floor | ELV Layout TERRACE FLOOR PLAN | T Surya | 2025-11-15 | 2025-07-13 | 2025-11-13 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
188 | MEP | ELV | WLH/KEC/SIEC/BMS SYSTEM/ELV/ABOVE TERRACE/00 | Terrace floor | BMS SYSTEM TERRACE PLAN | T Surya | 2025-11-15 | 2025-07-13 | 2025-11-13 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
189 | MEP | ELV | WLH/KEC/SIEC/WATER LEAK DETECTION/ELV/00 | Common | WATER LEAK DETECTION PLAN | T Surya | 2025-12-15 | 2025-07-13 | 2026-03-23 | 2025-08-06 |  | 2025-08-13 |  | 2025-08-20 |  | Dependent on JCI
190 | MEP | ELV | WLH/KEC/SIEC/ELV/BMS ROOM/MISC/00 | Common | ELV BMS ROOM LAYOUT | T Surya | 2025-12-31 | 2025-07-31 | 2026-04-17 | 2025-05-22 |  | 2025-05-29 |  | 2025-06-05 |  | Dependent on JCI, Jci to visit site survey (Existing building)& prepare
191 | MEP | Fire | WLH/KEC/SIEC/FDA/BASEMENT/00 | Basement | FIRE DETECTION & PA DRAWING BASEMENT FLOOR PLAN | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 |  | 2025-04-19 | 2025-05-31 | 2025-04-26
192 | MEP | Fire | WLH/KEC/SIEC/FPS/BASEMENT/00 | Basement | FIRE PROTECTION BASEMENT FLOOR PLAN | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-04 | 2025-04-04 | 2025-05-31 | 2025-04-11
193 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /BASEMENT/00 | Basement | SIGNAGE & FIRE EXTINGUISHER BASEMENT PLAN | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 |  | 2025-04-19 | 2025-05-31 | 2025-04-26
194 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/GR FL/00 | Ground Floor | FIRE DETECTION & PA DRAWING GROUND FLOOR PLAN | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
195 | MEP | Fire | WLH/KEC/SIEC/FPS/GR FL/00 | Ground Floor | FIRE PROTECTION GROUND FLOOR PLAN | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
196 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /GR FL/01 | Ground Floor | SIGNAGE & FIRE EXTINGUISHER GROUND FLOOR PLAN | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
197 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /1ST FL/00 | First Floor | SIGNAGE & FIRE EXTINGUISHER 1ST FLOOR PLAN | Aashish | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-04-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
198 | MEP | Fire | WLH/KEC/SIEC/FDA& PA/1ST FL/00 | First Floor | FIRE DETECTION & PA DRAWING 1ST FLOOR PLAN | Aashish | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-04-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
199 | MEP | Fire | WLH/KEC/SIEC/FPS/1ST FL/00 | First Floor | FIRE PROTECTION 1ST FLOOR PLAN | Aashish | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-04-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
200 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /2ND FL/00 | Second Floor | SIGNAGE & FIRE EXTINGUISHER 2ND FLOOR PLAN | Aashish | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
201 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/2ND FL/00 | Second Floor | FIRE DETECTION & PA DRAWING 2ND FLOOR PLAN | Aashish | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
202 | MEP | Fire | WLH/KEC/SIEC/FPS/2ND FL/00 | Second Floor | FIRE PROTECTION 2ND FLOOR PLAN | Aashish | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
203 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /3RD FL/00 | Third Floor | SIGNAGE & FIRE EXTINGUISHER 3RD FLOOR PLAN | Aashish | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
204 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/3RD FL/00 | Third Floor | FIRE DETECTION & PA DRAWING 3RD FLOOR PLAN | Aashish | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
205 | MEP | Fire | WLH/KEC/SIEC/FPS/3RD FL/00 | Third Floor | FIRE PROTECTION 3RD FLOOR PLAN | Aashish | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
206 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /4TH FL/00 | Fourth Floor | SIGNAGE & FIRE EXTINGUISHER 4TH FLOOR PLAN | Aashish | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
207 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/4TH FL/00 | Fourth Floor | FIRE DETECTION & PA DRAWING 4TH FLOOR PLAN | Aashish | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
208 | MEP | Fire | WLH/KEC/SIEC/FPS/4TH FL/00 | Fourth Floor | FIRE PROTECTION 4TH FLOOR PLAN | Aashish | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
209 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /5TH FL/00 | Fifth Floor | SIGNAGE & FIRE EXTINGUISHER 5TH FLOOR PLAN | Aashish | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
210 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/5TH FL/00 | Fifth Floor | FIRE DETECTION & PA DRAWING 5TH FLOOR PLAN | Aashish | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
211 | MEP | Fire | WLH/KEC/SIEC/FPS/5TH FL/00 | Fifth Floor | FIRE PROTECTION 5TH FLOOR PLAN | Aashish | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
212 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /6TH FL/00 | Sixth Floor | SIGNAGE & FIRE EXTINGUISHER 6th FLOOR PLAN | Aashish | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
213 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/6TH FL/00 | Sixth Floor | FIRE DETECTION & PA DRAWING 6TH FLOOR PLAN | Aashish | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
214 | MEP | Fire | WLH/KEC/SIEC/FPS/6TH FL/00 | Sixth Floor | FIRE PROTECTION 6TH FLOOR PLAN | Aashish | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
215 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /7TH FL/00 | Seventh Floor | SIGNAGE & FIRE EXTINGUISHER 7TH FLOOR PLAN | Aashish | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
216 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/7TH FL/00 | Seventh Floor | FIRE DETECTION & PA DRAWING 7TH FLOOR PLAN | Aashish | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
217 | MEP | Fire | WLH/KEC/SIEC/FPS/7TH FL/00 | Seventh Floor | FIRE PROTECTION 7TH FLOOR PLAN | Aashish | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
218 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /8TH FL/00 | Eighth Floor | SIGNAGE & FIRE EXTINGUISHER 8TH FLOOR PLAN | Aashish | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
219 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/8TH FL/00 | Eighth Floor | FIRE DETECTION & PA DRAWING 8TH FLOOR PLAN | Aashish | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
220 | MEP | Fire | WLH/KEC/SIEC/FPS/8TH FL/00 | Eighth Floor | FIRE PROTECTION 8TH FLOOR PLAN | Aashish | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
221 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /9TH FL/00 | Ninth floor | SIGNAGE & FIRE EXTINGUISHER 9TH FLOOR PLAN | Aashish | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
222 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/9TH FL/00 | Ninth floor | FIRE DETECTION & PA DRAWING 9th FLOOR PLAN | Aashish | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
223 | MEP | Fire | WLH/KEC/SIEC/FPS/9TH FL/00 | Ninth floor | FIRE PROTECTION 9th FLOOR PLAN | Aashish | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
224 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/10TH FL/00 | Tenth Floor | FIRE DETECTION & PA DRAWING 10th FLOOR PLAN | Aashish | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
225 | MEP | Fire | WLH/KEC/SIEC/FPS/10TH FL/00 | Tenth Floor | FIRE PROTECTION 10th FLOOR PLAN | Aashish | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
226 | MEP | Fire | WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /10TH FL/00 | Terrace floor | SIGNAGE & FIRE EXTINGUISHER ROOF PLAN | Aashish | 2025-11-15 | 2025-07-28 | 2025-11-17 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
227 | MEP | Fire | WLH/KEC/SIEC/FDA & PA/TERRACE/00 | Terrace floor | FIRE DETECTION & PA DRAWING ROOF PLAN | Aashish | 2025-11-15 | 2025-07-25 | 2025-11-13 | 2025-08-06 |  | 2025-08-13 | 2026-02-18 | 2025-08-20
228 | MEP | Fire | WLH/KEC/SIEC/FPS/TERRACE/00 | Terrace floor | FIRE PROTECTION ROOF PLAN | Aashish | 2025-11-15 | 2025-07-25 | 2025-11-13 | 2025-08-06 |  | 2025-08-13 | 2026-02-18 | 2025-08-20
229 | MEP | Fire | WLH/KEC/SIEC/FIRE/INFRA/PUMP ROOM/00 | Basement | PUMP ROOM DRAWING FIRE | Aashish | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-05-01 | 2025-04-15 | 2025-05-12 | 2025-04-15 | 2025-05-19
230 | MEP | Fire | WLH/KEC/SIEC/FIRE/EXTHYDRANT/00 | External | FIRE EXTERNAL HYDRANT LAYOUT | Aashish | 2025-03-15 | 2025-03-15 | 2025-11-05 | 2025-05-22 | 2025-08-29 | 2025-06-02 | 2026-02-18 | 2025-06-09
231 | MEP | Fire | WLH/KEC/SIEC/FIRE/PUMP HEAD CALCULATION/00 | Common | FIRE PUMP HEAD CALCULATION | Aashish | 2025-03-15 | 2025-03-15 | 2025-04-15 | 2025-04-01 | 2025-04-01 | 2025-04-10 | 2025-04-10 | 2025-04-17
232 | MEP | Fire | WLH/KEC/SIEC/FPS SLD/00 | Common | FIRE PROTECTION SINGLE LINE DIAGRAM | Aashish | 2025-03-15 | 2025-03-15 | 2025-04-15 | 2025-04-01 | 2025-04-01 | 2025-04-10 | 2025-04-10 | 2025-04-17
233 | MEP | Fire | WLH/KEC/SIEC/FDA & PA SLD/00 | Common | FIRE DETECTION SINGLE LINE DIAGRAM | Aashish | 2025-03-15 | 2025-03-15 | 2025-04-15 | 2025-04-01 | 2025-04-01 | 2025-04-10 | 2025-04-10 | 2025-04-17
234 | MEP | Fire | WLH/KEC/SIEC/PASCHEMATIC/00 | Common | FIRE PA SCHEMATIC | Aashish | 2025-03-15 | 2025-03-15 | 2025-04-15 | 2025-04-01 | 2025-04-01 | 2025-04-10 | 2025-04-10 | 2025-04-17
235 | MEP | Fire | WLH/KEC/SIEC/FIRE & BMS ROOM/00 | Ground Floor | FIRE ROOM LAYOUT | Aashish | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-16 | 2025-04-01 | 2025-04-25 | 2026-02-18 | 2025-05-02
236 | MEP | Fire | WLH/KEC/SIEC/FIRE/WET RISER/00 | Common | FIRE WET RISER WITH TYPICAL SHAFT DETAILS | Aashish | 2025-03-15 | 2025-03-15 | 2025-04-15 | 2025-04-01 | 2025-04-12 | 2025-04-10 | 2025-04-10 | 2025-04-17
237 | Structural | HVAC | WLH/KEC/SIEC/HVAC/BASEMENT/DUCTING/00 | Basement | HVAC DUCTING LAYOUT BASEMENT PLAN | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-12 | 2025-04-19 | 2025-05-31 | 2025-04-26
238 | Structural | HVAC | WLH/KEC/SIEC/HVAC/BASEMENT/CHW PIPING/00 | Basement | CHILLED WATER PIPING LAYOUT OVER BASEMENT PLAN | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-12 | 2025-04-19 | 2025-05-31 | 2025-04-26
239 | Structural | HVAC | WLH/KEC/SIEC/HVAC/BASEMENT/VENTILATION LAYOUT/00 | Basement | GFC BASEMENT VENTILATION LAYOUT OVER BASEMENT PLAN | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-12 | 2025-04-19 | 2025-05-31 | 2025-04-26
240 | Structural | HVAC | WLH/KEC/SIEC/HVAC/BASEMENT/SMOKE EXTRACTION/00 | Basement | SMOKE EXTRACTION LAYOUT OVER BASEMENT | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-12 | 2025-04-19 | 2025-05-31 | 2025-04-26
241 | Structural | HVAC | WLH/KEC/SIEC/HVAC/BASEMENT/FRESH AIR/00 | Basement | FRESH AIR & EXHAUST AIR LAYOUT OVER BASEMENT | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-12 | 2025-04-19 | 2025-05-31 | 2025-04-26
242 | Structural | HVAC | WLH/KEC/SIEC/HVAC/GF FL/CHW PIPING/00 | Ground Floor | DUCTING LAYOUT GR FLOOR PLAN | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
243 | Structural | HVAC | WLH/KEC/SIEC/HVAC/BASEMENT/ZONING/00 | Ground Floor | CHILLED WATER PIPING LAYOUT OVER GR FLOOR PLAN | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
244 | Structural | HVAC | WLH/KEC/SIEC/HVAC/GR FL/SMOKE EXTRACTION/00 | Ground Floor | SMOKE EXTRACTION LAYOUT OVER GR FLOOR PLAN | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
245 | Structural | HVAC | WLH/KEC/SIEC/HVAC/GR FL/SMOKE EXTRACTION/00-00 | Ground Floor | FRESH AIR & EXHAUST AIR LAYOUT OVER GR FLOOR PLAN | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
246 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/GR FL/00 | Ground Floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT GROUND FLOOR | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 | 2025-05-28 | 2025-04-19 | 2025-06-04 | 2025-04-26
247 | Structural | HVAC | WLH/KEC/SIEC/HVAC/1ST FL/DUCTING/00 | First Floor | DUCTING LAYOUT 1ST FLOOR PLAN | Jitendra | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
248 | Structural | HVAC | WLH/KEC/SIEC/HVAC/1ST FL/CHW PIPING/00 | First Floor | CHILLED WATER PIPING LAYOUT OVER 1ST FLOOR PLAN | Jitendra | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
249 | Structural | HVAC | WLH/KEC/SIEC/HVAC/1ST FL/SMOKE EXTRACTION/00 | First Floor | SMOKE EXTRACTION LAYOUT OVER 1ST FLOOR PLAN | Jitendra | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
250 | Structural | HVAC | WLH/KEC/SIEC/HVAC/1ST FL/FRESH AIR/00 | First Floor | FRESH AIR & EXHAUST AIR LAYOUT OVER 1ST FLOOR PLAN | Jitendra | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
251 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/1STFL/00 | First Floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT FIRST FLOOR | Jitendra | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 | 2025-05-19 | 2025-11-29 | 2025-12-04 | 2025-12-06
252 | Structural | HVAC | WLH/KEC/SIEC/HVAC/2ND FL/DUCTING/00 | Second Floor | DUCTING LAYOUT 2ND FLOOR PLAN | Jitendra | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
253 | Structural | HVAC | WLH/KEC/SIEC/HVAC/2ND FL/CHW PIPING/00 | Second Floor | CHILLED WATER PIPING LAYOUT OVER 2ND FLOOR PLAN | Jitendra | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
254 | Structural | HVAC | WLH/KEC/SIEC/HVAC/2ND FL/SMOKE EXTRACTION/00 | Second Floor | SMOKE EXTRACTION LAYOUT OVER 2ND FLOOR PLAN | Jitendra | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
255 | Structural | HVAC | WLH/KEC/SIEC/HVAC/2ND FL/FRESH AIR/00 | Second Floor | FRESH AIR & EXHAUST AIR LAYOUT OVER 2ND FLOOR PLAN | Jitendra | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
256 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/2ND FL/00 | Second Floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT SECOND FLOOR | Jitendra | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
257 | Structural | HVAC | WLH/KEC/SIEC/HVAC/3RD FL/DUCTING/00 | Third Floor | DUCTING LAYOUT 3RD FLOOR PLAN | Jitendra | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
258 | Structural | HVAC | WLH/KEC/SIEC/HVAC/3RD FL/00 | Third Floor | CHILLED WATER PIPING LAYOUT OVER 3RD FLOOR PLAN | Jitendra | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
259 | Structural | HVAC | WLH/KEC/SIEC/HVAC/3RD FL/SMOKE EXTRACTION/00 | Third Floor | SMOKE EXTRACTION LAYOUT OVER 3RD FLOOR PLAN | Jitendra | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
260 | Structural | HVAC | WLH/KEC/SIEC/HVAC/3RD FL/FRESH AIR/00 | Third Floor | FRESH AIR & EXHAUST AIR LAYOUT OVER 3RD FLOOR PLAN | Jitendra | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
261 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/3RD FL/00 | Third Floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT THIRD FLOOR | Jitendra | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
262 | Structural | HVAC | WLH/KEC/SIEC/HVAC/4TH F/DUCTINGL/00 | Fourth Floor | DUCTING LAYOUT 4TH FLOOR PLAN | Jitendra | 2025-05-13 | 2025-05-13 | 2025-06-09 | 2025-05-25 | 2025-07-31 | 2025-06-01 | 2025-06-04 | 2025-06-08
263 | Structural | HVAC | WLH/KEC/SIEC/HVAC/4TH FL/CHW PIPING/00 | Fourth Floor | CHILLED WATER PIPING LAYOUT OVER 4TH FLOOR PLAN | Jitendra | 2025-05-13 | 2025-05-13 | 2025-06-09 | 2025-05-25 | 2025-07-31 | 2025-06-01 | 2025-06-04 | 2025-06-08
264 | Structural | HVAC | WLH/KEC/SIEC/HVAC/4TH FL/SMOKE EXTRACTION/00 | Fourth Floor | SMOKE EXTRACTION LAYOUT OVER 4TH FLOOR PLAN | Jitendra | 2025-05-13 | 2025-05-13 | 2025-06-09 | 2025-05-25 | 2025-07-31 | 2025-06-01 | 2025-06-04 | 2025-06-08
265 | Structural | HVAC | WLH/KEC/SIEC/HVAC/4TH FL/FRESH AIR/00 | Fourth Floor | FRESH AIR & EXHAUST AIR LAYOUT OVER 4TH FLOOR PLAN | Jitendra | 2025-05-13 | 2025-05-13 | 2025-06-09 | 2025-05-25 | 2025-07-31 | 2025-06-01 | 2025-06-04 | 2025-06-08
266 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/4TH FL/00 | Fourth Floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT FOURTH FLOOR | Jitendra | 2025-05-13 | 2025-05-13 | 2025-06-09 | 2025-05-25 | 2025-07-31 | 2025-06-01 | 2025-06-04 | 2025-06-08
267 | Structural | HVAC | WLH/KEC/SIEC/HVAC/5TH FL/00 | Fifth Floor | DUCTING LAYOUT 5TH FLOOR PLAN | Jitendra | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
268 | Structural | HVAC | WLH/KEC/SIEC/HVAC/5TH FL/CHW PIPING/00 | Fifth Floor | CHILLED WATER PIPING LAYOUT OVER 5TH FLOOR PLAN | Jitendra | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
269 | Structural | HVAC | WLH/KEC/SIEC/HVAC/5TH FL/SMOKE EXTRACTION/00 | Fifth Floor | SMOKE EXTRACTION LAYOUT OVER 5TH FLOOR PLAN | Jitendra | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
270 | Structural | HVAC | WLH/KEC/SIEC/HVAC/5TH FL/FRESH AIR/00 | Fifth Floor | FRESH AIR & EXHAUST AIR LAYOUT OVER 5TH FLOOR PLAN | Jitendra | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-10-16 | 2025-06-22
271 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/5TH FL/00 | Fifth Floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT FIFTH FLOOR | Jitendra | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-09-10 | 2025-06-22
272 | Structural | HVAC | WLH/KEC/SIEC/HVAC/6TH FL/00 | Sixth Floor | DUCTING LAYOUT 6TH FLOOR PLAN | Jitendra | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
273 | Structural | HVAC | WLH/KEC/SIEC/HVAC/6TH FL/CHW PIPING/00 | Sixth Floor | HVAC 6TH FLOOR PLAN | Jitendra | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
274 | Structural | HVAC | WLH/KEC/SIEC/HVAC/6TH FL/SMOKE EXTRACTION/00 | Sixth Floor | SMOKE EXTRACTION LAYOUT OVER 6TH FLOOR PLAN | Jitendra | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
275 | Structural | HVAC | WLH/KEC/SIEC/HVAC/6TH FL/FRESH AIR/00 | Sixth Floor | FRESH AIR & EXHAUST AIR LAYOUT OVER 6TH FLOOR PLAN | Jitendra | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-10-16 | 2025-07-09
276 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/6TH FL/00 | Sixth Floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT SIXTH FLOOR | Jitendra | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-09-10 | 2025-07-09
277 | Structural | HVAC | WLH/KEC/SIEC/HVAC/7TH FL/DUCTING/00 | Seventh Floor | DUCTING LAYOUT 7TH FLOOR PLAN | Jitendra | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
278 | Structural | HVAC | WLH/KEC/SIEC/HVAC/7TH FL/CHW PIPING/00 | Seventh Floor | CHILLED WATER PIPING LAYOUT OVER 7TH FLOOR PLAN | Jitendra | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
279 | Structural | HVAC | WLH/KEC/SIEC/HVAC/7TH FL/SMOKE EXTRACTION/00 | Seventh Floor | SMOKE EXTRACTION LAYOUT OVER 7TH FLOOR PLAN | Jitendra | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
280 | Structural | HVAC | WLH/KEC/SIEC/HVAC/7TH FL/FRESH AIR/00 | Seventh Floor | FRESH AIR & EXHAUST AIR LAYOUT OVER 7TH FLOOR PLAN | Jitendra | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
281 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/7TH FL/00 | Seventh Floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT SEVENTH FLOOR | Jitendra | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
282 | Structural | HVAC | WLH/KEC/SIEC/HVAC/8TH FL/DUCTING/00 | Eighth Floor | DUCTING LAYOUT 8TH FLOOR PLAN | Jitendra | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
283 | Structural | HVAC | WLH/KEC/SIEC/HVAC/8TH FL/CHW PIPING/00 | Eighth Floor | CHILLED WATER PIPING LAYOUT OVER 8TH FLOOR PLAN | Jitendra | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
284 | Structural | HVAC | WLH/KEC/SIEC/HVAC/8TH FL/SMOKE EXTRACTION/00 | Eighth Floor | SMOKE EXTRACTION LAYOUT OVER 8TH FLOOR PLAN | Jitendra | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
285 | Structural | HVAC | WLH/KEC/SIEC/HVAC/8TH FL/FRESH AIR/00 | Eighth Floor | FRESH AIR & EXHAUST AIR LAYOUT OVER 8TH FLOOR PLAN | Jitendra | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
286 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/8TH FL/00 | Eighth Floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT EIGTH FLOOR | Jitendra | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
287 | Structural | HVAC | WLH/KEC/SIEC/HVAC/9TH FL/DUCTING/00 | Ninth floor | DUCTING LAYOUT 9th FLOOR PLAN | Jitendra | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
288 | Structural | HVAC | WLH/KEC/SIEC/HVAC/9TH FL/CHW PIPING/00 | Ninth floor | CHILLED WATER PIPING LAYOUT OVER 9th FLOOR PLAN | Jitendra | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
289 | Structural | HVAC | WLH/KEC/SIEC/HVAC/9TH FL/SMOKE EXTRACTION/00 | Ninth floor | SMOKE EXTRACTION LAYOUT OVER 9TH FLOOR PLAN | Jitendra | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
290 | Structural | HVAC | WLH/KEC/SIEC/HVAC/9TH FL/FRESH AIR/00 | Ninth floor | FRESH AIR & EXHAUST AIR LAYOUT OVER 9TH FLOOR PLAN | Jitendra | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
291 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/9TH FL/00 | Ninth floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT NINTH FLOOR | Jitendra | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
292 | Structural | HVAC | WLH/KEC/SIEC/HVAC/10TH FL/DUCTING/00 | Tenth Floor | DUCTING LAYOUT 10th FLOOR PLAN | Jitendra | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
293 | Structural | HVAC | WLH/KEC/SIEC/HVAC/10TH FL/CHW PIPING/00 | Tenth Floor | CHILLED WATER PIPING LAYOUT OVER 10th FLOOR PLAN | Jitendra | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
294 | Structural | HVAC | WLH/KEC/SIEC/HVAC/10 FL/SMOKE EXTRACTION/00 | Tenth Floor | SMOKE EXTRACTION LAYOUT OVER 10TH FLOOR PLAN | Jitendra | 2025-07-10 | 2025-07-10 | 2025-09-10 | 2025-07-22 |  | 2025-07-29 | 2025-10-16 | 2025-08-05
295 | Structural | HVAC | WLH/KEC/SIEC/HVAC/10TH FL/FRESH AIR/00 | Tenth Floor | FRESH AIR & EXHAUST AIR LAYOUT OVER 10TH FLOOR PLAN | Jitendra | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
296 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION/10TH FL/00 | Tenth Floor | LAYOUT OF LIFT, LIFT LOBBY & STAIRCASE PRESSURIZATION AT TENTH FLOOR | Jitendra | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
297 | Structural | HVAC | WLH/KEC/SIEC/HVAC/TERRACE FL/DUCTING/00 | Terrace floor | DUCTING LAYOUT ROOF PLAN | Jitendra | 2025-11-15 | 2025-07-25 | 2025-11-13 | 2025-08-06 |  | 2025-08-13 | 2026-02-18 | 2025-08-20
298 | Structural | HVAC | WLH/KEC/SIEC/HVAC/TERRACE FL/CHW PIPING/00 | Terrace floor | CHILLED WATER PIPING LAYOUT OVER ROOF PLAN | Jitendra | 2025-11-15 | 2025-07-25 | 2025-11-25 | 2025-08-06 |  | 2025-08-13 | 2026-02-18 | 2025-08-20
299 | Structural | HVAC | WLH/KEC/SIEC/HVAC/MUMTY TERRACE FL/DUCTING/00 | Above Roof | DUCTING LAYOUT ABOVE ROOF PLAN | Jitendra | 2025-11-15 | 2025-07-25 | 2025-11-13 | 2025-08-06 |  | 2025-08-13 | 2026-02-18 | 2025-08-20
300 | Structural | HVAC | WLH/KEC/SIEC/HVAC/STP VENTILATION/00 | Common | STP VENTILATION LAYOUT | Jitendra | 2025-07-25 | 2025-07-25 | 2025-04-04 | 2025-08-06 | 2025-04-12 | 2025-08-13 | 2025-05-31 | 2025-08-20
301 | Structural | HVAC | WLH/KEC/SIEC/HVAC/PRESSURIZATION BASEMENT/00 | Basement | HVAC PRESSURISATION BASEMENT | Jitendra | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 | 2025-04-12 | 2025-04-19 | 2025-05-31 | 2025-04-26
302 | Structural | HVAC | WLH/KEC/SIEC/HVAC/CHILLER PLANT FL/00 | Common | CHILLED PIPING LAYOUT | Jitendra | 2025-03-31 | 2025-03-31 | 2025-08-29 | 2025-04-12 |  | 2025-04-19 | 2025-08-29 | 2025-04-26
303 | Structural | HVAC | WLH/KEC/SIEC/HVAC/DBR/00 | Common | HVAC DBR COMMENTARY |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-04-01 | 2025-03-14 | 2025-04-10 | 2025-03-14 | 2025-04-17
304 | Structural | HVAC | ESP CALCULATION FOR ALL FIRE MODE EQUIOMENTS | Common | ESP CALCULATION FOR ALL FIRE MODE EQUIPMENTS |  | 2025-07-25 | 2025-07-25 | 2025-08-29 | 2025-08-12 |  | 2025-08-21 | 2025-08-29 | 2025-08-28
305 | Structural | HVAC | ESP CALCULATION FOR ALL EQUIPMENTS | Common | ESP CALCULATION FOR ALL EQUIPMENTS |  | 2025-07-25 | 2025-07-25 | 2025-08-29 | 2025-08-12 |  | 2025-08-21 | 2025-08-29 | 2025-08-28
306 | Structural | HVAC | PUMP HEAD CALCULATION | Common | PUMP HEAD CALCULATION |  | 2025-07-25 | 2025-07-25 | 2025-08-29 | 2025-08-12 |  | 2025-08-21 | 2025-08-29 | 2025-08-28
307 | Structural | HVAC | WLH/KEC/SIEC/HVAC/HEAT-LOAD/00 | Common | HEAT LOAD CALCULATIONS WITH EQUIPMENT SELECTION SHEET |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-04-01 | 2025-03-14 | 2025-04-10 | 2025-03-14 | 2025-04-17
308 | Structural | HVAC | WLH/KEC/SIEC/HVAC/VENTILATION CALCULATION/00 | Common | VENTILATION CALCULATIONS WITH FAN SELECTION SHEET |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-04-01 | 2025-03-14 | 2025-04-10 | 2025-03-14 | 2025-04-17
309 | Structural | HVAC | WLH/KEC/SIEC/HVAC/AIR FLOW-DIAGRAM/00 | Common | AIR FLOW DIAGRAMS |  | 2025-07-25 | 2025-07-25 | 2025-08-29 | 2025-08-12 |  | 2025-08-21 | 2025-08-29 | 2025-08-28
310 | Structural | HVAC | WLH/KEC/SIEC/HVAC/HVAC-SHAFT/00 | Common | HVAC RISER (SHAFT) WITH CHILLED WATER PIPE DRAWINGS |  | 2025-07-25 | 2025-07-25 | 2025-03-14 | 14-03-2025 | 14-03-2025 | 2025-03-25 | 2025-03-14 | 2025-04-01
311 | Structural | HVAC | WLH/KEC/SIEC/HVAC/CHILLED WATER SCHEMATIC/00 | Common | HVAC CHILLED WATER SCHEMATIC DRAWINGS (Hi & Low side) | Jitendra | 2025-11-30 | 2025-07-25 | 2026-01-12 | 2025-12-16 |  | 2025-12-25 |  | 2026-01-01
312 | Structural | HVAC | WLH/KEC/SIEC/HVAC/SCHEMATIC/00 | Common | HVAC SCHEMATIC DRAWINGS |  | 2025-07-25 | 2025-07-25 | 2025-08-29 | 2025-08-12 |  | 2025-08-21 | 2025-08-29 | 2025-08-28
313 | Structural | MEP | WLH/KEC/SIEC/MEP/BASEMENT/00 | Basement | BASEMENT MEP LAYOUT | MEP Team | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 |  | 2025-04-19 | 2025-05-31 | 2025-04-26
314 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/BASEMENT/00 | Basement | BASEMENT MEP SECTION | MEP Team | 2025-03-31 | 2025-03-31 | 2025-04-04 | 2025-04-12 |  | 2025-04-19 | 2025-05-31 | 2025-04-26
315 | Structural | MEP | WLH/KEC/SIEC/MEP/GR FL/00 | Ground Floor | GROUND FLOOR MEP LAYOUT | MEP Team | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 |  | 2025-04-19 | 2025-06-04 | 2025-04-26
316 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/GR FL/00 | Ground Floor | GROUND FLOOR MEP SECTION | MEP Team | 2025-03-31 | 2025-03-31 | 2025-04-07 | 2025-04-12 |  | 2025-04-19 | 2025-06-04 | 2025-04-26
317 | Structural | MEP | WLH/KEC/SIEC/MEP/1ST FL/00 | First Floor | FIRST FLOOR MEP LAYOUT | MEP Team | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 |  | 2025-11-29 | 2025-12-04 | 2025-12-06
318 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/1ST FL/00 | First Floor | FIRST FLOOR MEP SECTION | MEP Team | 2025-11-15 | 2025-03-31 | 2025-11-13 | 2025-04-12 |  | 2025-11-29 | 2025-12-04 | 2025-12-06
319 | Structural | MEP | WLH/KEC/SIEC/MEP/2ND FL/00 | Second Floor | SECOND FLOOR MEP LAYOUT | MEP Team | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
320 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/2ND FL/00 | Second Floor | SECOND FLOOR MEP SECTION | MEP Team | 2025-10-30 | 2025-04-13 | 2025-11-05 | 2025-04-25 |  | 2025-11-13 | 2025-12-04 | 2025-11-20
321 | Structural | MEP | WLH/KEC/SIEC/MEP/3RD FL/00 | Third Floor | THIRD FLOOR MEP LAYOUT | MEP Team | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
322 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/3RD FL/00 | Third Floor | THIRD FLOOR MEP SECTION | MEP Team | 2025-10-25 | 2025-04-29 | 2025-10-28 | 2025-05-11 | 2025-08-20 | 2025-11-08 | 2025-12-04 | 2025-11-15
323 | Structural | MEP | WLH/KEC/SIEC/MEP/4TH FL/00 | Fourth Floor | FOURTH FLOOR MEP LAYOUT | MEP Team | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
324 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/4TH FL/00 | Fourth Floor | FOURTH FLOOR MEP SECTION | MEP Team | 2025-05-13 | 2025-05-13 | 2025-05-19 | 2025-05-25 |  | 2025-06-01 | 2025-06-04 | 2025-06-08
325 | Structural | MEP | WLH/KEC/SIEC/MEP/5TH FL/00 | Fifth Floor | FIFTH FLOOR MEP LAYOUT | MEP Team | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-09-10 | 2025-06-22
326 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/5TH FL/00 | Fifth Floor | FIFTH FLOOR MEP SECTION | MEP Team | 2025-05-27 | 2025-05-27 | 2025-07-02 | 2025-06-08 | 2025-08-08 | 2025-06-15 | 2025-09-10 | 2025-06-22
327 | Structural | MEP | WLH/KEC/SIEC/MEP/6TH FL/00 | Sixth Floor | SIXTH FLOOR MEP LAYOUT | MEP Team | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-09-10 | 2025-07-09
328 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/6TH FL/00 | Sixth Floor | SIXTH FLOOR MEP SECTION | MEP Team | 2025-06-13 | 2025-06-13 | 2025-07-09 | 2025-06-25 | 2025-08-14 | 2025-07-02 | 2025-09-10 | 2025-07-09
329 | Structural | MEP | WLH/KEC/SIEC/MEP/7TH FL/00 | Seventh Floor | SEVENTH FLOOR MEP LAYOUT | MEP Team | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
330 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/7TH FL/00 | Seventh Floor | SEVENTH FLOOR MEP SECTION | MEP Team | 2025-06-29 | 2025-06-29 | 2025-08-27 | 2025-07-11 |  | 2025-07-18 | 2025-10-16 | 2025-07-25
331 | Structural | MEP | WLH/KEC/SIEC/MEP/8TH FL/00 | Eighth Floor | EIGTH FLOOR MEP LAYOUT | MEP Team | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
332 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/8TH FL/00 | Eighth Floor | EIGTH FLOOR MEP SECTION | MEP Team | 2025-06-29 | 2025-06-29 | 2025-08-30 | 2025-07-11 |  | 2025-07-18 | 2025-10-29 | 2025-07-25
333 | Structural | MEP | WLH/KEC/SIEC/MEP/9TH FL/00 | Eighth Floor | NINTH FLOOR MEP LAYOUT | MEP Team | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
334 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/9TH FL/00 | Eighth Floor | NINTH FLOOR MEP SECTION | MEP Team | 2025-07-13 | 2025-07-13 | 2025-06-18 | 2025-07-25 |  | 2025-08-01 | 2025-07-12 | 2025-08-08
335 | Structural | MEP | WLH/KEC/SIEC/MEP/10TH FL/00 | Eighth Floor | TENTH FLOOR MEP LAYOUT | MEP Team | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
336 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/10TH FL/01 | Eighth Floor | TENTH FLOOR MEP SECTION | MEP Team | 2025-07-13 | 2025-07-13 | 2025-09-10 | 2025-07-25 |  | 2025-08-01 | 2025-10-16 | 2025-08-08
337 | Structural | MEP | WLH/KEC/SIEC/MEP/TERRACE FL/01 | Terrace floor | TERRACE FLOOR MEP LAYOUT | MEP Team | 2025-11-15 | 2025-07-28 | 2025-11-13 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
338 | Structural | MEP | WLH/KEC/SIEC/MEP SECTION/TERRACE FL/02 | Terrace floor | TERRACE FLOOR MEP SECTION | MEP Team | 2025-11-15 | 2025-07-28 | 2025-11-17 | 2025-08-09 |  | 2025-08-16 | 2026-02-18 | 2025-08-23
339 | Architecture | New Building | WMHL-A20-B1-01 | Basement | BASEMENT FLOOR PLAN | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-06-21
340 | Architecture | New Building | WMHL-A20-B.LOFT-01 | Basement | BASEMENT LOFT PLANS | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-06-21
341 | Architecture | New Building | WMHL-A44-01 | Basement | BASEMENT FURNITURE LAYOUT | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-06-21
342 | Architecture | New Building | WMHL-A36-01 | Basement | BASEMENT PART SECTIONS | Shivangee | 2025-04-05 | 2025-04-05 | 2025-04-03 | 2025-04-22 |  | 2025-05-01 | 2025-09-12 | 2025-05-08 | 2025-12-15
343 | Architecture | New Building | WMHL-A36-02 | Basement | BASEMENT PART SECTIONS | Shivangee | 2025-04-05 | 2025-04-05 | 2025-04-03 | 2025-04-22 |  | 2025-05-01 | 2025-09-12 | 2025-05-08 | 2025-12-15
344 | Architecture | New Building | WMHL-A47-B1-01.1 | Basement | BASEMENT TOILET-1 DETAIL | Shivangee | 2025-04-05 | 2025-04-05 | 2025-04-10 | 2025-04-22 |  | 2025-05-01 | 2025-09-12 | 2025-05-08 | 2025-11-01
345 | Architecture | New Building | WMHL-A47-B1-01.2 | Basement | BASEMENT TOILET-2 DETAIL | Shivangee | 2025-04-05 | 2025-04-05 | 2025-04-10 | 2025-04-22 |  | 2025-05-01 | 2025-09-12 | 2025-05-08 | 2025-11-01
346 | Architecture | New Building | WMHL-A47-B1-01.3 | Basement | BASEMENT TOILET-3 DETAIL | Shivangee | 2025-04-05 | 2025-04-05 | 2025-04-10 | 2025-04-22 |  | 2025-05-01 | 2025-09-12 | 2025-05-08 | 2025-11-01
347 | Architecture | New Building | WMHL-A25-01 | Basement | BASEMENT FLOORING LAYOUT | Shivangee | 2025-04-12 | 2025-04-12 | 2025-04-09 | 2025-04-29 | 2025-04-28 | 2025-05-08 | 2025-05-02 | 2025-05-15 | 2025-09-19
348 | Architecture | New Building | WMHL-A25-02 | Basement | BASEMENT LOFT FLOORING LAYOUT | Shivangee | 2025-04-12 | 2025-04-12 | 2025-04-09 | 2025-04-29 | 2025-04-28 | 2025-05-08 | 2025-05-02 | 2025-05-15 | 2025-11-01
349 | Architecture | New Building | WMHL-A54-02.2 | Basement | WINDOW DETAILS SHEET 2 | Shivangee | 2025-04-12 | 2025-04-12 | 2025-04-17 | 2025-04-29 |  | 2025-05-08 | 2025-09-12 | 2025-05-15 |  | MEP Coordinated Drawing wih design inputs of fixtures and duct layouts
350 | Architecture | New Building | WMLH-A41-02.1 | Basement | BASEMENT LINAC DETAILS-1 | Shivangee | 2025-05-31 | 2025-05-31 | 2025-07-09 | 2025-06-17 |  | 2025-06-26 | 2025-07-16 | 2025-07-03 | 2025-11-01
351 | Architecture | New Building | WMLH-A41-02.2 | Basement | BASEMENT LINAC DETAILS-1 | Shivangee | 2025-05-31 | 2025-05-31 | 2025-07-09 | 2025-06-17 |  | 2025-06-26 | 2025-07-16 | 2025-07-03 | 2025-11-01
352 | Architecture | New Building | WMLH-A41-03 | Basement | BASEMENT -BOOTH SEATING AREA | Shivangee | 2025-05-31 | 2025-05-31 | 2025-07-10 | 2025-06-17 |  | 2025-06-26 | 2025-07-16 | 2025-07-03 | 2025-11-01
353 | Architecture | New Building | WMHL-A60-01 | Basement | BASEMENT FLOOR RCP | Shivangee | 2025-11-30 | 2025-05-31 | 2025-11-20 | 2025-12-16 |  | 2025-12-25 | 2025-12-06 | 2026-01-01
354 | Architecture | New Building | WMHL-A20-00-01 | Ground Floor | GROUND FLOOR PLAN | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07 | 2025-09-02
355 | Architecture | New Building | WMHL-A44-02 | Ground Floor | GROUND FLOOR FURNITURE LAYOUT | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07 | 2025-09-02
356 | Architecture | New Building | WMHL-A54-02 | Ground Floor | DOOR DETAILS SHEET 3 | Shivangee | 2025-04-12 | 2025-04-12 | 2025-04-17 | 2025-04-29 |  | 2025-05-08 | 2025-09-12 | 2025-05-15 |  | MEP Coordinated Drawing wih design inputs of fixtures and duct layouts
357 | Architecture | New Building | WMHL-A47-00-01.1 | Ground Floor | GROUND FLOOR TOILET-1 DETAIL | Shivangee | 2025-04-12 | 2025-04-12 | 2025-04-04 | 2025-04-29 |  | 2025-05-08 | 2025-12-15 | 2025-05-15 | 2025-12-27
358 | Architecture | New Building | WMHL-A47-00-01.2 | Ground Floor | GROUND FLOOR TOILET-2 DETAIL | Shivangee | 2025-04-12 | 2025-04-12 | 2025-04-04 | 2025-04-29 |  | 2025-05-08 | 2025-12-15 | 2025-05-15 | 2025-12-27
359 | Architecture | New Building | WMHL-A47-00-01.3 | Ground Floor | GROUND FLOOR TOILET-3 DETAIL | Shivangee | 2025-04-12 | 2025-04-12 | 2025-04-10 | 2025-04-29 |  | 2025-05-08 | 2025-12-15 | 2025-05-15 | 2025-12-27
360 | Architecture | New Building | WMHL-A54-01.4 | Ground Floor | DOOR DETAILS SHEET 3 | Shivangee | 2025-04-19 | 2025-04-19 | 2025-04-17 | 2025-05-06 |  | 2025-05-15 | 2025-09-12 | 2025-05-22
361 | Architecture | New Building | WMHL-A54-01.5 | Ground Floor | DOOR DETAILS SHEET 4 | Shivangee | 2025-04-19 | 2025-04-19 | 2025-04-17 | 2025-05-06 |  | 2025-05-15 | 2025-09-12 | 2025-05-22
362 | Architecture | New Building | WMHL-A25-03 | Ground Floor | GROUND FLOOR FLOORING LAYOUT | Shivangee | 2025-12-24 | 2025-05-03 | 2025-12-15 | 2026-01-09 | 2025-05-02 | 2026-01-20 | 2025-12-18 | 2026-01-27 | 2025-12-27
363 | Architecture | New Building | WMHL-A41-02 | Ground Floor | Interior Elevations- Ground Floor waiting area | Shivangee | 2025-12-24 | 2025-05-31 | 2025-12-18 | 2026-01-09 |  | 2026-01-20 | 2026-01-09 | 2026-01-27
364 | Architecture | New Building | WMHL-A60-02 | Ground Floor | GROUND FLOOR RCP | Shivangee | 2025-12-23 | 2025-05-31 | 2026-04-08 | 2026-01-08 |  | 2026-01-19 | 2026-05-15 | 2026-01-26
365 | Architecture | New Building | WMHL-A41-03 | Ground Floor | Ground Floor interior elevation- lift lobby & VIP waiting | Shivangee | 2025-12-24 | 2025-07-05 | 2025-12-08 | 2026-01-09 |  | 2026-01-20 | 2025-12-09 | 2026-01-27
366 | Architecture | New Building | WMHL-A41-04 | Ground Floor | Interior Elevations- Ground Floor Corridor | Shivangee | 2025-12-24 | 2025-07-05 | 2025-12-05 | 2026-01-09 |  | 2026-01-20 | 2025-12-09 | 2026-01-27
367 | Architecture | New Building | WMHL-A41-07 | Ground Floor | Interior Elevations- Ground Floor Physiotherapy | Shivangee | 2025-12-24 | 2025-06-07 | 2025-12-05 | 2026-01-09 |  | 2026-01-20 | 2025-12-09 | 2026-01-27
368 | Architecture | New Building | WMHL-A20-01-01 | First Floor | 1ST FLOOR PLAN | Shivangee | 2025-10-30 | 2025-03-03 | 2025-10-24 | 2025-11-17 | 2025-03-26 | 2025-11-15 | 2025-10-29 | 2025-11-22 | 2025-11-18
369 | Architecture | New Building | WMHL-A44-03 | First Floor | FIRST FLOOR FURNITURE LAYOUT | Shivangee | 2025-10-30 | 2025-03-03 | 2025-10-24 | 2025-11-17 | 2025-03-26 | 2025-11-15 | 2025-10-29 | 2025-11-22 | 2025-11-18
370 | Architecture | New Building | WMHL-A47-01-01.1 | First Floor | FIRST FLOOR TOILET-1 DETAIL | Shivangee | 2025-11-15 | 2025-04-19 | 2025-11-14 | 2025-12-02 |  | 2025-12-11 | 2025-12-02 | 2025-12-18 | 2025-12-09
371 | Architecture | New Building | WMHL-A47-01-01.2 | First Floor | FIRST FLOOR TOILET-2 DETAIL | Shivangee | 2025-11-15 | 2025-04-19 | 2025-11-14 | 2025-12-02 |  | 2025-12-11 | 2025-12-02 | 2025-12-18 | 2025-12-09
372 | Architecture | New Building | WMHL-A47-01-01.3 | First Floor | FIRST FLOOR TOILET-3 DETAIL | Shivangee | 2025-11-15 | 2025-04-19 | 2025-11-14 | 2025-12-02 |  | 2025-12-11 | 2025-12-02 | 2025-12-18 | 2025-12-09
373 | Architecture | New Building | WMHL-A25-04 | First Floor | FIRST FLOOR FLOORING LAYOUT | Shivangee | 2025-11-04 | 2025-05-03 | 2025-11-06 | 2025-11-20 | 2025-05-09 | 2025-11-15 | 2025-12-06 | 2025-11-22
374 | Architecture | New Building | WMHL-A60-03 | First Floor | FIRST FLOOR RCP | Shivangee | 2025-05-24 | 2025-05-24 | 2025-03-16 | 2025-06-10 |  | 2025-06-19 | 2026-04-20 | 2025-06-26
375 | Architecture | New Building | WMHL-A20-02-01 | Second Floor | 2ND FLOOR PLAN | Shivangee | 2025-10-20 | 2025-03-03 | 2025-10-24 | 2025-11-05 | 2025-03-26 | 2025-11-15 | 2025-11-12 | 2025-11-22
376 | Architecture | New Building | WMHL-A44-04 | Second Floor | SECOND FLOOR FURNITURE LAYOUT | Shivangee | 2025-10-20 | 2025-03-03 | 2025-10-24 | 2025-11-05 | 2025-03-26 | 2025-11-15 | 2025-11-12 | 2025-11-22
377 | Architecture | New Building | WMHL-A46-02 | Second Floor | 2ND FLOOR PANTRY DETAIL | Shivangee | 2025-12-05 | 2025-04-19 | 2025-11-28 | 2025-12-23 |  | 2026-01-01 | 2025-09-12 | 2026-01-08
378 | Architecture | New Building | WMHL-A47-02-01.1 | Second Floor | SECOND FLOOR TOILET-1 DETAIL | Shivangee | 2025-11-15 | 2025-05-10 | 2025-11-13 | 2025-12-02 |  | 2025-12-11 | 2025-12-09 | 2025-12-18 | 2025-12-09
379 | Architecture | New Building | WMHL-A47-02-01.2 | Second Floor | SECOND FLOOR TOILET-2 DETAIL | Shivangee | 2025-11-15 | 2025-05-10 | 2025-11-13 | 2025-12-02 |  | 2025-12-11 | 2025-12-09 | 2025-12-18 | 2025-12-09
380 | Architecture | New Building | WMHL-A47-02-01.3 | Second Floor | SECOND FLOOR TOILET-3 DETAIL | Shivangee | 2025-11-15 | 2025-05-10 | 2025-11-13 | 2025-12-02 |  | 2025-12-11 | 2025-12-09 | 2025-12-18 | 2025-12-09
381 | Architecture | New Building | WMHL-A54-01.7 | Second Floor | SECOND FLOOR DOOR DETAILS SHEET 1 | Shivangee | 2025-05-10 | 2025-05-10 | 2025-05-16 | 2025-05-27 |  | 2025-06-05 | 2025-12-09 | 2025-06-12
382 | Architecture | New Building | WMHL-A54-01.8 | Second Floor | SECOND FLOOR DOOR DETAILS SHEET 2 | Shivangee | 2025-05-10 | 2025-05-10 | 2025-05-16 | 2025-05-27 |  | 2025-06-05 | 2025-12-09 | 2025-06-12
383 | Architecture | New Building | WMHL-A60-04 | Second Floor | SECOND FLOOR RCP | Shivangee | 2025-12-04 | 2025-05-24 | 2026-03-12 | 2025-12-22 |  | 2025-12-31 | 2026-04-20 | 2026-01-07
384 | Architecture | New Building | WMHL-A27-01 | Second Floor | SECOND FLOOR FLOORING LAYOUT-1 | Shivangee | 2025-12-19 | 2025-12-19 | 2025-11-03 | 2026-01-06 |  | 2025-12-26 | 2025-11-12 | 2026-01-02
385 | Architecture | New Building | WMHL-A27-02 | Second Floor | SECOND FLOOR FLOORING LAYOUT-2 | Shivangee | 2025-12-19 | 2025-12-19 | 2025-11-03 | 2026-01-06 |  | 2025-12-26 | 2025-11-12 | 2026-01-02
386 | Architecture | New Building | WMHL-A20-03-01 | Third Floor | 3RD FLOOR PLAN | Shivangee | 2025-10-15 | 2025-03-03 | 2025-10-16 | 2025-10-31 | 2025-03-26 | 2025-11-15 | 2025-10-22 | 2025-11-22 | 2025-11-18
387 | Architecture | New Building | WMHL-A44-05 | Third Floor | THIRD FLOOR FURNITURE LAYOUT | Shivangee | 2025-10-15 | 2025-03-03 | 2025-10-16 | 2025-10-31 | 2025-03-26 | 2025-11-15 | 2025-10-22 | 2025-11-22 | 2025-11-18
388 | Architecture | New Building | WMHL-A47-03-01.1 | Third Floor | THIRD FLOOR TOILET-1 DETAIL | Shivangee | 2025-11-15 | 2025-05-10 | 2025-11-20 | 2025-12-02 |  | 2025-12-11 | 2025-12-02 | 2025-12-18 | 2025-12-09 | MEP Coordinated Drawing wih design inputs of fixtures and duct layouts
389 | Architecture | New Building | WMHL-A47-03-01.2 | Third Floor | THIRD FLOOR TOILET-2 DETAIL | Shivangee | 2025-11-15 | 2025-05-10 | 2025-11-20 | 2025-12-02 |  | 2025-12-11 | 2025-12-02 | 2025-12-18 | 2025-12-09 | MEP Coordinated Drawing wih design inputs of fixtures and duct layouts
390 | Architecture | New Building | WMHL-A54-01.9 | Third Floor | THIRD FLOOR DOOR DETAILS SHEET 1 | Shivangee | 2025-05-10 | 2025-05-10 | 2025-05-16 | 2025-05-27 |  | 2025-06-05 | 2025-12-09 | 2025-06-12
391 | Architecture | New Building | WMHL-A54-01.10 | Third Floor | THIRD FLOOR DOOR DETAILS SHEET 2 | Shivangee | 2025-05-10 | 2025-05-10 | 2025-05-16 | 2025-05-27 |  | 2025-06-05 | 2025-12-09 | 2025-06-12
392 | Architecture | New Building | WMHL-A25-06 | Third Floor | THIRD FLOOR FLOORING LAYOUT | Shivangee | 2025-05-31 | 2025-05-31 | 2025-06-18 | 2025-06-17 |  | 2025-06-26 | 2025-11-12 | 2025-07-03
393 | Architecture | New Building | WMHL-A41-05 | Third Floor | Interior Elevations- Third Floor General ward | Shivangee | 2025-12-03 | 2025-07-05 | 2025-11-26 | 2025-12-19 |  | 2025-12-30 | 2025-12-05 | 2026-01-06
394 | Architecture | New Building | WMHL-A60-05 | Third Floor | THIRD FLOOR RCP | Shivangee | 2025-12-08 | 2025-05-24 | 2026-03-06 | 2025-12-24 |  | 2025-11-15 | 2026-04-20 | 2025-11-22
395 | Architecture | New Building | WMHL-A10-11 | External | SECURITY ROOM 02- DETAILS | Shivangee | 2025-12-31 | 2025-07-05 | 2026-01-21 | 2026-01-16 |  | 2026-01-27 | 2026-05-15 | 2026-02-03
396 | Architecture | New Building | WMHL-A20-04-01 | Fourth Floor | 4TH FLOOR PLAN | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07 | 2025-08-08
397 | Architecture | New Building | WMHL-A44-06 | Fourth Floor | FOURTH FLOOR FURNITURE LAYOUT | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07 | 2025-08-08
398 | Architecture | New Building | WMHL-A47-04-01.1 | Fourth Floor | FOURTH FLOOR TOILET-1 DETAIL | Shivangee | 2025-11-26 | 2025-05-10 | 2025-11-26 | 2025-12-12 |  | 2025-12-23 | 2025-12-09 | 2025-12-30 | 2026-12-15
399 | Architecture | New Building | WMHL-A47-04-01.2 | Fourth Floor | FOURTH FLOOR TOILET-2 DETAIL | Shivangee | 2025-11-26 | 2025-05-10 | 2025-11-26 | 2025-12-12 |  | 2025-12-23 | 2025-12-09 | 2025-12-30 | 2026-12-15
400 | Architecture | New Building | WMHL-A54-01.11 | Fourth Floor | FOURTH FLOOR DOOR DETAILS SHEET 1 | Shivangee | 2025-05-10 | 2025-05-10 | 2025-05-21 | 2025-05-27 |  | 2025-06-05 | 2025-12-09 | 2025-06-12
401 | Architecture | New Building | WMHL-A54-01.12 | Fourth Floor | FOURTH FLOOR DOOR DETAILS SHEET 2 | Shivangee | 2025-05-10 | 2025-05-10 | 2025-05-21 | 2025-05-27 |  | 2025-06-05 | 2025-12-09 | 2025-06-12
402 | Architecture | New Building | WMHL-A25-07 | Fourth Floor | FOURTH FLOOR FLOORING LAYOUT | Shivangee | 2025-11-28 | 2025-06-07 | 2025-11-26 | 2025-12-16 |  | 2025-12-25 | 2025-12-02 | 2026-01-01
403 | Architecture | New Building | WMHL-A60-06 | Fourth Floor | FOURTH FLOOR RCP | Shivangee | 2025-11-28 | 2025-06-07 | 2025-11-20 | 2025-12-16 |  | 2025-12-25 | 2025-12-06 | 2026-01-01
404 | Architecture | New Building | WMHL-A41-22 | Fourth Floor | Interior Elevations- 4th Floor Change room | Shivangee | 2025-12-30 | 2025-06-28 | 2025-11-26 | 2026-01-15 |  | 2026-01-26 | 2025-10-05 | 2026-02-02 | 2025-11-01
405 | Architecture | New Building | WMHL-A20-05-01 | Fifth Floor | 5TH FLOOR PLAN | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07 | 2025-09-19
406 | Architecture | New Building | WMHL-A44-07 | Fifth Floor | FIFTH FLOOR FURNITURE LAYOUT | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07 | 2025-09-19
407 | Architecture | New Building | WMHL-A47-05-01.1 | Fifth Floor | FIFTH FLOOR TOILET-1 DETAIL | Shivangee | 2025-11-28 | 2025-05-17 | 2025-11-28 | 2025-12-16 |  | 2025-12-25 | 2025-09-12 | 2026-01-01 | 2026-12-15
408 | Architecture | New Building | WMHL-A47-05-01.2 | Fifth Floor | FIFTH FLOOR TOILET-2 DETAIL | Shivangee | 2025-11-28 | 2025-05-17 | 2025-11-28 | 2025-12-16 |  | 2025-12-25 | 2025-09-12 | 2026-01-01 | 2026-12-15
409 | Architecture | New Building | WMHL-A47-05-01.3 | Fifth Floor | FIFTH FLOOR TOILET-3 DETAIL | Shivangee | 2025-11-28 | 2025-05-17 | 2025-11-28 | 2025-12-16 |  | 2025-12-25 | 2025-09-12 | 2026-01-01 | 2026-12-15
410 | Architecture | New Building | WMHL-A54-01.13 | Fifth Floor | FIFTH FLOOR DOOR DETAILS SHEET 1 | Shivangee | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-06-03 |  | 2025-06-12 | 2025-09-12 | 2025-06-19
411 | Architecture | New Building | WMHL-A54-01.14 | Fifth Floor | FIFTH FLOOR DOOR DETAILS SHEET 2 | Shivangee | 2025-05-17 | 2025-05-17 | 2025-05-22 | 2025-06-03 |  | 2025-06-12 | 2025-09-12 | 2025-06-19
412 | Architecture | New Building | WMHL-A46-03 | Fifth Floor | FIFTH FLOOR PANTRY DETAIL(6TH,8TH & 9TH FLOOR SIMILAR) | Shivangee | 2025-12-03 | 2025-05-17 | 2025-11-28 | 2025-12-19 |  | 2025-12-30 | 2025-12-02 | 2026-01-06 | 2025-12-09
413 | Architecture | New Building | WMHL-A47-08-01.1 | Eighth Floor | EIGTH FLOOR TOILET-1 DETAIL | Shivangee | 2025-05-24 | 2025-05-24 | 2025-06-23 | 2025-06-10 |  | 2025-06-19 | 2025-12-15 | 2025-06-26 | 2025-12-19
414 | Architecture | New Building | WMHL-A47-08-01.2 | Eighth Floor | EIGTH FLOOR TOILET-2 DETAIL | Shivangee | 2025-05-24 | 2025-05-24 | 2025-06-23 | 2025-06-10 |  | 2025-06-19 | 2025-12-15 | 2025-06-26 | 2025-12-19
415 | Architecture | New Building | WMHL-A25-08.2 | Fifth Floor | FIFTH FLOOR FLOORING LAYOUT | Shivangee | 2025-05-24 | 2025-05-24 | 2025-06-23 | 2025-06-10 |  | 2025-06-19 | 2025-07-02 | 2025-06-26 | 2025-11-01
416 | Architecture | New Building | WMHL-A41-01 | Fifth Floor | Interior Elevations- consultant room | Shivangee | 2025-06-28 | 2025-06-28 | 2025-06-27 | 2025-07-15 |  | 2025-07-24 | 2025-07-02 | 2025-07-31 | 2025-11-18
417 | Architecture | New Building | WMHL-A25-08.1 | Fifth Floor | FIFTH FLOOR FLOORING LAYOUT | Shivangee | 2025-06-07 | 2025-06-07 | 2025-06-23 | 2025-06-24 |  | 2025-07-03 | 2025-07-02 | 2025-07-10 | 2025-11-01
418 | Architecture | New Building | WMHL-A60-07 | Fifth Floor | FIFTH FLOOR RCP | Shivangee | 2025-12-10 | 2025-06-07 | 2026-03-12 | 2025-12-26 |  | 2026-01-06 | 2026-04-20 | 2026-01-13
419 | Architecture | New Building | WMHL-A41-10.1 | Fifth Floor | FIFTH FLOOR - ICU SHEET 1 | Shivangee | 2025-12-03 |  | 2025-12-05 | 2025-12-19 |  | 2025-12-30 | 2026-04-20 | 2026-01-06
420 | Architecture | New Building | WMHL-A41-10.2 | Fifth Floor | FIFTH FLOOR - ICU SHEET 2 | Shivangee | 2025-12-03 |  | 2025-12-05 | 2025-12-19 |  | 2025-12-30 | 2026-04-20 | 2026-01-06
421 | Architecture | New Building | WMHL-A20-06-01 | Sixth Floor | 6TH FLOOR PLAN | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07 | 2025-08-02
422 | Architecture | New Building | WMHL-A44-08 | Sixth Floor | SIXTH FLOOR FURNITURE LAYOUT | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07 | 2025-08-02
423 | Architecture | New Building | WMHL-A47-06-01.1 | Sixth Floor | SIXTH FLOOR TOILET-1 DETAIL | Shivangee | 2025-12-05 | 2025-05-17 | 2025-12-03 | 2025-12-23 |  | 2026-01-01 | 2025-09-12 | 2026-01-08 | 2026-12-15
424 | Architecture | New Building | WMHL-A47-06-01.2 | Sixth Floor | SIXTH FLOOR TOILET-2 DETAIL | Shivangee | 2025-12-05 | 2025-05-17 | 2025-12-03 | 2025-12-23 |  | 2026-01-01 | 2025-09-12 | 2026-01-08 | 2026-12-15
425 | Architecture | New Building | WMHL-A47-06-01.3 | Sixth Floor | SIXTH FLOOR TOILET-3 DETAIL | Shivangee | 2025-12-05 | 2025-05-17 | 2025-12-03 | 2025-12-23 |  | 2026-01-01 | 2025-09-12 | 2026-01-08 | 2026-12-15
426 | Architecture | New Building | WMHL-A54-01.15 | Sixth Floor | SIXTH FLOOR DOOR DETAILS SHEET 1 | Shivangee | 2025-05-17 | 2025-05-17 | 2025-06-05 | 2025-06-03 |  | 2025-06-12 | 2025-09-12 | 2025-06-19
427 | Architecture | New Building | WMHL-A54-01.16 | Sixth Floor | SIXTH FLOOR DOOR DETAILS SHEET 2 | Shivangee | 2025-05-17 | 2025-05-17 | 2025-06-05 | 2025-06-03 |  | 2025-06-12 | 2025-09-12 | 2025-06-19
428 | Architecture | New Building | WMHL-A25-09.1 | Sixth Floor | SIXTH FLOOR FLOORING LAYOUT-1 | Shivangee | 2025-11-28 | 2025-06-14 | 2025-10-23 | 2025-12-16 |  | 2025-12-25 | 2025-07-08 | 2026-01-01 | 2025-11-01
429 | Architecture | New Building | WMHL-A60-08 | Sixth Floor | SIXTH FLOOR RCP | Shivangee | 2025-12-11 | 2025-06-07 | 2026-03-06 | 2025-12-29 |  | 2026-01-07 | 2026-04-20 | 2026-01-14
430 | Architecture | New Building | WMHL-A26-18 | Sixth Floor | Interior Elevations- Sixth Floor single gynac room | Shivangee | 2025-12-05 | 2025-07-12 | 2025-12-05 | 2025-12-23 |  | 2026-01-01 | 2025-12-09 | 2026-01-08
431 | Architecture | New Building | WMHL-A25-09.2 | Sixth Floor | SIXTH FLOOR FLOORING LAYOUT-2 | Shivangee | 2025-11-28 | 2025-06-21 | 2025-10-23 | 2025-12-16 |  | 2025-12-25 | 2025-07-08 | 2026-01-01 | 2025-11-01
432 | Architecture | New Building | WMHL-A41-14 | Sixth Floor | Interior Elevation Sixth Floor Double Room | Shivangee | 2025-12-05 | 2025-06-28 | 2025-12-05 | 2025-12-23 |  | 2025-11-15 | 2025-12-09 | 2025-11-22
433 | Architecture | New Building | WMHL-A41-13 | Sixth Floor | SIXTH FLOOR - PAEDIATRIC WARD |  | 2025-12-05 |  | 2025-12-05 | 2025-12-23 |  | 2026-01-01 | 2026-01-09 | 2026-01-08
434 | Architecture | New Building | WMHL-A20-07-01 | Seventh Floor | 7TH FLOOR PLAN | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07 | 2025-08-02
435 | Architecture | New Building | WMHL-A44-09 | Seventh Floor | SEVENTH FLOOR FURNITURE LAYOUT | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07 | 2025-08-02
436 | Architecture | New Building | WMHL-A47-07-01.1 | Seventh Floor | SEVENTH FLOOR TOILET-1 DETAIL | Shivangee | 2025-12-10 | 2025-05-17 | 2025-12-08 | 2025-12-26 |  | 2026-01-06 | 2026-01-09 | 2026-01-13 | 2026-12-27
437 | Architecture | New Building | WMHL-A54-01.17 | Seventh Floor | SEVENTH FLOOR DOOR DETAILS SHEET 1 | Shivangee | 2025-12-10 | 2025-05-17 | 2025-06-04 | 2025-12-26 |  | 2026-01-06 | 2025-09-12 | 2026-01-13
438 | Architecture | New Building | WMHL-A54-01.18 | Seventh Floor | SEVENTH FLOOR DOOR DETAILS SHEET 2 | Shivangee | 2025-12-10 | 2025-05-17 | 2025-06-04 | 2025-12-26 |  | 2026-01-06 | 2025-09-12 | 2026-01-13
439 | Architecture | New Building | WMHL-A46-04 | Seventh Floor | 7TH FLOOR PANTRY DETAIL | Shivangee | 2025-12-10 | 2025-05-24 | 2025-12-08 | 2025-12-26 |  | 2026-01-06 | 2025-12-09 | 2026-01-13 | 2026-12-15
440 | Architecture | New Building | WMHL-A41-06 | Seventh Floor | Interior Elevations- Basement Consultant Room | Shivangee | 2025-08-02 | 2025-06-07 | 2025-08-02 | 2025-08-19 |  | 2025-08-28 | 2025-08-16 | 2025-09-04 | 2025-11-01
441 | Architecture | New Building | WMHL-A25-10 | Seventh Floor | SEVENTH FLOOR FLOORING LAYOUT | Shivangee | 2025-12-10 | 2025-06-14 | 2025-12-09 | 2025-12-26 |  | 2026-01-06 | 2025-12-09 | 2026-01-13
442 | Architecture | New Building | WMHL-A60-09 | Seventh Floor | SEVENTH FLOOR RCP | Shivangee | 2025-12-12 | 2025-06-14 | 2026-03-06 | 2025-12-30 |  | 2026-01-08 | 2026-04-20 | 2026-01-15
443 | Architecture | New Building | WMHL-A41-08 | Seventh Floor | Interior Elevations- Seventh Floor Auditorium details | Shivangee | 2025-12-09 | 2025-07-12 | 2025-08-28 | 2025-12-25 |  | 2026-01-05 | 2025-12-09 | 2026-01-12
444 | Architecture | New Building | WMHL-A26-17 | Seventh Floor | Interior Elevations- Seventh Floor Library details | Shivangee | 2025-12-09 | 2025-07-12 | 2025-12-09 | 2025-12-25 |  | 2026-01-05 | 2025-12-09 | 2026-01-12
445 | Architecture | New Building | WMHL-A41-17 | Seventh Floor | SEVENTH FLOOR -STAFF DINING | Shivangee | 2025-12-09 |  | 2025-12-09 | 2025-12-25 |  | 2026-01-05 | 2026-01-09 | 2026-01-12
446 | Architecture | New Building | WMHL-A20-08-01 | Eighth Floor | 8TH FLOOR PLAN | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07
447 | Architecture | New Building | WMHL-A44-10 | Eighth Floor | EIGTH FLOOR FURNITURE LAYOUT | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07
448 | Architecture | New Building | WMHL-A54-01.19 | Eighth Floor | EIGHTH FLOOR DOOR DETAILS SHEET 1 | Shivangee | 2025-05-24 | 2025-05-24 | 2025-06-09 | 2025-06-10 |  | 2025-06-19 | 2025-12-09 | 2025-06-26
449 | Architecture | New Building | WMHL-A54-01.20 | Eighth Floor | EIGHTH FLOOR DOOR DETAILS SHEET 2 | Shivangee | 2025-05-24 | 2025-05-24 | 2025-06-09 | 2025-06-10 |  | 2025-06-19 | 2025-12-09 | 2025-06-26
450 | Architecture | New Building | WMHL-A54-03 | Eighth Floor | RAILING DETAILS | Shivangee | 2025-06-14 | 2025-06-14 | 2025-07-22 | 2025-07-01 |  | 2025-07-10 | 2025-08-16 | 2025-07-17
451 | Architecture | New Building | WMHL-A25-11 | Eighth Floor | EIGTH FLOOR FLOORING LAYOUT | Shivangee | 2025-12-16 | 2025-06-14 | 2025-12-08 | 2026-01-01 |  | 2026-01-12 | 2025-12-09 | 2026-01-19 | 2025-12-15
452 | Architecture | New Building | WMHL-A60-10 | Eighth Floor | EIGHTH FLOOR RCP | Shivangee | 2025-12-17 | 2025-06-21 | 2026-03-12 | 2026-01-02 |  | 2025-11-15 | 2026-04-20 | 2025-11-22
453 | Architecture | New Building | WMHL-A41-19 | Eighth Floor | Interior Elevation Eight Floor Single Room | Shivangee | 2025-12-16 | 2025-06-28 | 2025-12-12 | 2026-01-01 |  | 2025-11-15 | 2025-12-15 | 2025-11-22 | 2025-12-19
454 | Architecture | New Building | WMHL-A41-20 | Eighth Floor | Interior Elevation Eight Floor Junior Suite Room-1 | Shivangee | 2025-12-16 | 2025-06-28 | 2025-12-12 | 2026-01-01 |  | 2025-11-15 | 2025-12-15 | 2025-11-22 | 2025-12-19
455 | Architecture | New Building | WMHL-A41-21 | Detail Drawings | General Wall Fixing Detail | Shivangee | 2025-12-16 | 2025-06-28 | 2026-01-08 | 2026-01-01 |  | 2025-11-15 | 2025-12-15 | 2025-11-22
456 | Architecture | New Building | WMHL-A41-23 | Eighth Floor | Interior Elevation Eight Floor Suite Room | Shivangee | 2025-12-16 | 2025-06-28 | 2025-12-16 | 2026-01-01 |  | 2026-01-12 | 2026-04-20 | 2026-01-19
457 | Architecture | New Building | WMHL-A47-10.1 | Eighth Floor | EIGHTH FLOOR TOILET DETAIL SHEET 1 | Shivangee | 2025-12-16 |  | 2025-12-08 | 2026-01-01 |  | 2026-01-12 | 2025-12-09 | 2026-01-19 | 2025-12-19
458 | Architecture | New Building | WMHL-A20-RF-02 | Roof Floor | ABOVE ROOF PLAN & PART SECTIONS | Shivangee | 2025-12-16 |  | 2025-12-17 | 2026-01-01 |  | 2026-01-12 | 2026-04-20 | 2026-01-19
459 | Architecture | New Building | WMHL-A20-09-01 | Ninth floor | 9TH FLOOR PLAN | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07
460 | Architecture | New Building | WMHL-A44-11 | Ninth floor | NINTH FLOOR FURNITURE LAYOUT | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07
461 | Architecture | New Building | WMHL-A47-09-01.1 | Ninth floor | NINTH FLOOR TOILET-1 DETAIL | Shivangee | 2025-12-19 | 2025-05-24 | 2025-12-15 | 2026-01-06 |  | 2026-01-15 | 2025-12-18 | 2026-01-22 | 2025-12-19
462 | Structural | New Building | WMHL-A47-09-01.2 | Ninth floor | NINTH FLOOR TOILET-2 DETAIL | Shivangee | 2025-12-19 | 2025-05-24 | 2025-12-12 | 2026-01-06 |  | 2026-01-15 | 2025-12-18 | 2026-01-22 | 2025-12-19 | MEP Coordinated Drawing wih design inputs of fixtures and duct layouts
463 | Structural | New Building | WMHL-A54-01.21 | Ninth floor | NINTH FLOOR DOOR DETAILS SHEET 1 | Shivangee | 2025-05-31 | 2025-05-31 | 2025-07-02 | 2025-06-17 |  | 2025-06-26 | 2025-12-09 | 2025-07-03 |  | MEP Coordinated Drawing wih design inputs of fixtures and duct layouts
464 | Structural | New Building | WMHL-A54-01.22 | Ninth floor | NINTH FLOOR DOOR DETAILS SHEET 2 | Shivangee | 2025-05-31 | 2025-05-31 | 2025-07-02 | 2025-06-17 |  | 2025-06-26 | 2025-12-09 | 2025-07-03 |  | MEP Coordinated Drawing wih design inputs of fixtures and duct layouts
465 | Structural | New Building | WMHL-A60-11 | Ninth floor | NINTH FLOOR RCP | Shivangee | 2025-12-22 | 2025-06-21 | 2026-04-02 | 2026-01-07 |  | 2025-11-15 | 2026-04-20 | 2025-11-22
466 | Structural | New Building | WMHL-A25-12 | Ninth floor | NINTH FLOOR FLOORING LAYOUT |  | 2025-12-19 |  | 2025-12-12 | 2026-01-06 |  | 2026-01-15 | 2025-12-15 | 2026-01-22 | 2025-12-19
467 | Structural | New Building | WMHL-A20-10-01 | Tenth Floor | 10TH FLOOR PLAN | Shivangee | 2025-12-21 | 2025-03-03 | 2025-03-03 | 2026-01-06 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07
468 | Structural | New Building | WMHL-A44-12 | Tenth Floor | TENTH FLOOR FURNITURE LAYOUT | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-26 | 2025-03-31 | 2025-03-28 | 2025-04-07
469 | Structural | New Building | WMHL-A46-05 | Tenth Floor | 10TH FLOOR PANTRY-1 DETAIL | Shivangee | 2025-12-29 | 2025-06-21 | 2025-12-12 | 2026-01-14 |  | 2026-01-23 | 2025-12-15 | 2026-01-30 | 2025-12-27
470 | Structural | New Building | WMHL-A47-12.1 | Tenth Floor | TENTH FLOOR TOILET-1 DETAIL | Shivangee | 2025-12-29 | 2025-06-21 | 2025-12-12 | 2026-01-14 |  | 2026-01-23 | 2025-12-15 | 2026-01-30 | 2025-12-27
471 | Structural | New Building | WMHL-A47-12.2 | Tenth Floor | TENTH FLOOR TOILET-2 DETAIL | Shivangee | 2025-12-29 | 2025-06-21 | 2025-12-12 | 2026-01-14 |  | 2026-01-23 | 2025-12-15 | 2026-01-30 | 2025-12-27
472 | Structural | New Building | WMHL-A54-01.23 | Tenth Floor | TENTH FLOOR DOOR DETAILS SHEET 1 | Shivangee | 2025-06-21 | 2025-06-21 | 2025-07-04 | 2025-07-08 |  | 2025-07-17 | 2025-12-09 | 2025-07-24
473 | Structural | New Building | WMHL-A54-01.24 | Tenth Floor | TENTH FLOOR DOOR DETAILS SHEET 2 | Shivangee | 2025-06-21 | 2025-06-21 | 2025-07-04 | 2025-07-08 |  | 2025-07-17 | 2025-12-09 | 2025-07-24
474 | Structural | New Building | WMHL-A60-12 | Tenth Floor | TENTH FLOOR RCP | Shivangee | 2025-12-29 | 2025-06-21 | 2026-03-12 | 2026-01-14 |  | 2026-01-23 | 2026-04-20 | 2026-01-30 |  | MEP Coordinated Drawing wih design inputs of fixtures and duct layouts
475 | Structural | New Building | WMHL-A25-13 | Tenth Floor | TENTH FLOOR FLOORING LAYOUT | Shivangee | 2025-12-29 | 2025-06-21 | 2025-12-04 | 2026-01-14 |  | 2026-01-23 | 2025-12-09 | 2026-01-30 | 2025-12-27
476 | Structural | New Building | WMHL-A47-12.3 | Tenth Floor | TENTH FLOOR TOILET-3 DETAIL |  | 2025-12-29 |  | 2025-12-12 | 2026-01-14 |  | 2026-01-23 | 2025-12-15 | 2026-01-30 | 2025-12-27
477 | Structural | New Building | WMHL-A47-12.4 | Tenth Floor | TENTH FLOOR TOILET-4 DETAIL |  | 2025-12-29 |  | 2025-12-12 | 2026-01-14 |  | 2026-01-23 | 2025-12-15 | 2026-01-30 | 2025-12-27
478 | Structural | New Building | WMHL-A10-07 | Detail Drawings | STP DETAIL | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-04-05
479 | Structural | New Building | WMHL-A42-01.1 | Detail Drawings | STAIRCASE-2 DETAILS (SHEET 1) | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-04-05
480 | Structural | New Building | WMHL-A42-01.2 | Detail Drawings | STAIRCASE-2 DETAILS (SHEET 2) | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-04-05
481 | Structural | New Building | WMHL-A42-02.1 | Detail Drawings | STAIRCASE-3 DETAILS (SHEET 1) | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-04-05
482 | Structural | New Building | WMHL-A42-02.2 | Detail Drawings | STAIRCASE-3 DETAILS (SHEET 2) | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-04-05
483 | Structural | New Building | WMHL-A42-03 | Detail Drawings | STAIRCASE-4 (pump room) DETAILS | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-31 | 2025-04-09 | 2025-04-24 | 2025-04-16 | 2025-09-19
484 | Structural | New Building | WMHL-A43-01 | Detail Drawings | VISITORS LIFT DETAILS | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-04-24 | 2025-04-04 | 2025-04-05
485 | Structural | New Building | WMHL-A43-03 | Detail Drawings | PATIENT LIFT DETAILS | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-04-24 | 2025-04-04 | 2025-04-05
486 | Structural | New Building | WMHL-A54-04 | Detail Drawings | LINAC DETAILS | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-05-28
487 | Structural | New Building | WMHL-A43-02 | Detail Drawings | SERVICE LIFT DETAILS | Shivangee | 2025-03-28 | 2025-03-28 | 2025-03-26 | 2025-04-15 |  | 2025-04-24 | 2025-03-28 | 2025-05-01
488 | Structural | New Building | WMHL-A54-01.1 | Detail Drawings | DOOR & WINDOW SCHEDULE SHEET | Shivangee | 2025-04-05 | 2025-04-05 | 2025-04-05 | 2025-04-22 |  | 2025-05-01 | 2025-12-09 | 2025-05-08
489 | Structural | New Building | WMHL-A54-01.2 | Detail Drawings | DOOR DETAILS SHEET 1 | Shivangee | 2025-04-05 | 2025-04-05 | 2025-04-05 | 2025-04-22 |  | 2025-05-01 | 2025-12-09 | 2025-05-08
490 | Structural | New Building | WMHL-A54-01.3 | Detail Drawings | DOOR DETAILS SHEET 2 | Shivangee | 2025-04-05 | 2025-04-05 | 2025-04-10 | 2025-04-22 |  | 2025-05-01 | 2025-12-09 | 2025-05-08
491 | Structural | New Building | WMHL-A47-11-01.1 | Detail Drawings | TOILET FIXING DETAILS SHEET 1 | Shivangee | 2025-04-05 | 2025-04-05 | 2025-05-02 | 2025-04-22 |  | 2025-05-01 | 2026-04-20 | 2025-05-08
492 | Structural | New Building | WMHL-A54-02.1 | Detail Drawings | WINDOW DETAILS SHEET 1 | Shivangee | 2025-04-12 | 2025-04-12 | 2025-04-17 | 2025-04-29 |  | 2025-05-08 | 2025-12-09 | 2025-05-15
493 | Structural | New Building | WMHL-A10-06 | Detail Drawings | PUMP ROOM & UGR DETAILS | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 |  | 2025-03-28 | 2025-05-16 | 2025-04-04 | 2025-05-28
494 | Structural | New Building | WMHL-A10-08 | Detail Drawings | HT ROOM DETAILS | Shivangee | 2025-03-03: 2025-11-24; 2025-03-03: 2025-07-05; 2025-03-19: 2025-12-10; 2025-03-28: 2025-12-19; 2025-04-04: 2025-12-26
495 | Structural | New Building | WMHL-A10-09 | Detail Drawings | BWS ROOM DETAILS | Shivangee | 2025-11-26 | 2025-07-05 | 2026-01-21 | 2025-12-12 |  | 2025-12-23 | 2026-05-15 | 2025-12-30
496 | Structural | New Building | WMHL-A10-10 | Detail Drawings | SECURITY ROOM 01- DETAILS | Shivangee | 2025-11-28 | 2025-07-05 | 2026-01-21 | 2025-12-16 |  | 2025-12-25 | 2026-05-15 | 2026-01-01
497 | Structural | New Building | WMHL-A10-04 | External | MASTER PLAN WITH ROAD LAYOUT | Shivangee | 2025-12-31 | 2025-06-28 | 2026-01-15 | 2026-01-16 |  | 2026-01-27 | 2026-05-15 | 2026-02-03
498 | Structural | New Building | WMHL-A10-05 | External | COORDINATED MASTER PLAN | Shivangee | 2025-12-31 | 2025-06-28 | 2026-02-13 | 2026-01-16 |  | 2026-01-27 | 2026-05-15 | 2026-02-03
499 | Structural | New Building | WMHL-A10-12 | External | ROAD SECTIONS | Shivangee | 2025-12-31 | 2025-07-05 | 2026-02-13 | 2026-01-16 |  | 2026-01-27 | 2026-05-15 | 2026-02-03
500 | Structural | New Building | WMHL-A10-13 | External | BOUNDARY WALL DETAILS | Shivangee | 2025-12-08 | 2025-07-05 | 2026-01-22 | 2025-12-24 |  | 2026-01-02 | 2026-05-15 | 2026-01-09
501 | Structural | New Building | WMHL-A10-14 | External | GATE 01 DETAILS | Shivangee | 2025-12-10 | 2025-07-05 | 2026-01-21 | 2025-12-26 |  | 2026-01-06 | 2026-05-15 | 2026-01-13
502 | Structural | New Building | WMHL-A20-RF-01 | Roof Floor | ROOF PLAN | Shivangee | 2025-12-31 | 2025-03-03 | 2025-10-10 | 2026-01-16 |  | 2025-10-17 | 2026-04-20 | 2025-10-24
503 | Structural | New Building | WMHL-A44-13 | Roof Floor | ROOF FURNITURE LAYOUT | Shivangee | 2025-10-10 | 2025-03-03 | 2025-10-10 | 2025-03-31 |  | 2025-10-17 | 2026-04-20 | 2025-10-24
504 | Structural | New Building | WMHL-A60-13 | Roof Floor | ROOF RCP | Shivangee | 2025-12-31 | 2025-06-28 | 2026-04-08 | 2026-01-16 |  | 2026-01-27 | 2026-05-15 | 2026-02-03 |  | MEP Coordinated Drawing wih design inputs of fixtures and duct layouts
505 | Structural | New Building | WMHL-A25-14 | Roof Floor | ROOF FLOORING | Shivangee | 2025-12-31 | 2025-06-21 | 2025-12-29 | 2026-01-16 |  | 2026-01-27 | 2026-01-09 | 2026-02-03
506 | Structural | New Building | WMHL-A47-11-01.2 | Roof Floor | ROOF FLOOR TOILET-1 DETAIL | Shivangee | 2025-06-28 | 2025-06-28 | 2025-06-27 | 2025-07-15 |  | 2025-07-24 | 2025-07-02 | 2025-07-31 | 2025-12-19
507 | Structural | New Building | WMHL-A54-01.25 | Roof Floor | ROOF FLOOR DOOR DETAILS SHEET 1 | Shivangee | 2025-06-28 | 2025-06-28 | 2025-07-04 | 2025-07-15 |  | 2025-07-24 | 2025-09-12 | 2025-07-31
508 | Structural | New Building | WMHL-A54-01.26 | Roof Floor | ROOF FLOOR DOOR DETAILS SHEET 2 | Shivangee | 2025-06-28 | 2025-06-28 | 2025-07-04 | 2025-07-15 |  | 2025-07-24 | 2025-09-12 | 2025-07-31
509 | Structural | New Building | WMHL-A10-02 | Overall Plan, Elevations & Sections | BLOCK LAYOUT PLAN | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-04-03
510 | Structural | New Building | WMHL-A10-03 | Overall Plan, Elevations & Sections | COLUMN AND GRID SETTING OUT PLAN | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-19 | 2025-03-19 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-04-03
511 | Structural | New Building | WMLH-A30-00-01 | Overall Plan, Elevations & Sections | ELEVATION A | Shivangee | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-04-11 |  | 2025-04-22 | 2025-09-12 | 2025-04-29
512 | Structural | New Building | WMLH-A30-00-02 | Overall Plan, Elevations & Sections | ELEVATION B & C | Shivangee | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-04-11 |  | 2025-04-22 | 2025-09-12 | 2025-04-29
513 | Structural | New Building | WMLH-A30-00-03 | Overall Plan, Elevations & Sections | ELEVATION D | Shivangee | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-04-11 |  | 2025-04-22 | 2025-09-12 | 2025-04-29
514 | Structural | New Building | WMHL-A35-01 | Overall Plan, Elevations & Sections | SECTION A-A | Shivangee | 2025-12-31 | 2025-03-28 | 2025-12-15 | 2026-01-16 |  | 2026-01-27 | 2025-12-18 | 2026-02-03
515 | Structural | New Building | WMLH-A35-02 | Overall Plan, Elevations & Sections | SECTION B-B | Shivangee | 2025-12-31 | 2025-03-28 | 2025-12-15 | 2026-01-16 |  | 2026-01-27 | 2025-12-18 | 2026-02-03
516 | Structural | New Building | WMLH-A35-03 | Overall Plan, Elevations & Sections | SECTION C-C | Shivangee | 2025-12-31 | 2025-03-28 | 2025-12-15 | 2026-01-16 |  | 2026-01-27 | 2025-12-18 | 2026-02-03
517 | Structural | New Building | WMLH-A35-04 | Overall Plan, Elevations & Sections | SECTION D-D | Shivangee | 2025-12-31 | 2025-03-28 | 2025-12-15 | 2026-01-16 |  | 2026-01-27 | 2025-12-18 | 2026-02-03
518 | Structural | New Building | WMHL-A10-01 | Detail Drawings | GENERAL NOTES | Shivangee | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-13 | 2025-03-13 | 2025-03-24 | 2025-12-04 | 2025-03-31 | 2025-04-06
519 | Structural | Existing Building | WMHL-EX-A25-01 | Existing Building | GROUND FLOOR FLOORING LAYOUT | Shivangee | 2026-02-24 |  | 2025-03-25 | 2026-03-12 |  | 2026-03-23 | 2026-04-20 | 2026-03-30
520 | Structural | Existing Building | WMHL-EX-A60-01 | Existing Building | GROUND FLOOR RCP LAYOUT | Shivangee | 2025-03-03: 2026-02-28; 2025-03-19: 2026-03-17; 2025-03-28: 2026-03-27; 2025-04-04: 2026-04-03
521 | Structural | Existing Building | WMHL-EX-A20-00-01 | Existing Building | GROUND FLOOR PLAN | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-02-21 | 2026-03-09
522 | Structural | Existing Building | WMHL-EX-A44-01 | Existing Building | GROUND FLOOR FURNITURE LAYOUT | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-02-21 | 2026-03-09
523 | Structural | Existing Building | WMHL-EX-A25-02 | Existing Building | FIRST FLOOR FLOORING LAYOUT | Shivangee | 2026-02-24 |  | 2025-03-25 | 2026-03-12 |  | 2026-03-23 | 2026-04-20 | 2026-03-30
524 | Structural | Existing Building | WMHL-EX-A60-02 | Existing Building | FIRST FLOOR RCP LAYOUT | Shivangee | 2025-03-03: 2026-02-28; 2025-03-19: 2026-03-17; 2025-03-28: 2026-03-27; 2025-04-04: 2026-04-03
525 | Structural | Existing Building | WMHL-EX-A20-01-01 | Existing Building | FIRST FLOOR PLAN | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-02-21 | 2026-03-09
526 | Structural | Existing Building | WMHL-EX-A44-02 | Existing Building | FIRST FLOOR FURNITURE LAYOUT | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-02-21 | 2026-03-09
527 | Structural | Existing Building | WMHL-EX-A25-03 | Existing Building | SECOND FLOOR FLOORING LAYOUT | Shivangee | 2026-02-24 |  | 2025-03-25 | 2026-03-12 |  | 2026-03-23 | 2026-04-20 | 2026-03-30
528 | Structural | Existing Building | WMHL-EX-A60-03 | Existing Building | SECOND FLOOR RCP LAYOUT | Shivangee | 2025-03-03: 2026-02-28; 2025-03-19: 2026-03-17; 2025-03-28: 2026-03-27; 2025-04-04: 2026-04-03
529 | Structural | Existing Building | WMHL-EX-A20-02-01 | Existing Building | SECOND FLOOR PLAN | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-02-21 | 2026-03-09
530 | Structural | Existing Building | WMHL-EX-A44-03 | Existing Building | SECOND FLOOR FURNITURE LAYOUT | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-02-21 | 2026-03-09
531 | Structural | Existing Building | WMHL-EX-A25-04 | Existing Building | THIRD FLOOR FLOORING LAYOUT | Shivangee | 2026-02-24 |  | 2026-03-25 | 2026-03-12 |  | 2026-03-23 | 2026-04-20 | 2026-03-30
532 | Structural | Existing Building | WMHL-EX-A60-04 | Existing Building | THIRD FLOOR RCP LAYOUT | Shivangee | 2025-03-03: 2026-02-28; 2025-03-19: 2026-03-17; 2025-03-28: 2026-03-27; 2025-04-04: 2026-04-03
533 | Structural | Existing Building | WMHL-EX-A20-03-01 | Existing Building | THIRD FLOOR PLAN | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-02-21 | 2026-03-09
534 | Structural | Existing Building | WMHL-EX-A44-04 | Existing Building | THIRD FLOOR FURNITURE LAYOUT | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-02-21 | 2026-03-09
535 | Structural | Existing Building | WMHL-EX-A25-05 | Existing Building | FOURTH FLOOR FLOORING LAYOUT | Shivangee | 2026-02-24 |  | 2025-03-25 | 2026-03-12 |  | 2026-03-23 | 2026-04-20 | 2026-03-30
536 | Structural | Existing Building | WMHL-EX-A60-05 | Existing Building | FOURTH FLOOR RCP LAYOUT | Shivangee | 2025-03-03: 2026-02-28; 2025-03-19: 2026-03-17; 2025-03-28: 2026-03-27; 2025-04-04: 2026-04-03
537 | Structural | Existing Building | WMHL-EX-A20-04-01 | Existing Building | FOURTH FLOOR PLAN | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-02-21 | 2026-03-09
538 | Structural | Existing Building | WMHL-EX-A44-05 | Existing Building | FOURTH FLOOR FURNITURE LAYOUT | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-02-21 | 2026-03-09
539 | Structural | Existing Building | WMHL-EX-A25-06 | Existing Building | FIFTH FLOOR FLOORING LAYOUT | Shivangee | 2026-02-24 |  | 2026-04-20 | 2026-03-12 |  | 2026-03-23 | 2026-04-20 | 2026-03-30
540 | Structural | Existing Building | WMHL-EX-A60-06 | Existing Building | FIFTH FLOOR RCP LAYOUT | Shivangee | 2025-03-03: 2026-02-28; 2025-03-19: 2026-03-17; 2025-03-28: 2026-03-27; 2025-04-04: 2026-04-03
541 | Structural | Existing Building | WMHL-EX-A20-05-01 | Existing Building | FIFTH FLOOR PLAN | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-04-20 | 2026-03-09
542 | Structural | Existing Building | WMHL-EX-A44-06 | Existing Building | FIFTH FLOOR FURNITURE LAYOUT | Shivangee | 2026-02-03 |  | 2026-02-03 | 2026-02-19 |  | 2026-03-02 | 2026-04-20 | 2026-03-09

## DRG_Status
DRG ID | Discipline | 1st Submission Plan_wk | Actual Submission to Client_wk | Planned Approval_wk | Actual Approval_wk | 1st Submission Plan_mth | Actual Submission to Client_mth | Planned Approval_mth | Actual Approval_mth
WLH/KEC/SIEC/SEWAGE/BASEMENT/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/DRAINAGE/BASEMENT/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/WATER SUPPLY/GF FL/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/DRAINAGE/GF FL/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/WATER SUPPLY/1ST FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/DRAINAGE/1ST FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/WATER SUPPLY/2ND FL/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/DRAINAGE/2ND FL/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/WATER SUPPLY/3RD FL/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/DRAINAGE/3RD FL/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/WATER SUPPLY/4TH FL/00 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-06-01
WLH/KEC/SIEC/DRAINAGE/4TH FL/00 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/WATER SUPPLY/5TH FL/00 | MEP | 2025-05-26 | 2025-06-30 | 2025-06-16 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/DRAINAGE/5TH FL/00 | MEP | 2025-05-26 | 2025-06-30 | 2025-06-16 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/WATER SUPPLY/6TH FL/00 | MEP | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/DRAINAGE/6TH FL/00 | MEP | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/WATER SUPPLY/7TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/DRAINAGE/7TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/WATER SUPPLY/8TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/DRAINAGE/8TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/WATER SUPPLY/9TH FL/00 | MEP | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/DRAINAGE/9TH FL/00 | MEP | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/WATER SUPPLY/10TH FL/00 | MEP | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/DRAINAGE/10TH FL/00 | MEP | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/WATER SUPPLY/TERRACE FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/DRAINAGE/TRRRACE FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/DRAINAGE/MUMTY TERRACE FL/00 | MEP | 2025-11-10 | 2025-11-24 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/PHE/INFRA/EXTSEWERAGE/00 | MEP | 2025-03-10 | 2025-11-03 | 2025-05-26 | 2026-02-16 | 2025-03-01 | 2025-11-01 | 2025-05-01 | 2026-02-01
WLH/KEC/SIEC/PHE/INFRA/00 | MEP | 2025-03-10 | 2025-11-03 | 2025-05-26 | 2026-02-16 | 2025-03-01 | 2025-11-01 | 2025-05-01 | 2026-02-01
WLH/KEC/SIEC/PHE/INFRA WATER SUPPLY/00 | MEP | 2025-03-10 | 2025-11-03 | 2025-05-26 | 2026-02-16 | 2025-03-01 | 2025-11-01 | 2025-05-01 | 2026-02-01
WLH/KEC/SIEC/PHE/INFRA/EXTSTORMWATER/00 | MEP | 2025-03-10 | 2025-11-03 | 2025-05-26 | 2026-02-16 | 2025-03-01 | 2025-11-01 | 2025-05-01 | 2026-02-01
WLH/KEC/SIEC/PHE/INFRA/RECHARGE BOREWELL00 | MEP | 2025-03-10 | 2025-11-03 | 2025-05-26 | 2026-02-16 | 2025-03-01 | 2025-11-01 | 2025-05-01 | 2026-02-01
WLH/KEC/SIEC/WATER SUPPLY SLD/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-05-26 | 2026-02-23 | 2025-03-01 | 2025-03-01 | 2025-05-01 | 2026-02-01
WLH/KEC/SIEC/SANITARY DRAINAGE/SLD/00 | MEP | 2025-06-16 | 2025-08-25 | 2025-06-23 | 2025-08-25 | 2025-06-01 | 2025-08-01 | 2025-06-01 | 2025-08-01
WLH/KEC/SIEC/RAIN WATER DRAINAGE/SLD/00 | MEP | 2025-06-16 | 2025-08-25 | 2025-06-23 | 2025-08-25 | 2025-06-01 | 2025-08-01 | 2025-06-01 | 2025-08-01
WLH/KEC/SIEC/OWT/PHE/00 | MEP | 2025-06-16 | 2025-11-24 | 2025-06-23 |  | 2025-06-01 | 2025-11-01 | 2025-06-01
WLH/KEC/SIEC/DRAINAGE/BASEMENT/DEWATERING/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-05-26 | 2025-05-26 | 2025-03-01 | 2025-03-01 | 2025-05-01 | 2025-05-01
WLH/KEC/SIEC/PHE/CONST. DETAILS/00 | MEP | 2025-03-10 | 2025-08-25 | 2025-05-26 | 2025-08-25 | 2025-03-01 | 2025-08-01 | 2025-05-01 | 2025-08-01
WLH/KEC/SIEC/WATER SUPPLY/EXTERNAL/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-05-26 | 2026-02-16 | 2025-03-01 | 2025-03-01 | 2025-05-01 | 2026-02-01
WLH/KEC/SIEC/PHE/BASEMENT TOILET/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-05-26 | 2025-05-26 | 2025-03-01 | 2025-03-01 | 2025-05-01 | 2025-05-01
WLH/KEC/SIEC/DRAINAGE/SUMP DETAIL/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-05-26 | 2025-05-26 | 2025-03-01 | 2025-03-01 | 2025-05-01 | 2025-05-01
WLH/KEC/STP/BASEMENT/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-04-14 | 2025-04-14 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-04-01
WLH/KEC/STP/SCHEMATIC | MEP | 2025-03-10 | 2025-03-10 | 2025-04-07 | 2025-04-07 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-04-01
WLH/KEC/ETP/SCHEMATIC | MEP | 2025-03-10 | 2025-03-10 | 2025-04-07 | 2025-04-07 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-04-01
WLH/KEC/ETP/BASEMENT/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-04-07 | 2025-04-07 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-04-01
WLH/KEC/SIEC/PHE/IRRIGATION/00 | MEP | 2025-03-10 | 2025-11-03 | 2025-05-26 | 2026-02-16 | 2025-03-01 | 2025-11-01 | 2025-05-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/INFRA/00 | MEP | 2025-03-10 | 2025-11-03 | 2025-06-02 | 2026-03-02 | 2025-03-01 | 2025-11-01 | 2025-06-01 | 2026-03-01
WLH/KEC/SIEC/ELEC/DG/00 | MEP | 2025-12-29 | 2026-02-02 | 2025-06-02 | 2026-03-02 | 2025-12-01 | 2026-02-01 | 2025-06-01 | 2026-03-01
WLH/KEC/SIEC/ELEC/EXTERNAL LIGHTING/00 | MEP | 2025-07-14 | 2025-11-10 | 2025-08-11 |  | 2025-07-01 | 2025-11-01 | 2025-08-01
WLH/KEC/SIEC/ELEC/SUBSTATION/00 | MEP | 2025-06-09 | 2025-11-03 | 2025-07-07 | 2026-03-02 | 2025-06-01 | 2025-11-01 | 2025-07-01 | 2026-03-01
WLH/KEC/SIEC/ELEC/EARTHING GRID SCHEMATIC/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-06-02 |  | 2025-03-01 | 2025-03-01 | 2025-06-01
WLH/KEC/SIEC/ELECTRICAL/DBR/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-06-02 | 2025-05-26 | 2025-03-01 | 2025-03-01 | 2025-06-01 | 2025-05-01
WLH/KEC/SIEC/ELEC/MUMTY TERRACE SOLAR/00 | MEP | 2025-07-14 | 2025-11-10 | 2025-08-11 | 2026-02-02 | 2025-07-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/EQUIPMENT & EARTHING/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-06-02 | 2026-02-23 | 2025-03-01 | 2025-03-01 | 2025-06-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/HEIGHT SCHEDULE/00 | MEP | 2025-07-14 | 2025-03-10 | 2025-08-11 | 2025-05-26 | 2025-07-01 | 2025-03-01 | 2025-08-01 | 2025-05-01
WLH/KEC/SIEC/ELEC/EXTCT/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-06-02 | 2026-02-23 | 2025-03-01 | 2025-03-01 | 2025-06-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/MAIN ROOM DETAILED LAYOUT/00 | MEP | 2025-03-10 | 2025-03-10 | 2025-06-02 | 2026-02-23 | 2025-03-01 | 2025-03-01 | 2025-06-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/UPS/00 | MEP | 2025-12-29 | 2026-02-02 | 2026-01-26 | 2026-02-23 | 2025-12-01 | 2026-02-01 | 2026-01-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/BASEMENT/01 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/BASEMENT/02 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/BASEMENT/03 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/BASEMENT/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/ELEC/BASEMENT/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/GR FL/01 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/GR FL/02 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/GR FL/03 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/GR FL/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/ELEC/GFCT/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/1ST FL/01 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/1ST FL/02 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/1ST FL/03 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/1ST FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/POWERCONDUIT/2ND FL/01 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/POWERCONDUIT/2ND FL/02 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/POWERCONDUIT/2ND FL/03 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/2ND FL/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/2NDCT/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/3RD FL/01 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/3RD FL/02 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/3RD FL/03 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/3RD FL/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/3RDCT/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/4TH FL/01 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/4TH FL/02 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/4TH FL/03 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/4TH FL/00 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/ELEC/4THCT/00 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/5TH FL/01 | MEP | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/5TH FL/02 | MEP | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/5TH FL/03 | MEP | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/5TH FL/00 | MEP | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/5THCT/00 | MEP | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/6TH FL/01 | MEP | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/6TH FL/02 | MEP | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/6TH FL/03 | MEP | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/6TH FL/00 | MEP | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/6THCT/00 | MEP | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/7TH FL/01 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/7TH FL/02 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/7TH FL/03 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/7TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/7THCT/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/8TH FL/01 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/8TH FL/02 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/8TH FL/03 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/8TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/8THCT/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/9TH FL/01 | MEP | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/9TH FL/02 | MEP | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/9TH FL/03 | MEP | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/9TH FL/00 | MEP | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/ELEC/9TH CT/00 | MEP | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/10TH FL/01 | MEP | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/10TH FL/02 | MEP | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/10TH FL/03 | MEP | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/10TH FL/00 | MEP | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/10THCT/00 | MEP | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/ELEC/POWER/TERRACE/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/POWER CONDUIT/TERRACE FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/LIGHTING CONDUIT/TERRACE FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/TERRACECT/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/SCHEMATIC DIAGRAM/00 | MEP | 2025-04-14 | 2025-04-14 | 2025-05-05 | 2025-05-26 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-05-01
WLH/KEC/SIEC/ELEC/LT ARRESTOR/00 | MEP | 2025-07-21 | 2025-10-06 | 2025-08-11 | 2026-02-16 | 2025-07-01 | 2025-10-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/AVIATION/00 | MEP | 2025-07-21 | 2025-10-06 | 2025-08-11 | 2026-02-16 | 2025-07-01 | 2025-10-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/ELEC/EXTPOWER/00 | MEP | 2025-07-21 | 2025-11-10 | 2025-08-11 |  | 2025-07-01 | 2025-11-01 | 2025-08-01
WLH/KEC/SIEC/ELV/INFRA/00 | MEP | 2025-03-10 | 2025-07-21 | 2025-04-07 | 2026-04-20 | 2025-03-01 | 2025-07-01 | 2025-04-01 | 2026-04-01
WLH/KEC/SIEC/ELV/CCTV/00 | MEP | 2025-11-24 | 2025-11-10 | 2025-12-22 | 2026-04-20 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2026-04-01
WLH/KEC/SIEC/ELV/DBR/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-21 | 2025-03-31 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-03-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/GR FL/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-21 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/1ST FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/2ND FL/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/3RD FL/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/4TH FL/00 | MEP | 2025-03-31 | 2025-05-19 | 2025-04-21 | 2025-06-02 | 2025-03-01 | 2025-05-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/5TH FL/00 | MEP | 2025-03-31 | 2025-06-30 | 2025-04-21 | 2025-10-13 | 2025-03-01 | 2025-07-01 | 2025-04-01 | 2025-10-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/6TH FL/00 | MEP | 2025-03-31 | 2025-07-07 | 2025-04-21 | 2025-10-13 | 2025-03-01 | 2025-07-01 | 2025-04-01 | 2025-10-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/7TH FL/00 | MEP | 2025-03-31 | 2025-08-25 | 2025-04-21 | 2025-10-13 | 2025-03-01 | 2025-08-01 | 2025-04-01 | 2025-10-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/8TH FL/00 | MEP | 2025-03-31 | 2025-08-25 | 2025-04-21 | 2025-10-27 | 2025-03-01 | 2025-08-01 | 2025-04-01 | 2025-10-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/9TH FL/00 | MEP | 2025-03-31 | 2025-07-21 | 2025-04-21 | 2025-07-07 | 2025-03-01 | 2025-07-01 | 2025-04-01 | 2025-07-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/10TH FL/00 | MEP | 2025-03-31 | 2025-09-08 | 2025-04-21 | 2025-10-13 | 2025-03-01 | 2025-09-01 | 2025-04-01 | 2025-10-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM/ELV/TERRACE FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-12-08 | 2025-10-13 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-10-01
WLH/KEC/SIEC/RODENT REPELLENT SYSTEM SLD/ELV/00 | MEP | 2025-12-15 | 2026-03-23 | 2026-01-05 |  | 2025-12-01 | 2026-03-01 | 2026-01-01
WLH/KEC/SIEC/ELV SLD/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-08-11 |  | 2025-03-01 | 2025-03-01 | 2025-08-01
WLH/KEC/SIEC/ELV/NURSE CALLING SLD/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-08-11 |  | 2025-03-01 | 2025-03-01 | 2025-08-01
WLH/KEC/SIEC/ELV/OPD CALLING SLD/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-08-11 | 2026-04-20 | 2025-03-01 | 2025-03-01 | 2025-08-01 | 2026-04-01
WLH/KEC/SIEC/ELV/BMS IO SUMMARY & SLD/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-08-11 |  | 2025-03-01 | 2025-03-01 | 2025-08-01
WLH/KEC/SIEC/ELV/CCTV SLD/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-08-11 |  | 2025-03-01 | 2025-03-01 | 2025-08-01
WLH/KEC/SIEC/ACCESS CONTROL SCHEMATIC/ELV/BASEMENT/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2026-04-20 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2026-04-01
WLH/KEC/SIEC/ELV/BASEMENT/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/BASEMENT/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/Heat map/ELV/BASEMENT/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/ELV/GF FL/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/Heat map/ELV/GF FL/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/GF FL/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/ELV/1ST FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/Heat map/ELV/1ST FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/1ST FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELV/2ND FL/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/Heat map/ELV/2ND FL/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/2ND FL/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELV/3RD FL/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/Heat map/ELV/3RD FL/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/3RD FL/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/ELV/4TH FL/00 | MEP | 2025-04-28 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/Heat map/ELV/4TH FL/00 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/4TH FL/00 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/ELV/5TH FL/00 | MEP | 2025-05-12 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/Heat map/ELV/5TH FL/00 | MEP | 2025-05-12 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/5TH FL/00 | MEP | 2025-05-12 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/ELV/6TH FL/00 | MEP | 2025-05-26 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/Heat map/ELV/6TH FL/00 | MEP | 2025-05-26 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/6TH FL/00 | MEP | 2025-05-26 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELV/7TH FL/00 | MEP | 2025-06-09 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/Heat map/ELV/7TH FL/00 | MEP | 2025-06-09 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/7TH FL/00 | MEP | 2025-06-09 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/AV SYSTEM/ELV/7TH FL/00 | MEP | 2025-06-09 | 2026-03-02 | 2025-07-14 |  | 2025-06-01 | 2026-03-01 | 2025-07-01
WLH/KEC/SIEC/ELV/8TH FL/00 | MEP | 2025-06-09 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/Heat map/ELV/8TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/8TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/ELV/9TH FL/00 | MEP | 2025-06-23 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-06-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/Heat map/ELV/9TH FL/00 | MEP | 2025-06-23 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-06-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/9TH FL/00 | MEP | 2025-06-23 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-06-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/ELV/10TH FL/00 | MEP | 2025-06-23 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-06-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/Heat map/ELV/10TH FL/00 | MEP | 2025-06-23 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-06-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/10TH FL/00 | MEP | 2025-06-23 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-06-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/AV SYSTEM/ELV/10TH FL/00 | MEP | 2025-07-07 | 2026-03-02 | 2025-07-28 |  | 2025-07-01 | 2026-03-01 | 2025-08-01
WLH/KEC/SIEC/Heat map/ELV/TERRACE/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/ELV/TERRACE/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/BMS SYSTEM/ELV/ABOVE TERRACE/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/WATER LEAK DETECTION/ELV/00 | MEP | 2025-12-15 | 2026-03-23 | 2025-08-11 |  | 2025-12-01 | 2026-03-01 | 2025-08-01
WLH/KEC/SIEC/ELV/BMS ROOM/MISC/00 | MEP | 2025-12-29 | 2026-04-13 | 2025-05-26 |  | 2025-12-01 | 2026-04-01 | 2025-05-01
WLH/KEC/SIEC/FDA/BASEMENT/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/FPS/BASEMENT/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /BASEMENT/00 | MEP | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/FDA & PA/GR FL/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/FPS/GR FL/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /GR FL/01 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /1ST FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/FDA& PA/1ST FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/FPS/1ST FL/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /2ND FL/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/FDA & PA/2ND FL/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/FPS/2ND FL/00 | MEP | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /3RD FL/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/FDA & PA/3RD FL/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/FPS/3RD FL/00 | MEP | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /4TH FL/00 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/FDA & PA/4TH FL/00 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/FPS/4TH FL/00 | MEP | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /5TH FL/00 | MEP | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/FDA & PA/5TH FL/00 | MEP | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/FPS/5TH FL/00 | MEP | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /6TH FL/00 | MEP | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/FDA & PA/6TH FL/00 | MEP | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/FPS/6TH FL/00 | MEP | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /7TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/FDA & PA/7TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/FPS/7TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /8TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/FDA & PA/8TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/FPS/8TH FL/00 | MEP | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /9TH FL/00 | MEP | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/FDA & PA/9TH FL/00 | MEP | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/FPS/9TH FL/00 | MEP | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/FDA & PA/10TH FL/00 | MEP | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/FPS/10TH FL/00 | MEP | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/SIGNAGE & EXTINGUISHER /10TH FL/00 | MEP | 2025-11-10 | 2025-11-17 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/FDA & PA/TERRACE/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/FPS/TERRACE/00 | MEP | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/FIRE/INFRA/PUMP ROOM/00 | MEP | 2025-04-14 | 2025-04-14 | 2025-05-12 | 2025-04-14 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-04-01
WLH/KEC/SIEC/FIRE/EXTHYDRANT/00 | MEP | 2025-03-10 | 2025-11-03 | 2025-06-02 | 2026-02-16 | 2025-03-01 | 2025-11-01 | 2025-06-01 | 2026-02-01
WLH/KEC/SIEC/FIRE/PUMP HEAD CALCULATION/00 | MEP | 2025-03-10 | 2025-04-14 | 2025-04-07 | 2025-04-07 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-04-01
WLH/KEC/SIEC/FPS SLD/00 | MEP | 2025-03-10 | 2025-04-14 | 2025-04-07 | 2025-04-07 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-04-01
WLH/KEC/SIEC/FDA & PA SLD/00 | MEP | 2025-03-10 | 2025-04-14 | 2025-04-07 | 2025-04-07 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-04-01
WLH/KEC/SIEC/PASCHEMATIC/00 | MEP | 2025-03-10 | 2025-04-14 | 2025-04-07 | 2025-04-07 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-04-01
WLH/KEC/SIEC/FIRE & BMS ROOM/00 | MEP | 2025-03-31 | 2025-04-07 | 2025-04-21 | 2026-02-16 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2026-02-01
WLH/KEC/SIEC/FIRE/WET RISER/00 | MEP | 2025-03-10 | 2025-04-14 | 2025-04-07 | 2025-04-07 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-04-01
WLH/KEC/SIEC/HVAC/BASEMENT/DUCTING/00 | Structural | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/HVAC/BASEMENT/CHW PIPING/00 | Structural | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/HVAC/BASEMENT/VENTILATION LAYOUT/00 | Structural | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/HVAC/BASEMENT/SMOKE EXTRACTION/00 | Structural | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/HVAC/BASEMENT/FRESH AIR/00 | Structural | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/HVAC/GF FL/CHW PIPING/00 | Structural | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/HVAC/BASEMENT/ZONING/00 | Structural | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/HVAC/GR FL/SMOKE EXTRACTION/00 | Structural | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/HVAC/GR FL/SMOKE EXTRACTION/00-00 | Structural | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/GR FL/00 | Structural | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/HVAC/1ST FL/DUCTING/00 | Structural | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/1ST FL/CHW PIPING/00 | Structural | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/1ST FL/SMOKE EXTRACTION/00 | Structural | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/1ST FL/FRESH AIR/00 | Structural | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/1STFL/00 | Structural | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/2ND FL/DUCTING/00 | Structural | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/2ND FL/CHW PIPING/00 | Structural | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/2ND FL/SMOKE EXTRACTION/00 | Structural | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/2ND FL/FRESH AIR/00 | Structural | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/2ND FL/00 | Structural | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/3RD FL/DUCTING/00 | Structural | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/3RD FL/00 | Structural | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/3RD FL/SMOKE EXTRACTION/00 | Structural | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/3RD FL/FRESH AIR/00 | Structural | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/3RD FL/00 | Structural | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/4TH F/DUCTINGL/00 | Structural | 2025-05-12 | 2025-06-09 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/HVAC/4TH FL/CHW PIPING/00 | Structural | 2025-05-12 | 2025-06-09 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/HVAC/4TH FL/SMOKE EXTRACTION/00 | Structural | 2025-05-12 | 2025-06-09 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/HVAC/4TH FL/FRESH AIR/00 | Structural | 2025-05-12 | 2025-06-09 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/4TH FL/00 | Structural | 2025-05-12 | 2025-06-09 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/HVAC/5TH FL/00 | Structural | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/5TH FL/CHW PIPING/00 | Structural | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/5TH FL/SMOKE EXTRACTION/00 | Structural | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/5TH FL/FRESH AIR/00 | Structural | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-10-13 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/5TH FL/00 | Structural | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-09-08 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-09-01
WLH/KEC/SIEC/HVAC/6TH FL/00 | Structural | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/6TH FL/CHW PIPING/00 | Structural | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/6TH FL/SMOKE EXTRACTION/00 | Structural | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/6TH FL/FRESH AIR/00 | Structural | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-10-13 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/6TH FL/00 | Structural | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-09-08 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-09-01
WLH/KEC/SIEC/HVAC/7TH FL/DUCTING/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/7TH FL/CHW PIPING/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/7TH FL/SMOKE EXTRACTION/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/7TH FL/FRESH AIR/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/7TH FL/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/8TH FL/DUCTING/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/8TH FL/CHW PIPING/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/8TH FL/SMOKE EXTRACTION/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/8TH FL/FRESH AIR/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/8TH FL/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/9TH FL/DUCTING/00 | Structural | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/HVAC/9TH FL/CHW PIPING/00 | Structural | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/HVAC/9TH FL/SMOKE EXTRACTION/00 | Structural | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/HVAC/9TH FL/FRESH AIR/00 | Structural | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/9TH FL/00 | Structural | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/HVAC/10TH FL/DUCTING/00 | Structural | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/10TH FL/CHW PIPING/00 | Structural | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/10 FL/SMOKE EXTRACTION/00 | Structural | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/10TH FL/FRESH AIR/00 | Structural | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION/10TH FL/00 | Structural | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/HVAC/TERRACE FL/DUCTING/00 | Structural | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/HVAC/TERRACE FL/CHW PIPING/00 | Structural | 2025-11-10 | 2025-11-24 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/HVAC/MUMTY TERRACE FL/DUCTING/00 | Structural | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/HVAC/STP VENTILATION/00 | Structural | 2025-07-21 | 2025-03-31 | 2025-08-11 | 2025-05-26 | 2025-07-01 | 2025-04-01 | 2025-08-01 | 2025-05-01
WLH/KEC/SIEC/HVAC/PRESSURIZATION BASEMENT/00 | Structural | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/HVAC/CHILLER PLANT FL/00 | Structural | 2025-03-31 | 2025-08-25 | 2025-04-14 | 2025-08-25 | 2025-03-01 | 2025-08-01 | 2025-04-01 | 2025-08-01
WLH/KEC/SIEC/HVAC/DBR/00 | Structural | 2025-03-10 | 2025-03-10 | 2025-04-07 | 2025-03-10 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-03-01
ESP CALCULATION FOR ALL FIRE MODE EQUIOMENTS | Structural | 2025-07-21 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 2025-07-01 | 2025-08-01 | 2025-08-01 | 2025-08-01
ESP CALCULATION FOR ALL EQUIPMENTS | Structural | 2025-07-21 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 2025-07-01 | 2025-08-01 | 2025-08-01 | 2025-08-01
PUMP HEAD CALCULATION | Structural | 2025-07-21 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 2025-07-01 | 2025-08-01 | 2025-08-01 | 2025-08-01
WLH/KEC/SIEC/HVAC/HEAT-LOAD/00 | Structural | 2025-03-10 | 2025-03-10 | 2025-04-07 | 2025-03-10 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-03-01
WLH/KEC/SIEC/HVAC/VENTILATION CALCULATION/00 | Structural | 2025-03-10 | 2025-03-10 | 2025-04-07 | 2025-03-10 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-03-01
WLH/KEC/SIEC/HVAC/AIR FLOW-DIAGRAM/00 | Structural | 2025-07-21 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 2025-07-01 | 2025-08-01 | 2025-08-01 | 2025-08-01
WLH/KEC/SIEC/HVAC/HVAC-SHAFT/00 | Structural | 2025-07-21 | 2025-03-10 | 2025-03-24 | 2025-03-10 | 2025-07-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WLH/KEC/SIEC/HVAC/CHILLED WATER SCHEMATIC/00 | Structural | 2025-11-24 | 2026-01-12 | 2025-12-22 |  | 2025-11-01 | 2026-01-01 | 2025-12-01
WLH/KEC/SIEC/HVAC/SCHEMATIC/00 | Structural | 2025-07-21 | 2025-08-25 | 2025-08-18 | 2025-08-25 | 2025-07-01 | 2025-08-01 | 2025-08-01 | 2025-08-01
WLH/KEC/SIEC/MEP/BASEMENT/00 | Structural | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/MEP SECTION/BASEMENT/00 | Structural | 2025-03-31 | 2025-03-31 | 2025-04-14 | 2025-05-26 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-05-01
WLH/KEC/SIEC/MEP/GR FL/00 | Structural | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/MEP SECTION/GR FL/00 | Structural | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-06-02 | 2025-03-01 | 2025-04-01 | 2025-04-01 | 2025-06-01
WLH/KEC/SIEC/MEP/1ST FL/00 | Structural | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/MEP SECTION/1ST FL/00 | Structural | 2025-11-10 | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/MEP/2ND FL/00 | Structural | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/MEP SECTION/2ND FL/00 | Structural | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/MEP/3RD FL/00 | Structural | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/MEP SECTION/3RD FL/00 | Structural | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
WLH/KEC/SIEC/MEP/4TH FL/00 | Structural | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/MEP SECTION/4TH FL/00 | Structural | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01
WLH/KEC/SIEC/MEP/5TH FL/00 | Structural | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-09-08 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-09-01
WLH/KEC/SIEC/MEP SECTION/5TH FL/00 | Structural | 2025-05-26 | 2025-06-30 | 2025-06-09 | 2025-09-08 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-09-01
WLH/KEC/SIEC/MEP/6TH FL/00 | Structural | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-09-08 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-09-01
WLH/KEC/SIEC/MEP SECTION/6TH FL/00 | Structural | 2025-06-09 | 2025-07-07 | 2025-06-30 | 2025-09-08 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-09-01
WLH/KEC/SIEC/MEP/7TH FL/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/MEP SECTION/7TH FL/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-13 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/MEP/8TH FL/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/MEP SECTION/8TH FL/00 | Structural | 2025-06-23 | 2025-08-25 | 2025-07-14 | 2025-10-27 | 2025-06-01 | 2025-08-01 | 2025-07-01 | 2025-10-01
WLH/KEC/SIEC/MEP/9TH FL/00 | Structural | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/MEP SECTION/9TH FL/00 | Structural | 2025-07-07 | 2025-06-16 | 2025-07-28 | 2025-07-07 | 2025-07-01 | 2025-06-01 | 2025-08-01 | 2025-07-01
WLH/KEC/SIEC/MEP/10TH FL/00 | Structural | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/MEP SECTION/10TH FL/01 | Structural | 2025-07-07 | 2025-09-08 | 2025-07-28 | 2025-10-13 | 2025-07-01 | 2025-09-01 | 2025-08-01 | 2025-10-01
WLH/KEC/SIEC/MEP/TERRACE FL/01 | Structural | 2025-11-10 | 2025-11-10 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WLH/KEC/SIEC/MEP SECTION/TERRACE FL/02 | Structural | 2025-11-10 | 2025-11-17 | 2025-08-11 | 2026-02-16 | 2025-11-01 | 2025-11-01 | 2025-08-01 | 2026-02-01
WMHL-A20-B1-01 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A20-B.LOFT-01 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A44-01 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A36-01 | Architecture | 2025-03-31 | 2025-03-31 | 2025-04-28 | 2025-09-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-09-01
WMHL-A36-02 | Architecture | 2025-03-31 | 2025-03-31 | 2025-04-28 | 2025-09-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-09-01
WMHL-A47-B1-01.1 | Architecture | 2025-03-31 | 2025-04-07 | 2025-04-28 | 2025-09-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-09-01
WMHL-A47-B1-01.2 | Architecture | 2025-03-31 | 2025-04-07 | 2025-04-28 | 2025-09-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-09-01
WMHL-A47-B1-01.3 | Architecture | 2025-03-31 | 2025-04-07 | 2025-04-28 | 2025-09-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-09-01
WMHL-A25-01 | Architecture | 2025-04-07 | 2025-04-07 | 2025-05-05 | 2025-04-28 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-05-01
WMHL-A25-02 | Architecture | 2025-04-07 | 2025-04-07 | 2025-05-05 | 2025-04-28 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-05-01
WMHL-A54-02.2 | Architecture | 2025-04-07 | 2025-04-14 | 2025-05-05 | 2025-09-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-09-01
WMLH-A41-02.1 | Architecture | 2025-05-26 | 2025-07-07 | 2025-06-23 | 2025-07-14 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-07-01
WMLH-A41-02.2 | Architecture | 2025-05-26 | 2025-07-07 | 2025-06-23 | 2025-07-14 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-07-01
WMLH-A41-03 | Architecture | 2025-05-26 | 2025-07-07 | 2025-06-23 | 2025-07-14 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-07-01
WMHL-A60-01 | Architecture | 2025-11-24 | 2025-11-17 | 2025-12-22 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A20-00-01 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A44-02 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A54-02 | Architecture | 2025-04-07 | 2025-04-14 | 2025-05-05 | 2025-09-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-09-01
WMHL-A47-00-01.1 | Architecture | 2025-04-07 | 2025-03-31 | 2025-05-05 | 2025-12-15 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-12-01
WMHL-A47-00-01.2 | Architecture | 2025-04-07 | 2025-03-31 | 2025-05-05 | 2025-12-15 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-12-01
WMHL-A47-00-01.3 | Architecture | 2025-04-07 | 2025-04-07 | 2025-05-05 | 2025-12-15 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-12-01
WMHL-A54-01.4 | Architecture | 2025-04-14 | 2025-04-14 | 2025-05-12 | 2025-09-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-09-01
WMHL-A54-01.5 | Architecture | 2025-04-14 | 2025-04-14 | 2025-05-12 | 2025-09-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-09-01
WMHL-A25-03 | Architecture | 2025-12-22 | 2025-12-15 | 2026-01-19 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A41-02 | Architecture | 2025-12-22 | 2025-12-15 | 2026-01-19 | 2026-01-05 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-01-01
WMHL-A60-02 | Architecture | 2025-12-22 | 2026-04-06 | 2026-01-19 | 2026-05-11 | 2025-12-01 | 2026-04-01 | 2026-01-01 | 2026-05-01
WMHL-A41-03 | Architecture | 2025-12-22 | 2025-12-08 | 2026-01-19 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A41-04 | Architecture | 2025-12-22 | 2025-12-01 | 2026-01-19 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A41-07 | Architecture | 2025-12-22 | 2025-12-01 | 2026-01-19 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A20-01-01 | Architecture | 2025-10-27 | 2025-10-20 | 2025-11-10 | 2025-10-27 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-10-01
WMHL-A44-03 | Architecture | 2025-10-27 | 2025-10-20 | 2025-11-10 | 2025-10-27 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-10-01
WMHL-A47-01-01.1 | Architecture | 2025-11-10 | 2025-11-10 | 2025-12-08 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A47-01-01.2 | Architecture | 2025-11-10 | 2025-11-10 | 2025-12-08 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A47-01-01.3 | Architecture | 2025-11-10 | 2025-11-10 | 2025-12-08 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A25-04 | Architecture | 2025-11-03 | 2025-11-03 | 2025-11-10 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-12-01
WMHL-A60-03 | Architecture | 2025-05-19 | 2025-03-10 | 2025-06-16 | 2026-04-20 | 2025-05-01 | 2025-03-01 | 2025-06-01 | 2026-04-01
WMHL-A20-02-01 | Architecture | 2025-10-20 | 2025-10-20 | 2025-11-10 | 2025-11-10 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-11-01
WMHL-A44-04 | Architecture | 2025-10-20 | 2025-10-20 | 2025-11-10 | 2025-11-10 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-11-01
WMHL-A46-02 | Architecture | 2025-12-01 | 2025-11-24 | 2025-12-29 | 2025-09-08 | 2025-12-01 | 2025-11-01 | 2026-01-01 | 2025-09-01
WMHL-A47-02-01.1 | Architecture | 2025-11-10 | 2025-11-10 | 2025-12-08 | 2025-12-08 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A47-02-01.2 | Architecture | 2025-11-10 | 2025-11-10 | 2025-12-08 | 2025-12-08 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A47-02-01.3 | Architecture | 2025-11-10 | 2025-11-10 | 2025-12-08 | 2025-12-08 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A54-01.7 | Architecture | 2025-05-05 | 2025-05-12 | 2025-06-02 | 2025-12-08 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-12-01
WMHL-A54-01.8 | Architecture | 2025-05-05 | 2025-05-12 | 2025-06-02 | 2025-12-08 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-12-01
WMHL-A60-04 | Architecture | 2025-12-01 | 2026-03-09 | 2025-12-29 | 2026-04-20 | 2025-12-01 | 2026-03-01 | 2025-12-01 | 2026-04-01
WMHL-A27-01 | Architecture | 2025-12-15 | 2025-11-03 | 2025-12-22 | 2025-11-10 | 2025-12-01 | 2025-11-01 | 2025-12-01 | 2025-11-01
WMHL-A27-02 | Architecture | 2025-12-15 | 2025-11-03 | 2025-12-22 | 2025-11-10 | 2025-12-01 | 2025-11-01 | 2025-12-01 | 2025-11-01
WMHL-A20-03-01 | Architecture | 2025-10-13 | 2025-10-13 | 2025-11-10 | 2025-10-20 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-10-01
WMHL-A44-05 | Architecture | 2025-10-13 | 2025-10-13 | 2025-11-10 | 2025-10-20 | 2025-10-01 | 2025-10-01 | 2025-11-01 | 2025-10-01
WMHL-A47-03-01.1 | Architecture | 2025-11-10 | 2025-11-17 | 2025-12-08 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A47-03-01.2 | Architecture | 2025-11-10 | 2025-11-17 | 2025-12-08 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A54-01.9 | Architecture | 2025-05-05 | 2025-05-12 | 2025-06-02 | 2025-12-08 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-12-01
WMHL-A54-01.10 | Architecture | 2025-05-05 | 2025-05-12 | 2025-06-02 | 2025-12-08 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-12-01
WMHL-A25-06 | Architecture | 2025-05-26 | 2025-06-16 | 2025-06-23 | 2025-11-10 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-11-01
WMHL-A41-05 | Architecture | 2025-12-01 | 2025-11-24 | 2025-12-29 | 2025-12-01 | 2025-12-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A60-05 | Architecture | 2025-12-08 | 2026-03-02 | 2025-11-10 | 2026-04-20 | 2025-12-01 | 2026-03-01 | 2025-11-01 | 2026-04-01
WMHL-A10-11 | Architecture | 2025-12-29 | 2026-01-19 | 2026-01-26 | 2026-05-11 | 2025-12-01 | 2026-01-01 | 2026-01-01 | 2026-05-01
WMHL-A20-04-01 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A44-06 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A47-04-01.1 | Architecture | 2025-11-24 | 2025-11-24 | 2025-12-22 | 2025-12-08 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A47-04-01.2 | Architecture | 2025-11-24 | 2025-11-24 | 2025-12-22 | 2025-12-08 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A54-01.11 | Architecture | 2025-05-05 | 2025-05-19 | 2025-06-02 | 2025-12-08 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-12-01
WMHL-A54-01.12 | Architecture | 2025-05-05 | 2025-05-19 | 2025-06-02 | 2025-12-08 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-12-01
WMHL-A25-07 | Architecture | 2025-11-24 | 2025-11-24 | 2025-12-22 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A60-06 | Architecture | 2025-11-24 | 2025-11-17 | 2025-12-22 | 2025-12-01 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A41-22 | Architecture | 2025-12-29 | 2025-11-24 | 2026-01-26 | 2025-09-29 | 2025-12-01 | 2025-11-01 | 2026-01-01 | 2025-10-01
WMHL-A20-05-01 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A44-07 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A47-05-01.1 | Architecture | 2025-11-24 | 2025-11-24 | 2025-12-22 | 2025-09-08 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-09-01
WMHL-A47-05-01.2 | Architecture | 2025-11-24 | 2025-11-24 | 2025-12-22 | 2025-09-08 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-09-01
WMHL-A47-05-01.3 | Architecture | 2025-11-24 | 2025-11-24 | 2025-12-22 | 2025-09-08 | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-09-01
WMHL-A54-01.13 | Architecture | 2025-05-12 | 2025-05-19 | 2025-06-09 | 2025-09-08 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-09-01
WMHL-A54-01.14 | Architecture | 2025-05-12 | 2025-05-19 | 2025-06-09 | 2025-09-08 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-09-01
WMHL-A46-03 | Architecture | 2025-12-01 | 2025-11-24 | 2025-12-29 | 2025-12-01 | 2025-12-01 | 2025-11-01 | 2025-12-01 | 2025-12-01
WMHL-A47-08-01.1 | Architecture | 2025-05-19 | 2025-06-23 | 2025-06-16 | 2025-12-15 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-12-01
WMHL-A47-08-01.2 | Architecture | 2025-05-19 | 2025-06-23 | 2025-06-16 | 2025-12-15 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-12-01
WMHL-A25-08.2 | Architecture | 2025-05-19 | 2025-06-23 | 2025-06-16 | 2025-06-30 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-07-01
WMHL-A41-01 | Architecture | 2025-06-23 | 2025-06-23 | 2025-07-21 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-07-01 | 2025-07-01
WMHL-A25-08.1 | Architecture | 2025-06-02 | 2025-06-23 | 2025-06-30 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-07-01 | 2025-07-01
WMHL-A60-07 | Architecture | 2025-12-08 | 2026-03-09 | 2026-01-05 | 2026-04-20 | 2025-12-01 | 2026-03-01 | 2026-01-01 | 2026-04-01
WMHL-A41-10.1 | Architecture | 2025-12-01 | 2025-12-01 | 2025-12-29 | 2026-04-20 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-04-01
WMHL-A41-10.2 | Architecture | 2025-12-01 | 2025-12-01 | 2025-12-29 | 2026-04-20 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2026-04-01
WMHL-A20-06-01 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A44-08 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A47-06-01.1 | Architecture | 2025-12-01 | 2025-12-01 | 2025-12-29 | 2025-09-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-09-01
WMHL-A47-06-01.2 | Architecture | 2025-12-01 | 2025-12-01 | 2025-12-29 | 2025-09-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-09-01
WMHL-A47-06-01.3 | Architecture | 2025-12-01 | 2025-12-01 | 2025-12-29 | 2025-09-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-09-01
WMHL-A54-01.15 | Architecture | 2025-05-12 | 2025-06-02 | 2025-06-09 | 2025-09-08 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-09-01
WMHL-A54-01.16 | Architecture | 2025-05-12 | 2025-06-02 | 2025-06-09 | 2025-09-08 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-09-01
WMHL-A25-09.1 | Architecture | 2025-11-24 | 2025-10-20 | 2025-12-22 | 2025-07-07 | 2025-11-01 | 2025-10-01 | 2025-12-01 | 2025-07-01
WMHL-A60-08 | Architecture | 2025-12-08 | 2026-03-02 | 2026-01-05 | 2026-04-20 | 2025-12-01 | 2026-03-01 | 2026-01-01 | 2026-04-01
WMHL-A26-18 | Architecture | 2025-12-01 | 2025-12-01 | 2025-12-29 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A25-09.2 | Architecture | 2025-11-24 | 2025-10-20 | 2025-12-22 | 2025-07-07 | 2025-11-01 | 2025-10-01 | 2025-12-01 | 2025-07-01
WMHL-A41-14 | Architecture | 2025-12-01 | 2025-12-01 | 2025-11-10 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2025-11-01 | 2025-12-01
WMHL-A41-13 | Architecture | 2025-12-01 | 2025-12-01 | 2025-12-29 | 2026-01-05 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-01-01
WMHL-A20-07-01 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A44-09 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A47-07-01.1 | Architecture | 2025-12-08 | 2025-12-08 | 2026-01-05 | 2026-01-05 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-01-01
WMHL-A54-01.17 | Architecture | 2025-12-08 | 2025-06-02 | 2026-01-05 | 2025-09-08 | 2025-12-01 | 2025-06-01 | 2026-01-01 | 2025-09-01
WMHL-A54-01.18 | Architecture | 2025-12-08 | 2025-06-02 | 2026-01-05 | 2025-09-08 | 2025-12-01 | 2025-06-01 | 2026-01-01 | 2025-09-01
WMHL-A46-04 | Architecture | 2025-12-08 | 2025-12-08 | 2026-01-05 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A41-06 | Architecture | 2025-07-28 | 2025-07-28 | 2025-08-25 | 2025-08-11 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01
WMHL-A25-10 | Architecture | 2025-12-08 | 2025-12-08 | 2026-01-05 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A60-09 | Architecture | 2025-12-08 | 2026-03-02 | 2026-01-05 | 2026-04-20 | 2025-12-01 | 2026-03-01 | 2026-01-01 | 2026-04-01
WMHL-A41-08 | Architecture | 2025-12-08 | 2025-08-25 | 2026-01-05 | 2025-12-08 | 2025-12-01 | 2025-08-01 | 2026-01-01 | 2025-12-01
WMHL-A26-17 | Architecture | 2025-12-08 | 2025-12-08 | 2026-01-05 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A41-17 | Architecture | 2025-12-08 | 2025-12-08 | 2026-01-05 | 2026-01-05 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-01-01
WMHL-A20-08-01 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A44-10 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A54-01.19 | Architecture | 2025-05-19 | 2025-06-09 | 2025-06-16 | 2025-12-08 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-12-01
WMHL-A54-01.20 | Architecture | 2025-05-19 | 2025-06-09 | 2025-06-16 | 2025-12-08 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2025-12-01
WMHL-A54-03 | Architecture | 2025-06-09 | 2025-07-21 | 2025-07-07 | 2025-08-11 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-08-01
WMHL-A25-11 | Architecture | 2025-12-15 | 2025-12-08 | 2026-01-12 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A60-10 | Architecture | 2025-12-15 | 2026-03-09 | 2025-11-10 | 2026-04-20 | 2025-12-01 | 2026-03-01 | 2025-11-01 | 2026-04-01
WMHL-A41-19 | Architecture | 2025-12-15 | 2025-12-08 | 2025-11-10 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2025-11-01 | 2025-12-01
WMHL-A41-20 | Architecture | 2025-12-15 | 2025-12-08 | 2025-11-10 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2025-11-01 | 2025-12-01
WMHL-A41-21 | Architecture | 2025-12-15 | 2026-01-05 | 2025-11-10 | 2025-12-15 | 2025-12-01 | 2026-01-01 | 2025-11-01 | 2025-12-01
WMHL-A41-23 | Architecture | 2025-12-15 | 2025-12-15 | 2026-01-12 | 2026-04-20 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-04-01
WMHL-A47-10.1 | Architecture | 2025-12-15 | 2025-12-08 | 2026-01-12 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A20-RF-02 | Architecture | 2025-12-15 | 2025-12-15 | 2026-01-12 | 2026-04-20 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-04-01
WMHL-A20-09-01 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A44-11 | Architecture | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A47-09-01.1 | Architecture | 2025-12-15 | 2025-12-15 | 2026-01-12 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A47-09-01.2 | Structural | 2025-12-15 | 2025-12-08 | 2026-01-12 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A54-01.21 | Structural | 2025-05-26 | 2025-06-30 | 2025-06-23 | 2025-12-08 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-12-01
WMHL-A54-01.22 | Structural | 2025-05-26 | 2025-06-30 | 2025-06-23 | 2025-12-08 | 2025-05-01 | 2025-07-01 | 2025-06-01 | 2025-12-01
WMHL-A60-11 | Structural | 2025-12-22 | 2026-03-30 | 2025-11-10 | 2026-04-20 | 2025-12-01 | 2026-04-01 | 2025-11-01 | 2026-04-01
WMHL-A25-12 | Structural | 2025-12-15 | 2025-12-08 | 2026-01-12 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A20-10-01 | Structural | 2025-12-15 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-12-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A44-12 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-31 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A46-05 | Structural | 2025-12-29 | 2025-12-08 | 2026-01-19 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A47-12.1 | Structural | 2025-12-29 | 2025-12-08 | 2026-01-19 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A47-12.2 | Structural | 2025-12-29 | 2025-12-08 | 2026-01-19 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A54-01.23 | Structural | 2025-06-16 | 2025-06-30 | 2025-07-14 | 2025-12-08 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-12-01
WMHL-A54-01.24 | Structural | 2025-06-16 | 2025-06-30 | 2025-07-14 | 2025-12-08 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-12-01
WMHL-A60-12 | Structural | 2025-12-29 | 2026-03-09 | 2026-01-19 | 2026-04-20 | 2025-12-01 | 2026-03-01 | 2026-01-01 | 2026-04-01
WMHL-A25-13 | Structural | 2025-12-29 | 2025-12-01 | 2026-01-19 | 2025-12-08 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A47-12.3 | Structural | 2025-12-29 | 2025-12-08 | 2026-01-19 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A47-12.4 | Structural | 2025-12-29 | 2025-12-08 | 2026-01-19 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A10-07 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A42-01.1 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A42-01.2 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A42-02.1 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A42-02.2 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A42-03 | Structural | 2025-03-03 | 2025-03-03 | 2025-04-07 | 2025-04-21 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-04-01
WMHL-A43-01 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-04-21 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-04-01
WMHL-A43-03 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-04-21 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-04-01
WMHL-A54-04 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A43-02 | Structural | 2025-03-24 | 2025-03-24 | 2025-04-21 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-03-01
WMHL-A54-01.1 | Structural | 2025-03-31 | 2025-03-31 | 2025-04-28 | 2025-12-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-12-01
WMHL-A54-01.2 | Structural | 2025-03-31 | 2025-03-31 | 2025-04-28 | 2025-12-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-12-01
WMHL-A54-01.3 | Structural | 2025-03-31 | 2025-04-07 | 2025-04-28 | 2025-12-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-12-01
WMHL-A47-11-01.1 | Structural | 2025-03-31 | 2025-04-28 | 2025-04-28 | 2026-04-20 | 2025-04-01 | 2025-05-01 | 2025-05-01 | 2026-04-01
WMHL-A54-02.1 | Structural | 2025-04-07 | 2025-04-14 | 2025-05-05 | 2025-12-08 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-12-01
WMHL-A10-06 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-05-12 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-05-01
WMHL-A10-08 | Structural | 2025-11-24 |  | 2025-12-15 |  | 2025-11-01 |  | 2025-12-01
WMHL-A10-09 | Structural | 2025-11-24 | 2026-01-19 | 2025-12-22 | 2026-05-11 | 2025-11-01 | 2026-01-01 | 2025-12-01 | 2026-05-01
WMHL-A10-10 | Structural | 2025-11-24 | 2026-01-19 | 2025-12-22 | 2026-05-11 | 2025-11-01 | 2026-01-01 | 2025-12-01 | 2026-05-01
WMHL-A10-04 | Structural | 2025-12-29 | 2026-01-12 | 2026-01-26 | 2026-05-11 | 2025-12-01 | 2026-01-01 | 2026-01-01 | 2026-05-01
WMHL-A10-05 | Structural | 2025-12-29 | 2026-02-09 | 2026-01-26 | 2026-05-11 | 2025-12-01 | 2026-02-01 | 2026-01-01 | 2026-05-01
WMHL-A10-12 | Structural | 2025-12-29 | 2026-02-09 | 2026-01-26 | 2026-05-11 | 2025-12-01 | 2026-02-01 | 2026-01-01 | 2026-05-01
WMHL-A10-13 | Structural | 2025-12-08 | 2026-01-19 | 2025-12-29 | 2026-05-11 | 2025-12-01 | 2026-01-01 | 2026-01-01 | 2026-05-01
WMHL-A10-14 | Structural | 2025-12-08 | 2026-01-19 | 2026-01-05 | 2026-05-11 | 2025-12-01 | 2026-01-01 | 2026-01-01 | 2026-05-01
WMHL-A20-RF-01 | Structural | 2025-12-29 | 2025-10-06 | 2025-10-13 | 2026-04-20 | 2025-12-01 | 2025-10-01 | 2025-10-01 | 2026-04-01
WMHL-A44-13 | Structural | 2025-10-06 | 2025-10-06 | 2025-10-13 | 2026-04-20 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2026-04-01
WMHL-A60-13 | Structural | 2025-12-29 | 2026-04-06 | 2026-01-26 | 2026-05-11 | 2025-12-01 | 2026-04-01 | 2026-01-01 | 2026-05-01
WMHL-A25-14 | Structural | 2025-12-29 | 2025-12-29 | 2026-01-26 | 2026-01-05 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-01-01
WMHL-A47-11-01.2 | Structural | 2025-06-23 | 2025-06-23 | 2025-07-21 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-07-01 | 2025-07-01
WMHL-A54-01.25 | Structural | 2025-06-23 | 2025-06-30 | 2025-07-21 | 2025-09-08 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-09-01
WMHL-A54-01.26 | Structural | 2025-06-23 | 2025-06-30 | 2025-07-21 | 2025-09-08 | 2025-06-01 | 2025-07-01 | 2025-07-01 | 2025-09-01
WMHL-A10-02 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMHL-A10-03 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-03-24 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-03-01
WMLH-A30-00-01 | Structural | 2025-03-24 | 2025-03-24 | 2025-04-21 | 2025-09-08 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-09-01
WMLH-A30-00-02 | Structural | 2025-03-24 | 2025-03-24 | 2025-04-21 | 2025-09-08 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-09-01
WMLH-A30-00-03 | Structural | 2025-03-24 | 2025-03-24 | 2025-04-21 | 2025-09-08 | 2025-03-01 | 2025-03-01 | 2025-04-01 | 2025-09-01
WMHL-A35-01 | Structural | 2025-12-29 | 2025-12-15 | 2026-01-26 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMLH-A35-02 | Structural | 2025-12-29 | 2025-12-15 | 2026-01-26 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMLH-A35-03 | Structural | 2025-12-29 | 2025-12-15 | 2026-01-26 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMLH-A35-04 | Structural | 2025-12-29 | 2025-12-15 | 2026-01-26 | 2025-12-15 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2025-12-01
WMHL-A10-01 | Structural | 2025-03-03 | 2025-03-03 | 2025-03-24 | 2025-12-01 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2025-12-01
WMHL-EX-A25-01 | Structural | 2026-02-23 | 2025-03-24 | 2026-03-23 | 2026-04-20 | 2026-02-01 | 2025-03-01 | 2026-03-01 | 2026-04-01
WMHL-EX-A60-01 | Structural | 2026-02-23 |  | 2026-03-23 |  | 2026-02-01 |  | 2026-03-01
WMHL-EX-A20-00-01 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-02-16 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-02-01
WMHL-EX-A44-01 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-02-16 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-02-01
WMHL-EX-A25-02 | Structural | 2026-02-23 | 2025-03-24 | 2026-03-23 | 2026-04-20 | 2026-02-01 | 2025-03-01 | 2026-03-01 | 2026-04-01
WMHL-EX-A60-02 | Structural | 2026-02-23 |  | 2026-03-23 |  | 2026-02-01 |  | 2026-03-01
WMHL-EX-A20-01-01 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-02-16 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-02-01
WMHL-EX-A44-02 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-02-16 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-02-01
WMHL-EX-A25-03 | Structural | 2026-02-23 | 2025-03-24 | 2026-03-23 | 2026-04-20 | 2026-02-01 | 2025-03-01 | 2026-03-01 | 2026-04-01
WMHL-EX-A60-03 | Structural | 2026-02-23 |  | 2026-03-23 |  | 2026-02-01 |  | 2026-03-01
WMHL-EX-A20-02-01 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-02-16 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-02-01
WMHL-EX-A44-03 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-02-16 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-02-01
WMHL-EX-A25-04 | Structural | 2026-02-23 | 2026-03-23 | 2026-03-23 | 2026-04-20 | 2026-02-01 | 2026-03-01 | 2026-03-01 | 2026-04-01
WMHL-EX-A60-04 | Structural | 2026-02-23 |  | 2026-03-23 |  | 2026-02-01 |  | 2026-03-01
WMHL-EX-A20-03-01 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-02-16 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-02-01
WMHL-EX-A44-04 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-02-16 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-02-01
WMHL-EX-A25-05 | Structural | 2026-02-23 | 2025-03-24 | 2026-03-23 | 2026-04-20 | 2026-02-01 | 2025-03-01 | 2026-03-01 | 2026-04-01
WMHL-EX-A60-05 | Structural | 2026-02-23 |  | 2026-03-23 |  | 2026-02-01 |  | 2026-03-01
WMHL-EX-A20-04-01 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-02-16 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-02-01
WMHL-EX-A44-05 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-02-16 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-02-01
WMHL-EX-A25-06 | Structural | 2026-02-23 | 2026-04-20 | 2026-03-23 | 2026-04-20 | 2026-02-01 | 2026-04-01 | 2026-03-01 | 2026-04-01
WMHL-EX-A60-06 | Structural | 2026-02-23 |  | 2026-03-23 |  | 2026-02-01 |  | 2026-03-01
WMHL-EX-A20-05-01 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-04-20 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-04-01
WMHL-EX-A44-06 | Structural | 2026-02-02 | 2026-02-02 | 2026-03-02 | 2026-04-20 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-04-01

## S_Curve_Data
| Column Labels |  |  | Structural | 183 |  |  |  | Architecture | 123 |  |  |  | MEP | 236 |  |  |  | Structural | 183 |  |  |  | Architecture | 123 |  |  |  | MEP | 236
| Architecture | MEP | Structural | Rpt_Week | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Rpt_Week | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Rpt_Week | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Rpt_Month | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Rpt_Month | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Rpt_Month | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals
Total DRG ID | 123 | 236 | 183 | 2025-01-06 | 0% | 0% | 0% | 0% | 2025-01-06 | 0% | 0% | 0% | 0% | 2025-01-06 | 0% | 0% | 0% | 0% | 2025-01-01 | 0% | 0% | 0% | 0% | 2025-01-01 | 0% | 0% | 0% | 0% | 2025-01-01 | 0% | 0% | 0% | 0%
|  |  |  | 2025-01-13 | 0% | 0% | 0% | 0% | 2025-01-13 | 0% | 0% | 0% | 0% | 2025-01-13 | 0% | 0% | 0% | 0% | 2025-02-01 | 0% | 0% | 0% | 0% | 2025-02-01 | 0% | 0% | 0% | 0% | 2025-02-01 | 0% | 0% | 0% | 0%
|  |  |  | 2025-01-20 | 0% | 0% | 0% | 0% | 2025-01-20 | 0% | 0% | 0% | 0% | 2025-01-20 | 0% | 0% | 0% | 0% | 2025-03-01 | 20.22% | 14.75% | 8.197% | 8.197% | 2025-03-01 | 13.82% | 14.63% | 13.82% | 13.82% | 2025-03-01 | 30.08% | 9.322% | 0% | 0.4237%
|  |  |  | 2025-01-27 | 0% | 0% | 0% | 0% | 2025-01-27 | 0% | 0% | 0% | 0% | 2025-01-27 | 0% | 0% | 0% | 0% | 2025-04-01 | 2.732% | 10.93% | 13.11% | 1.639% | 2025-04-01 | 11.38% | 11.38% | 0% | 0% | 2025-04-01 | 1.271% | 14.83% | 19.92% | 4.237%
|  |  |  | 2025-02-03 | 0% | 0% | 0% | 0% | 2025-02-03 | 0% | 0% | 0% | 0% | 2025-02-03 | 0% | 0% | 0% | 0% | 2025-05-01 | 8.743% | 1.639% | 2.732% | 5.464% | 2025-05-01 | 16.26% | 6.504% | 11.38% | 1.626% | 2025-05-01 | 11.86% | 5.932% | 6.78% | 8.051%
|  |  |  | 2025-02-10 | 0% | 0% | 0% | 0% | 2025-02-10 | 0% | 0% | 0% | 0% | 2025-02-10 | 0% | 0% | 0% | 0% | 2025-06-01 | 14.21% | 7.104% | 8.743% | 7.65% | 2025-06-01 | 2.439% | 9.756% | 16.26% | 0% | 2025-06-01 | 19.92% | 5.508% | 15.25% | 11.86%
|  |  |  | 2025-02-17 | 0% | 0% | 0% | 0% | 2025-02-17 | 0% | 0% | 0% | 0% | 2025-02-17 | 0% | 0% | 0% | 0% | 2025-07-01 | 11.48% | 10.93% | 14.75% | 4.372% | 2025-07-01 | 0% | 3.252% | 2.439% | 6.504% | 2025-07-01 | 11.02% | 12.71% | 17.37% | 5.932%
|  |  |  | 2025-02-24 | 0% | 0% | 0% | 0% | 2025-02-24 | 0% | 0% | 0% | 0% | 2025-02-24 | 0% | 0% | 0% | 0% | 2025-08-01 | 0% | 10.93% | 13.11% | 3.279% | 2025-08-01 | 0.813% | 1.626% | 0.813% | 1.626% | 2025-08-01 | 0% | 13.14% | 21.61% | 1.271%
|  |  |  | 2025-03-03 | 7.65% | 8.197% | 0% | 0% | 2025-03-03 | 13.82% | 13.82% | 0% | 0% | 2025-03-03 | 0% | 0% | 0% | 0% | 2025-09-01 | 0% | 3.825% | 0% | 6.011% | 2025-09-01 | 0% | 0% | 0% | 17.89% | 2025-09-01 | 0% | 5.508% | 0% | 0%
|  |  |  | 2025-03-10 | 1.639% | 2.186% | 0% | 2.186% | 2025-03-10 | 0% | 0.813% | 0% | 0% | 2025-03-10 | 12.29% | 6.356% | 0% | 0% | 2025-10-01 | 8.197% | 4.918% | 1.093% | 15.85% | 2025-10-01 | 4.878% | 6.504% | 0% | 4.065% | 2025-10-01 | 11.86% | 6.78% | 0% | 29.66%
|  |  |  | 2025-03-17 | 0% | 0% | 0% | 0% | 2025-03-17 | 0% | 0% | 0% | 0% | 2025-03-17 | 0% | 0% | 0% | 0% | 2025-11-01 | 8.743% | 10.38% | 12.02% | 0% | 2025-11-01 | 15.45% | 18.7% | 10.57% | 4.065% | 2025-11-01 | 11.86% | 23.31% | 17.37% | 0%
|  |  |  | 2025-03-24 | 2.186% | 4.372% | 7.104% | 6.011% | 2025-03-24 | 0% | 0% | 2.439% | 13.82% | 2025-03-24 | 0% | 0% | 0% | 0% | 2025-12-01 | 12.57% | 7.104% | 2.186% | 22.95% | 2025-12-01 | 34.96% | 20.33% | 20.33% | 36.59% | 2025-12-01 | 2.119% | 0% | 0.8475% | 17.37%
|  |  |  | 2025-03-31 | 10.93% | 6.011% | 1.093% | 0% | 2025-03-31 | 4.065% | 3.252% | 11.38% | 0% | 2025-03-31 | 17.8% | 8.475% | 0.4237% | 0.4237% | 2026-01-01 | 0% | 3.279% | 10.93% | 0.5464% | 2026-01-01 | 0% | 1.626% | 24.39% | 3.252% | 2026-01-01 | 0% | 0% | 0.8475% | 0%
|  |  |  | 2025-04-07 | 0.5464% | 4.372% | 2.186% | 0% | 2025-04-07 | 5.691% | 4.878% | 0% | 0% | 2025-04-07 | 0% | 6.356% | 3.814% | 3.39% | 2026-02-01 | 13.11% | 7.65% | 0% | 8.197% | 2026-02-01 | 0% | 0% | 0% | 0% | 2026-02-01 | 0% | 0.8475% | 0% | 12.71%
|  |  |  | 2025-04-14 | 0% | 0.5464% | 8.743% | 0% | 2025-04-14 | 1.626% | 3.252% | 0% | 0% | 2025-04-14 | 0.8475% | 2.966% | 11.44% | 0.8475% | 2026-03-01 | 0% | 1.093% | 13.11% | 0% | 2026-03-01 | 0% | 4.878% | 0% | 0% | 2026-03-01 | 0% | 1.695% | 0% | 1.271%
|  |  |  | 2025-04-21 | 0% | 0% | 2.186% | 1.639% | 2025-04-21 | 0% | 0% | 0% | 0% | 2025-04-21 | 0% | 0% | 4.237% | 0% | 2026-04-01 | 0% | 1.639% | 0% | 7.104% | 2026-04-01 | 0% | 0.813% | 0% | 8.943% | 2026-04-01 | 0% | 0.4237% | 0% | 1.695%
|  |  |  | 2025-04-28 | 0% | 0.5464% | 2.186% | 0% | 2025-04-28 | 0% | 0% | 4.065% | 1.626% | 2025-04-28 | 0.4237% | 0% | 0% | 0% | 2026-05-01 | 0% | 0% | 0% | 4.372% | 2026-05-01 | 0% | 0% | 0% | 1.626% | 2026-05-01 | 0% | 0% | 0% | 0%
|  |  |  | 2025-05-05 | 0% | 0% | 0.5464% | 0% | 2025-05-05 | 4.878% | 0% | 5.691% | 0% | 2025-05-05 | 0% | 0% | 0.4237% | 0% | 2026-06-01 | 0% | 0% | 0% | 0% | 2026-06-01 | 0% | 0% | 0% | 0% | 2026-06-01 | 0% | 0% | 0% | 0%
|  |  |  | 2025-05-12 | 3.825% | 0% | 0% | 0.5464% | 2025-05-12 | 3.252% | 3.252% | 1.626% | 0% | 2025-05-12 | 6.356% | 0% | 0.4237% | 0% | 2026-07-01 | 0% | 0% | 0% | 0% | 2026-07-01 | 0% | 0% | 0% | 0% | 2026-07-01 | 0% | 0% | 0% | 0%
|  |  |  | 2025-05-19 | 0% | 1.093% | 0% | 0% | 2025-05-19 | 4.878% | 3.252% | 0% | 0% | 2025-05-19 | 0% | 5.932% | 0% | 0% | 2026-08-01 | 0% | 0% | 0% | 0% | 2026-08-01 | 0% | 0% | 0% | 0% | 2026-08-01 | 0% | 0% | 0% | 0%
|  |  |  | 2025-05-26 | 4.918% | 0% | 3.825% | 4.918% | 2025-05-26 | 3.252% | 0% | 0% | 0% | 2025-05-26 | 5.508% | 0% | 11.02% | 8.051%
|  |  |  | 2025-06-02 | 0% | 0% | 0% | 7.65% | 2025-06-02 | 0.813% | 3.252% | 4.878% | 0% | 2025-06-02 | 0% | 0% | 3.39% | 11.86%
|  |  |  | 2025-06-09 | 3.825% | 2.732% | 3.825% | 0% | 2025-06-09 | 0.813% | 1.626% | 3.252% | 0% | 2025-06-09 | 6.78% | 0% | 4.661% | 0%
|  |  |  | 2025-06-16 | 1.093% | 3.825% | 0% | 0% | 2025-06-16 | 0% | 0.813% | 4.878% | 0% | 2025-06-16 | 1.271% | 5.508% | 0.8475% | 0%
|  |  |  | 2025-06-23 | 9.29% | 0.5464% | 1.093% | 0% | 2025-06-23 | 0.813% | 4.065% | 3.252% | 0% | 2025-06-23 | 11.86% | 0% | 1.271% | 0%
|  |  |  | 2025-06-30 | 0% | 7.104% | 3.825% | 0.5464% | 2025-06-30 | 0% | 0% | 0.813% | 2.439% | 2025-06-30 | 0% | 5.932% | 5.508% | 0%
|  |  |  | 2025-07-07 | 7.65% | 3.825% | 0% | 3.825% | 2025-07-07 | 0% | 2.439% | 0.813% | 1.626% | 2025-07-07 | 8.475% | 5.932% | 0.4237% | 5.932%
|  |  |  | 2025-07-14 | 0% | 0% | 8.743% | 0% | 2025-07-14 | 0% | 0% | 0% | 2.439% | 2025-07-14 | 1.271% | 0% | 11.44% | 0%
|  |  |  | 2025-07-21 | 3.825% | 0% | 1.639% | 0% | 2025-07-21 | 0% | 0.813% | 0.813% | 0% | 2025-07-21 | 1.271% | 0.8475% | 0% | 0%
|  |  |  | 2025-07-28 | 0% | 0% | 7.65% | 0% | 2025-07-28 | 0.813% | 0.813% | 0% | 0% | 2025-07-28 | 0% | 0% | 11.02% | 0%
|  |  |  | 2025-08-04 | 0% | 0% | 0% | 0% | 2025-08-04 | 0% | 0% | 0% | 0% | 2025-08-04 | 0% | 0% | 0% | 0%
|  |  |  | 2025-08-11 | 0% | 0% | 3.279% | 0% | 2025-08-11 | 0% | 0% | 0% | 1.626% | 2025-08-11 | 0% | 0% | 10.59% | 0%
|  |  |  | 2025-08-18 | 0% | 0% | 2.732% | 0% | 2025-08-18 | 0% | 0% | 0% | 0% | 2025-08-18 | 0% | 0% | 0% | 0%
|  |  |  | 2025-08-25 | 0% | 10.93% | 0% | 3.279% | 2025-08-25 | 0% | 0.813% | 0.813% | 0% | 2025-08-25 | 0% | 13.14% | 0% | 1.271%
|  |  |  | 2025-09-01 | 0% | 0% | 0% | 0% | 2025-09-01 | 0% | 0% | 0% | 0% | 2025-09-01 | 0% | 0% | 0% | 0%
|  |  |  | 2025-09-08 | 0% | 3.825% | 0% | 6.011% | 2025-09-08 | 0% | 0% | 0% | 17.89% | 2025-09-08 | 0% | 5.508% | 0% | 0%
|  |  |  | 2025-09-15 | 0% | 0% | 0% | 0% | 2025-09-15 | 0% | 0% | 0% | 0% | 2025-09-15 | 0% | 0% | 0% | 0%
|  |  |  | 2025-09-22 | 0% | 0% | 0% | 0% | 2025-09-22 | 0% | 0% | 0% | 0% | 2025-09-22 | 0% | 0% | 0% | 0%
|  |  |  | 2025-09-29 | 0% | 0% | 0% | 0% | 2025-09-29 | 0% | 0% | 0% | 0.813% | 2025-09-29 | 0% | 0% | 0% | 0%
|  |  |  | 2025-10-06 | 0.5464% | 1.093% | 0% | 0% | 2025-10-06 | 0% | 0% | 0% | 0% | 2025-10-06 | 0% | 0.8475% | 0% | 0%
|  |  |  | 2025-10-13 | 0% | 0% | 1.093% | 12.02% | 2025-10-13 | 1.626% | 1.626% | 0% | 0% | 2025-10-13 | 0% | 0% | 0% | 23.73%
|  |  |  | 2025-10-20 | 3.825% | 0% | 0% | 0% | 2025-10-20 | 1.626% | 4.878% | 0% | 1.626% | 2025-10-20 | 5.932% | 0% | 0% | 0%
|  |  |  | 2025-10-27 | 3.825% | 3.825% | 0% | 3.825% | 2025-10-27 | 1.626% | 0% | 0% | 1.626% | 2025-10-27 | 5.932% | 5.932% | 0% | 5.932%
|  |  |  | 2025-11-03 | 0% | 3.825% | 3.825% | 0% | 2025-11-03 | 0.813% | 2.439% | 0% | 0% | 2025-11-03 | 0% | 9.746% | 5.932% | 0%
|  |  |  | 2025-11-10 | 6.557% | 5.464% | 4.372% | 0% | 2025-11-10 | 6.504% | 4.878% | 10.57% | 4.065% | 2025-11-10 | 11.44% | 12.29% | 5.932% | 0%
|  |  |  | 2025-11-17 | 0% | 0.5464% | 0% | 0% | 2025-11-17 | 0% | 3.252% | 0% | 0% | 2025-11-17 | 0% | 0.4237% | 0% | 0%
|  |  |  | 2025-11-24 | 2.186% | 0.5464% | 3.825% | 0% | 2025-11-24 | 8.13% | 8.13% | 0% | 0% | 2025-11-24 | 0.4237% | 0.8475% | 5.508% | 0%
|  |  |  | 2025-12-01 | 0% | 0.5464% | 0% | 12.02% | 2025-12-01 | 9.756% | 8.13% | 0% | 8.943% | 2025-12-01 | 0% | 0% | 0% | 17.37%
|  |  |  | 2025-12-08 | 1.093% | 3.825% | 0% | 4.918% | 2025-12-08 | 9.756% | 8.13% | 6.504% | 19.51% | 2025-12-08 | 0% | 0% | 0.4237% | 0%
|  |  |  | 2025-12-15 | 1.639% | 2.186% | 0.5464% | 6.011% | 2025-12-15 | 8.943% | 4.065% | 0% | 8.13% | 2025-12-15 | 0.8475% | 0% | 0% | 0%
|  |  |  | 2025-12-22 | 0.5464% | 0% | 1.639% | 0% | 2025-12-22 | 4.878% | 0% | 9.756% | 0% | 2025-12-22 | 0% | 0% | 0.4237% | 0%
|  |  |  | 2025-12-29 | 9.29% | 0.5464% | 0.5464% | 0% | 2025-12-29 | 1.626% | 0% | 8.943% | 0% | 2025-12-29 | 1.271% | 0% | 0% | 0%
|  |  |  | 2026-01-05 | 0% | 0% | 0.5464% | 0.5464% | 2026-01-05 | 0% | 0.813% | 8.943% | 3.252% | 2026-01-05 | 0% | 0% | 0.4237% | 0%
|  |  |  | 2026-01-12 | 0% | 1.093% | 1.093% | 0% | 2026-01-12 | 0% | 0% | 4.065% | 0% | 2026-01-12 | 0% | 0% | 0% | 0%
|  |  |  | 2026-01-19 | 0% | 2.186% | 3.825% | 0% | 2026-01-19 | 0% | 0.813% | 4.878% | 0% | 2026-01-19 | 0% | 0% | 0% | 0%
|  |  |  | 2026-01-26 | 0% | 0% | 4.918% | 0% | 2026-01-26 | 0% | 0% | 1.626% | 0% | 2026-01-26 | 0% | 0% | 0.4237% | 0%
|  |  |  | 2026-02-02 | 6.557% | 6.557% | 0% | 0% | 2026-02-02 | 0% | 0% | 0% | 0% | 2026-02-02 | 0% | 0.8475% | 0% | 0.4237%
|  |  |  | 2026-02-09 | 0% | 1.093% | 0% | 0% | 2026-02-09 | 0% | 0% | 0% | 0% | 2026-02-09 | 0% | 0% | 0% | 0%
|  |  |  | 2026-02-16 | 0% | 0% | 0% | 8.197% | 2026-02-16 | 0% | 0% | 0% | 0% | 2026-02-16 | 0% | 0% | 0% | 10.17%
|  |  |  | 2026-02-23 | 6.557% | 0% | 0% | 0% | 2026-02-23 | 0% | 0% | 0% | 0% | 2026-02-23 | 0% | 0% | 0% | 2.119%
|  |  |  | 2026-03-02 | 0% | 0% | 6.557% | 0% | 2026-03-02 | 0% | 2.439% | 0% | 0% | 2026-03-02 | 0% | 0.8475% | 0% | 1.271%
|  |  |  | 2026-03-09 | 0% | 0.5464% | 0% | 0% | 2026-03-09 | 0% | 2.439% | 0% | 0% | 2026-03-09 | 0% | 0% | 0% | 0%
|  |  |  | 2026-03-16 | 0% | 0% | 0% | 0% | 2026-03-16 | 0% | 0% | 0% | 0% | 2026-03-16 | 0% | 0% | 0% | 0%
|  |  |  | 2026-03-23 | 0% | 0.5464% | 6.557% | 0% | 2026-03-23 | 0% | 0% | 0% | 0% | 2026-03-23 | 0% | 0.8475% | 0% | 0%
|  |  |  | 2026-03-30 | 0% | 0.5464% | 0% | 0% | 2026-03-30 | 0% | 0% | 0% | 0% | 2026-03-30 | 0% | 0% | 0% | 0%
|  |  |  | 2026-04-06 | 0% | 0.5464% | 0% | 0% | 2026-04-06 | 0% | 0.813% | 0% | 0% | 2026-04-06 | 0% | 0% | 0% | 0%
|  |  |  | 2026-04-13 | 0% | 0% | 0% | 0% | 2026-04-13 | 0% | 0% | 0% | 0% | 2026-04-13 | 0% | 0.4237% | 0% | 0%
|  |  |  | 2026-04-20 | 0% | 0.5464% | 0% | 7.104% | 2026-04-20 | 0% | 0% | 0% | 8.943% | 2026-04-20 | 0% | 0% | 0% | 1.695%
|  |  |  | 2026-04-27 | 0% | 0% | 0% | 0% | 2026-04-27 | 0% | 0% | 0% | 0% | 2026-04-27 | 0% | 0% | 0% | 0%
|  |  |  | 2026-05-04 | 0% | 0% | 0% | 0% | 2026-05-04 | 0% | 0% | 0% | 0% | 2026-05-04 | 0% | 0% | 0% | 0%
|  |  |  | 2026-05-11 | 0% | 0% | 0% | 4.372% | 2026-05-11 | 0% | 0% | 0% | 1.626% | 2026-05-11 | 0% | 0% | 0% | 0%
|  |  |  | 2026-05-18 | 0% | 0% | 0% | 0% | 2026-05-18 | 0% | 0% | 0% | 0% | 2026-05-18 | 0% | 0% | 0% | 0%
|  |  |  | 2026-05-25 | 0% | 0% | 0% | 0% | 2026-05-25 | 0% | 0% | 0% | 0% | 2026-05-25 | 0% | 0% | 0% | 0%
|  |  |  | 2026-06-01 | 0% | 0% | 0% | 0% | 2026-06-01 | 0% | 0% | 0% | 0% | 2026-06-01 | 0% | 0% | 0% | 0%
|  |  |  | 2026-06-08 | 0% | 0% | 0% | 0% | 2026-06-08 | 0% | 0% | 0% | 0% | 2026-06-08 | 0% | 0% | 0% | 0%
|  |  |  | 2026-06-15 | 0% | 0% | 0% | 0% | 2026-06-15 | 0% | 0% | 0% | 0% | 2026-06-15 | 0% | 0% | 0% | 0%
|  |  |  | 2026-06-22 | 0% | 0% | 0% | 0% | 2026-06-22 | 0% | 0% | 0% | 0% | 2026-06-22 | 0% | 0% | 0% | 0%
|  |  |  | 2026-06-29 | 0% | 0% | 0% | 0% | 2026-06-29 | 0% | 0% | 0% | 0% | 2026-06-29 | 0% | 0% | 0% | 0%
|  |  |  | 2026-07-06 | 0% | 0% | 0% | 0% | 2026-07-06 | 0% | 0% | 0% | 0% | 2026-07-06 | 0% | 0% | 0% | 0%
|  |  |  | 2026-07-13 | 0% | 0% | 0% | 0% | 2026-07-13 | 0% | 0% | 0% | 0% | 2026-07-13 | 0% | 0% | 0% | 0%
|  |  |  | 2026-07-20 | 0% | 0% | 0% | 0% | 2026-07-20 | 0% | 0% | 0% | 0% | 2026-07-20 | 0% | 0% | 0% | 0%
|  |  |  | 2026-07-27 | 0% | 0% | 0% | 0% | 2026-07-27 | 0% | 0% | 0% | 0% | 2026-07-27 | 0% | 0% | 0% | 0%
|  |  |  | 2026-08-03 | 0% | 0% | 0% | 0% | 2026-08-03 | 0% | 0% | 0% | 0% | 2026-08-03 | 0% | 0% | 0% | 0%
|  |  |  | 2026-08-10 | 0% | 0% | 0% | 0% | 2026-08-10 | 0% | 0% | 0% | 0% | 2026-08-10 | 0% | 0% | 0% | 0%
|  |  |  | 2026-08-17 | 0% | 0% | 0% | 0% | 2026-08-17 | 0% | 0% | 0% | 0% | 2026-08-17 | 0% | 0% | 0% | 0%
|  |  |  | 2026-08-24 | 0% | 0% | 0% | 0% | 2026-08-24 | 0% | 0% | 0% | 0% | 2026-08-24 | 0% | 0% | 0% | 0%
|  |  |  | 2026-08-31 | 0% | 0% | 0% | 0% | 2026-08-31 | 0% | 0% | 0% | 0% | 2026-08-31 | 0% | 0% | 0% | 0%

## Mappings
Date | Rpt_Week | Approval Code | Desc
| 2025-01-06 | 1 | Approved
| 2025-01-13 | 2 | Approved with comments
| 2025-01-20 | 3 | Not Approved
| 2025-01-27 | R | Retained for info
| 2025-02-03 | V | Void
2025-02-10
2025-02-17
2025-02-24
2025-03-03
2025-03-10
2025-03-17
2025-03-24
2025-03-31
2025-04-07
2025-04-14
2025-04-21
2025-04-28
2025-05-05
2025-05-12
2025-05-19
2025-05-26
2025-06-02
2025-06-09
2025-06-16
2025-06-23
2025-06-30
2025-07-07
2025-07-14
2025-07-21
2025-07-28
2025-08-04
2025-08-11
2025-08-18
2025-08-25
2025-09-01
2025-09-08
2025-09-15
2025-09-22
2025-09-29
2025-10-06
2025-10-13
2025-10-20
2025-10-27
2025-11-03
2025-11-10
2025-11-17
2025-11-24
2025-12-01
2025-12-08
2025-12-15
2025-12-22
2025-12-29
2026-01-05
2026-01-12
2026-01-19
2026-01-26
2026-02-02
2026-02-09
2026-02-16
2026-02-23
2026-03-02
2026-03-09
2026-03-16
2026-03-23
2026-03-30
2026-04-06
2026-04-13
2026-04-20
2026-04-27
2026-05-04
2026-05-11
2026-05-18
2026-05-25
2026-06-01
2026-06-08
2026-06-15
2026-06-22
2026-06-29
2026-07-06
2026-07-13
2026-07-20
2026-07-27
2026-08-03
2026-08-10
2026-08-17
2026-08-24
2026-08-31
2026-09-07
2026-09-14
2026-09-21
2026-09-28
2026-10-05
2026-10-12
2026-10-19
2026-10-26
2026-11-02
2026-11-09
2026-11-16
2026-11-23
2026-11-30
2026-12-07
2026-12-14
2026-12-21
2026-12-28
2027-01-04
2027-01-11
2027-01-18
2027-01-25
2027-02-01
2027-02-08
2027-02-15
2027-02-22
2027-03-01
2027-03-08
2027-03-15
2027-03-22
2027-03-29
2027-04-05
2027-04-12
2027-04-19
2027-04-26
2027-05-03
2027-05-10
2027-05-17
2027-05-24
2027-05-31
2027-06-07
2027-06-14
2027-06-21
2027-06-28
2027-07-05
2027-07-12
2027-07-19
2027-07-26
2027-08-02
2027-08-09
2027-08-16
2027-08-23
2027-08-30
2027-09-06
2027-09-13
2027-09-20
2027-09-27
2027-10-04
2027-10-11
2027-10-18
2027-10-25
2027-11-01
2027-11-08
2027-11-15
2027-11-22
2027-11-29
2027-12-06
2027-12-13
2027-12-20
2027-12-27
2028-01-03
2028-01-10
2028-01-17
2028-01-24
2028-01-31
2028-02-07
2028-02-14
2028-02-21
2028-02-28
2028-03-06
2028-03-13
2028-03-20
2028-03-27
2028-04-03
2028-04-10
2028-04-17
2028-04-24
2028-05-01
2028-05-08
2028-05-15
2028-05-22
2028-05-29
2028-06-05
2028-06-12
2028-06-19
2028-06-26
2028-07-03
2028-07-10
2028-07-17
2028-07-24
2028-07-31
2028-08-07
2028-08-14
2028-08-21
2028-08-28
2028-09-04
2028-09-11
2028-09-18
2028-09-25
2028-10-02
2028-10-09
2028-10-16
2028-10-23
2028-10-30
2028-11-06
2028-11-13
2028-11-20
2028-11-27
2028-12-04
2028-12-11
2028-12-18
2028-12-25
2029-01-01
2029-01-08
2029-01-15
2029-01-22
2029-01-29
2029-02-05
2029-02-12
2029-02-19
2029-02-26
2029-03-05
2029-03-12
2029-03-19
2029-03-26
2029-04-02
2029-04-09
2029-04-16
2029-04-23
2029-04-30
2029-05-07
2029-05-14
2029-05-21
2029-05-28
2029-06-04
2029-06-11
2029-06-18
2029-06-25
2029-07-02
2029-07-09
2029-07-16
2029-07-23
2029-07-30
2029-08-06
2029-08-13
2029-08-20
2029-08-27
2029-09-03
2029-09-10
2029-09-17
2029-09-24
2029-10-01
2029-10-08
2029-10-15
2029-10-22
2029-10-29
2029-11-05
2029-11-12
2029-11-19
2029-11-26
2029-12-03
2029-12-10
2029-12-17
2029-12-24
2029-12-31
2030-01-07
2030-01-14
2030-01-21
2030-01-28
2030-02-04
2030-02-11
2030-02-18
2030-02-25
2030-03-04
2030-03-11
2030-03-18
2030-03-25
2030-04-01
2030-04-08
2030-04-15
2030-04-22
2030-04-29
2030-05-06
2030-05-13
2030-05-20
2030-05-27
2030-06-03
2030-06-10
2030-06-17
2030-06-24
2030-07-01
2030-07-08
2030-07-15
2030-07-22
2030-07-29
2030-08-05
2030-08-12
2030-08-19
2030-08-26
2030-09-02
2030-09-09
2030-09-16
2030-09-23
2030-09-30
2030-10-07
2030-10-14
2030-10-21
2030-10-28
2030-11-04
2030-11-11
2030-11-18
2030-11-25
2030-12-02
2030-12-09
2030-12-16
2030-12-23
2030-12-30
2031-01-06
2031-01-13
2031-01-20
2031-01-27
2031-02-03
2031-02-10
2031-02-17
2031-02-24
2031-03-03
2031-03-10
2031-03-17
2031-03-24
2031-03-31
2031-04-07
2031-04-14
2031-04-21
2031-04-28
2031-05-05
2031-05-12
2031-05-19
2031-05-26
2031-06-02
2031-06-09
2031-06-16
2031-06-23
2031-06-30
2031-07-07
2031-07-14
2031-07-21
2031-07-28
2031-08-04
2031-08-11
2031-08-18
2031-08-25
2031-09-01
2031-09-08
2031-09-15
2031-09-22
2031-09-29
2031-10-06
2031-10-13
2031-10-20
2031-10-27
2031-11-03
2031-11-10
2031-11-17
2031-11-24
2031-12-01
2031-12-08
2031-12-15
2031-12-22
2031-12-29
2032-01-05
2032-01-12
2032-01-19
2032-01-26
2032-02-02
2032-02-09
2032-02-16
2032-02-23
2032-03-01
2032-03-08
2032-03-15
2032-03-22
2032-03-29
2032-04-05
2032-04-12
2032-04-19
2032-04-26
2032-05-03
2032-05-10
2032-05-17
2032-05-24
2032-05-31
2032-06-07
2032-06-14
2032-06-21
2032-06-28
2032-07-05
2032-07-12
2032-07-19
2032-07-26
2032-08-02
2032-08-09
2032-08-16
2032-08-23
2032-08-30
2032-09-06
2032-09-13
2032-09-20
2032-09-27
2032-10-04
2032-10-11
2032-10-18
2032-10-25
2032-11-01
2032-11-08
2032-11-15
2032-11-22
2032-11-29
2032-12-06
2032-12-13
2032-12-20
2032-12-27
2033-01-03
2033-01-10
2033-01-17
2033-01-24
2033-01-31
2033-02-07
2033-02-14
2033-02-21
2033-02-28
2033-03-07
2033-03-14
2033-03-21
2033-03-28
2033-04-04
2033-04-11
2033-04-18
2033-04-25
2033-05-02
2033-05-09
2033-05-16
2033-05-23
2033-05-30
2033-06-06
2033-06-13
2033-06-20
2033-06-27
2033-07-04
2033-07-11
2033-07-18
2033-07-25
2033-08-01
2033-08-08
2033-08-15
2033-08-22
2033-08-29
2033-09-05
2033-09-12
2033-09-19
2033-09-26
2033-10-03
2033-10-10
2033-10-17
2033-10-24
2033-10-31
2033-11-07
2033-11-14
2033-11-21
2033-11-28
2033-12-05
2033-12-12
2033-12-19
2033-12-26
2034-01-02
2034-01-09
2034-01-16
2034-01-23
2034-01-30
2034-02-06
2034-02-13
2034-02-20
2034-02-27
2034-03-06
2034-03-13
2034-03-20
2034-03-27
2034-04-03
2034-04-10
2034-04-17
2034-04-24
2034-05-01
2034-05-08
2034-05-15
2034-05-22
2034-05-29
2034-06-05
2034-06-12
2034-06-19
2034-06-26
2034-07-03
2034-07-10
2034-07-17
2034-07-24
2034-07-31
2034-08-07
2034-08-14
2034-08-21
2034-08-28
2034-09-04
2034-09-11
2034-09-18
2034-09-25
2034-10-02
2034-10-09
2034-10-16
2034-10-23
2034-10-30
2034-11-06
2034-11-13
2034-11-20
2034-11-27
2034-12-04
2034-12-11
2034-12-18
2034-12-25
2035-01-01
2035-01-08
2035-01-15
2035-01-22
2035-01-29
2035-02-05
2035-02-12
2035-02-19
2035-02-26
2035-03-05
2035-03-12
2035-03-19
2035-03-26
2035-04-02
2035-04-09
2035-04-16
2035-04-23
2035-04-30
2035-05-07
2035-05-14
2035-05-21
2035-05-28
2035-06-04
2035-06-11
2035-06-18
2035-06-25
2035-07-02
2035-07-09
2035-07-16
2035-07-23
2035-07-30
2035-08-06
2035-08-13
2035-08-20
2035-08-27
2035-09-03
2035-09-10
2035-09-17
2035-09-24
2035-10-01
2035-10-08
2035-10-15
2035-10-22
2035-10-29
2035-11-05
2035-11-12
2035-11-19
2035-11-26
2035-12-03
2035-12-10
2035-12-17
2035-12-24
2035-12-31
2036-01-07
2036-01-14
2036-01-21
2036-01-28
2036-02-04
2036-02-11
2036-02-18
2036-02-25
2036-03-03
2036-03-10
2036-03-17
2036-03-24
2036-03-31
2036-04-07
2036-04-14
2036-04-21
2036-04-28
2036-05-05
2036-05-12
2036-05-19
2036-05-26
2036-06-02
2036-06-09
2036-06-16
2036-06-23
2036-06-30
2036-07-07
2036-07-14
2036-07-21
2036-07-28
2036-08-04
2036-08-11
2036-08-18
2036-08-25
2036-09-01
2036-09-08
2036-09-15
2036-09-22
2036-09-29
2036-10-06
2036-10-13
2036-10-20
2036-10-27
2036-11-03
2036-11-10
2036-11-17
2036-11-24
2036-12-01
2036-12-08
2036-12-15
2036-12-22
2036-12-29
2037-01-05
2037-01-12
2037-01-19
2037-01-26
2037-02-02
2037-02-09
2037-02-16
2037-02-23
2037-03-02
2037-03-09
2037-03-16
2037-03-23
2037-03-30
2037-04-06
2037-04-13
2037-04-20
2037-04-27
2037-05-04
2037-05-11
2037-05-18
2037-05-25
2037-06-01
2037-06-08
2037-06-15
2037-06-22
2037-06-29
2037-07-06
2037-07-13
2037-07-20
2037-07-27
2037-08-03
2037-08-10
2037-08-17
2037-08-24
2037-08-31
2037-09-07
2037-09-14
2037-09-21
2037-09-28
2037-10-05
2037-10-12
2037-10-19
2037-10-26
2037-11-02
2037-11-09
2037-11-16
2037-11-23
2037-11-30
2037-12-07
2037-12-14
2037-12-21
2037-12-28
2038-01-04
2038-01-11
2038-01-18
2038-01-25
2038-02-01
2038-02-08
2038-02-15
2038-02-22
2038-03-01
2038-03-08
2038-03-15
2038-03-22
2038-03-29
2038-04-05
2038-04-12
2038-04-19
2038-04-26
2038-05-03
2038-05-10
2038-05-17
2038-05-24
2038-05-31
2038-06-07
2038-06-14
2038-06-21
2038-06-28
2038-07-05
2038-07-12
2038-07-19
2038-07-26
2038-08-02
2038-08-09
2038-08-16
2038-08-23
2038-08-30
2038-09-06
2038-09-13
2038-09-20
2038-09-27
2038-10-04
2038-10-11
2038-10-18
2038-10-25
2038-11-01
2038-11-08
2038-11-15
2038-11-22
2038-11-29
2038-12-06
2038-12-13
2038-12-20
2038-12-27
2039-01-03
2039-01-10
2039-01-17
2039-01-24
2039-01-31
2039-02-07
2039-02-14
2039-02-21
2039-02-28
2039-03-07
2039-03-14
2039-03-21
2039-03-28
2039-04-04
2039-04-11
2039-04-18
2039-04-25
2039-05-02
2039-05-09
2039-05-16
2039-05-23
2039-05-30
2039-06-06
2039-06-13
2039-06-20
2039-06-27
2039-07-04
2039-07-11
2039-07-18
2039-07-25
2039-08-01
2039-08-08
2039-08-15
2039-08-22
2039-08-29
2039-09-05
2039-09-12
2039-09-19
2039-09-26
2039-10-03
2039-10-10
2039-10-17
2039-10-24
2039-10-31
2039-11-07
2039-11-14
2039-11-21
2039-11-28
2039-12-05
2039-12-12
2039-12-19
2039-12-26
2040-01-02
2040-01-09
2040-01-16
2040-01-23
2040-01-30
2040-02-06
2040-02-13
2040-02-20
2040-02-27
2040-03-05
2040-03-12
2040-03-19
2040-03-26
2040-04-02
2040-04-09
2040-04-16
2040-04-23
2040-04-30
2040-05-07
2040-05-14
2040-05-21
2040-05-28
2040-06-04
2040-06-11
2040-06-18
2040-06-25
2040-07-02
2040-07-09
2040-07-16
2040-07-23
2040-07-30
2040-08-06
2040-08-13
2040-08-20
2040-08-27
2040-09-03
2040-09-10
2040-09-17
2040-09-24
2040-10-01
2040-10-08
2040-10-15
2040-10-22
2040-10-29
2040-11-05
2040-11-12
2040-11-19
2040-11-26
2040-12-03
2040-12-10
2040-12-17
2040-12-24
2040-12-31
2041-01-07
2041-01-14
2041-01-21
2041-01-28
2041-02-04
2041-02-11
2041-02-18
2041-02-25
2041-03-04
2041-03-11
2041-03-18
2041-03-25
2041-04-01
2041-04-08
2041-04-15
2041-04-22
2041-04-29
2041-05-06
2041-05-13
2041-05-20
2041-05-27
2041-06-03
2041-06-10
2041-06-17
2041-06-24
2041-07-01
2041-07-08
2041-07-15
2041-07-22
2041-07-29
2041-08-05
2041-08-12
2041-08-19
2041-08-26
2041-09-02
2041-09-09
2041-09-16
2041-09-23
2041-09-30
2041-10-07
2041-10-14
2041-10-21
2041-10-28
2041-11-04
2041-11-11
2041-11-18
2041-11-25
2041-12-02
2041-12-09
2041-12-16
2041-12-23
2041-12-30
2042-01-06
2042-01-13
2042-01-20
2042-01-27
2042-02-03
2042-02-10
2042-02-17
2042-02-24
2042-03-03
2042-03-10
2042-03-17
2042-03-24
2042-03-31
2042-04-07
2042-04-14
2042-04-21
2042-04-28
2042-05-05
2042-05-12
2042-05-19
2042-05-26
2042-06-02
2042-06-09
2042-06-16
2042-06-23
2042-06-30
2042-07-07
2042-07-14
2042-07-21
2042-07-28
2042-08-04
2042-08-11
2042-08-18
2042-08-25
2042-09-01
2042-09-08
2042-09-15
2042-09-22
2042-09-29
2042-10-06
2042-10-13
2042-10-20
2042-10-27
2042-11-03
2042-11-10
2042-11-17
2042-11-24
2042-12-01
2042-12-08
2042-12-15
2042-12-22
2042-12-29
2043-01-05
2043-01-12
2043-01-19
2043-01-26
2043-02-02
2043-02-09
2043-02-16
2043-02-23
2043-03-02
2043-03-09
2043-03-16
2043-03-23
2043-03-30
2043-04-06
2043-04-13
2043-04-20
2043-04-27
2043-05-04
2043-05-11
2043-05-18
2043-05-25
2043-06-01
2043-06-08
2043-06-15
2043-06-22
2043-06-29
2043-07-06
2043-07-13
2043-07-20
2043-07-27
2043-08-03
2043-08-10
2043-08-17
2043-08-24
2043-08-31
2043-09-07
2043-09-14
2043-09-21
2043-09-28
2043-10-05
2043-10-12
2043-10-19
2043-10-26
2043-11-02
2043-11-09
2043-11-16
2043-11-23
2043-11-30
2043-12-07
2043-12-14
2043-12-21
2043-12-28
2044-01-04
2044-01-11
2044-01-18
2044-01-25
2044-02-01
2044-02-08
2044-02-15
2044-02-22
2044-02-29
2044-03-07
2044-03-14
2044-03-21
2044-03-28
2044-04-04
2044-04-11
2044-04-18
2044-04-25
2044-05-02
2044-05-09
2044-05-16
2044-05-23
2044-05-30
2044-06-06
2044-06-13
2044-06-20
2044-06-27
2044-07-04
2044-07-11
2044-07-18
2044-07-25
2044-08-01
2044-08-08
Formulas:
Rpt_Week = [Rpt_Week, row above]+7-WEEKDAY([Rpt_Week, row above],2)+1