## DCI_ ARCH
58.4615
Completion Submittion | Completion Approval | Weightage | S.NO. | REVISION | Document No. | DOCUMENTS | Rev no | PLANNED ISSUE DATE | PLANNED APPROVAL DATE | R0 SUBMISSION | R0 APPROVAL |  | R1 SUBMISSION | R1 APPROVAL |  | Last Submission Date | R2 APPROVAL |  | R3 SUBMISSION | R3 APPROVAL | R4 SUBMISSION | R4 APPROVAL | R5 SUBMISSION | R5 APPROVAL | R6 SUBMISSION | R6 APPROVAL | R7 SUBMISSION | R7 APPROVAL | R8 SUBMISSION | R8 APPROVAL | Comment
TRUE | TRUE | 10 | 1 |  | CV-192-ARC-DBR-0001 | Architectural DBR
|  |  | 2 |  |  | GTC Substation and control room
FALSE | FALSE | 6.9231 | 2.1 |  | CV-192-ARC-GTC-DRW-0001 | GROUND AND FIRST FLOOR PLAN @ E.L. 100.45 & 104.65 (DOOR - WINDOW AND FINISHES SCHEDULE) | R3 | 2026-01-16 | 2026-01-21 | 2026-01-23 | 2026-02-10 | 2 | 2026-03-23 | 2026-03-27 | 2 | 2026-05-27 | 2026-05-06 | 2
FALSE | FALSE | 6.9231 | 2.2 |  | CV-192-ARC-GTC-DRW-0002 | SECOND AND TERRACE FLOOR PLAN @ E.L. 111.55 & 118.30 | R3 | 2026-01-16 | 2026-01-21 | 2026-01-23 | 2026-02-10 | 2 | 2026-03-23 | 2026-03-27 | 2 | 2026-05-27 | 2026-05-06 | 2
FALSE | FALSE | 6.9231 | 2.3 |  | CV-192-ARC-GTC-DRW-0003 | ELEVATION | R2 | 2026-01-21 | 2026-01-26 | 2026-02-03 | 2026-02-13 | 2 | 2026-04-21 | 2026-05-06 | 2 | 2026-05-27
FALSE | FALSE | 6.9231 | 2.4 |  | CV-192-ARC-GTC-DRW-0004 | SECTIONS | R2 | 2026-01-21 | 2026-01-26 | 2026-02-03 | 2026-02-13 | 2 | 2026-04-21 | 2026-05-06 | 2 | 2026-05-27
FALSE | FALSE | 6.9231 | 2.5 |  | CV-192-ARC-GTC-DRW-0005 | ARCHITECTURAL STAIRCASE DETAILS FOR GTC SUBSTATION & CONTROL ROOM BUILDING | R2 | 2026-01-21 | 2026-01-26
|  |  | 3 |  |  | PTA SUBSTATION
TRUE | FALSE | 6.9231 | 3.1 |  | CV-192-ARC-PTA-DRW-0001 | GROUND AND FIRST FLOOR PLAN @ E.L. 100.45 & 104.65 (DOOR - WINDOW AND FINISHES SCHEDULE) | R7 | 2026-01-13 | 2026-01-16 | 2026-01-23 | 2026-02-10 | 2 | 2026-03-04 | 2026-03-05 | V | 2026-06-03 | 2026-03-25 | 2
TRUE | FALSE | 6.9231 | 3.2 |  | CV-192-ARC-PTA-DRW-0002 | ROOF PLAN, ELEVATION & SECTION @ E.L. 110.35 | R8 | 2026-01-15 | 2026-01-20 | 2026-01-23 | 2026-02-10 | 2 | 2026-03-04 | 2026-03-05 | V | 2026-06-03 | 2026-03-25 | 2
TRUE | FALSE | 6.9231 | 3.3 |  | CV-192-ARC-PTA-DRW-0003 | ARCHITECTURAL STAIRCASE DETAILS FOR PTA SUBSTATION | R2 | 2026-01-15 | 2026-01-20 | 2026-05-08 | 2026-05-13 | 2 | 2026-05-19 | 2026-06-01 | 2 | 2026-06-03 |  | 2
|  |  | 4 |  |  | ABF Substation & Control Room
TRUE | FALSE | 6.9231 | 4.1 |  | CV-192-ARC-ABF-DRW-0001 | GROUND AND FIRST FLOOR PLAN @ E.L. 100.45 & 104.65 (DOOR - WINDOW AND FINISHES SCHEDULE) | R3 | 2026-01-21 | 2026-01-26 | 2026-01-23 | 2026-02-10 | 2 | 2026-02-13 | 2026-03-27 | 2 | 2026-06-10 | 2026-05-05 | 2
TRUE | FALSE | 6.9231 | 4.2 |  | CV-192-ARC-ABF-DRW-0002 | SECOND AND TERRACE FLOOR PLAN @ E.L. 110.35 & 116.95 | R3 | 2026-01-27 | 2026-01-30 | 2026-01-27 | 2026-02-10 | 2 | 2026-03-12 | 2026-04-06 | 2 | 2026-06-10 | 2026-05-05 | 2
TRUE | FALSE | 6.9231 | 4.3 |  | CV-192-ARC-ABF-DRW-0003 | ELEVATION | R3 | 2026-01-30 | 2026-02-04 | 2026-02-02 | 2026-02-13 | 2 | 2026-03-12 | 2026-04-06 | 2 | 2026-06-10 | 2026-05-05 | 2
TRUE | FALSE | 6.9231 | 4.4 |  | CV-192-ARC-ABF-DRW-0004 | SECTION | R3 | 2026-01-30 | 2026-02-04 | 2026-02-02 | 2026-02-13 | 2 | 2026-03-12 | 2026-03-27 | 2 | 2026-06-10 | 2026-05-05 | 2
FALSE | FALSE | 6.9231 | 4.5 |  | CV-192-ARC-ABF-DRW-0005 | ARCHITECTURAL STAIRCASE DETAILS FOR ABF SUBSTATION & CONTROL ROOM BUILDING | R3 | 2026-01-30 | 2026-02-04
1 | All Arch drawings have recived CODE 2 approval | 13
2 | GTC Architectural drawings are yet to be submitted incorporating EIL commnets
3 | GIS and 11 kV Control Room building - CODE 2- approved Architectural drawings are received from GE on 15th April 2026.
6.9231
Formulas:
PLANNED APPROVAL DATE = WORKDAY([PLANNED ISSUE DATE],3)
PLANNED ISSUE DATE = WORKDAY([PLANNED ISSUE DATE, row above],3)