## Sheet1
TOTAL
Submitted | S.NO. | Document No. | DESCRIPTION | SCALE | PLANNED DATE OF ISSUE (ORIGINAL) | PLANNED DATE OF APPROVAL (ORIGINAL) | PLANNED DATE OF ISSUE (NEW) | PLANNED DATE OF APPROVAL (NEW) | ACTUAL DATE OF ISSUE | ACTUAL DATE OF APPROVAL | Approval Code | R1 | R1 Approval | Approval Code | R2 | R2 Approval | Approval Code | R3 | R3 Approval | Approval Code | R4 | R4 Approval | Approval Code | R5 | R5 Approval | Approval Code
Client
TRUE | A | CV-192-STR-DBR-0001 | DESIGN BASIS REPORT (CIVIL) | NA | 2025-11-21 | 2025-12-04 | 2025-12-17 | 2025-12-23 | 2026-12-17 | 2025-12-22 | R
Holidays
| 1 | GIS BUILDING | [24 empty] | 2025-12-25
|  |  | INPUT RECEIVED (06.01.2025) - ARCHITECTURAL DRAWING YET TO BE RECEIVED EXPECTED ON 10.01.2026 | [23 empty] | 2026-01-01
FALSE | 1.1 | CV-192-STR-GIS-STD-0001 | STAAD ANALYSIS AND DESIGN |  | 2025-12-04 | 2025-12-08 | 2026-01-16 | 2026-01-21 | [18 empty] | 2026-01-26 | 2026-01-10
FALSE | 1.2 | CV-192-STR-GIS-DRW-0002 | LAYOUT AND R/F DETAILS OF PEDESTAL |  | 2025-12-22 | 2025-12-25 | 2026-01-21 | 2026-01-26
FALSE | 1.3 | CV-192-STR-GIS-DRW-0003 | LAYOUT AND DETAILS OF ANCHOR BOLT |  | 2025-12-22 | 2025-12-25 | 2026-01-21 | 2026-01-26
FALSE | 1.4 | CV-192-STR-GIS-DRW-0004 | LAYOUT AND R/F DETAILS OF PLINTH BEAM |  | 2025-12-22 | 2025-12-25 | 2026-01-21 | 2026-01-26
FALSE | 1.5 | CV-192-STR-GIS-DRW-0005 | R/F DETAILS OF PLINTH BEAM |  | 2025-12-22 | 2025-12-25 | 2026-01-21 | 2026-01-26
FALSE | 1.6 | CV-192-STR-GIS-DRW-0006 | G.A. LAYOUT AND DETAIL OF STEEL COLUMNS |  | 2025-12-19 | 2026-01-14 | 2026-01-27 | 2026-01-30 | [19 empty] | 2025-12-11 | 60
FALSE | 1.7 | CV-192-STR-GIS-DRW-0007 | CONNECTION DETAIL OF STEEL COLUMNS |  | 2025-12-21 |  | 2026-01-29 | 2026-02-03 | [19 empty] | 2026-03-09
FALSE | 1.8 | CV-192-STR-GIS-DRW-0008 | G.A. LAYOUT AND DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @ EL. 4.3 (B.O.C OF DECK SLAB) |  | 2025-12-23 |  | 2026-02-02 | 2026-02-05
FALSE | 1.9 | CV-192-STR-GIS-DRW-0009 | CONNECTION DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @ EL. 4.3 (B.O.C OF DECK SLAB) |  | 2025-12-25 |  | 2026-02-04 | 2026-02-09
FALSE | 1.10 | CV-192-STR-GIS-DRW-0010 | G.A. LAYOUT AND DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @ EL. 9.0 (B.O.C OF DECK SLAB) |  | 2025-12-27 |  | 2026-02-06 | 2026-02-11
FALSE | 1.11 | CV-192-STR-GIS-DRW-0011 | CONNECTION DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @ EL. 9.0 (B.O.C OF DECK SLAB) |  | 2025-12-29 |  | 2026-02-10 | 2026-02-13
FALSE | 1.12 | CV-192-STR-GIS-DRW-0012 | G.A. LAYOUT AND DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 13.700 (T.O.C OF DECK SLAB) |  | 2025-12-31 |  | 2026-02-12 | 2026-02-17
FALSE | 1.13 | CV-192-STR-GIS-DRW-0013 | CONNECTION DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 13.700 (T.O.C OF DECK SLAB) |  | 2026-01-02 |  | 2026-02-16 | 2026-02-19
FALSE | 1.14 | CV-192-STR-GIS-DRW-0014 | G.A. LAYOUT AND DETAILS OF STAIRS |  | 2026-01-04 |  | 2026-02-18 | 2026-02-23
FALSE | 1.15 | CV-192-STR-GIS-DRW-0015 | CONNECTION DETAILS OF STAIRS |  | 2026-01-06 |  | 2026-02-20 | 2026-02-25
FALSE | 1.16 | CV-192-STR-GIS-DRW-0016 | G.A. ELEVATION AND DETAILS |  | 2026-01-09 |  | 2026-02-24 | 2026-02-27
FALSE | 1.17 |  | SHOP DRAWINGS |  | 2026-02-09 | NA | 2026-03-19 | NA
| 2 | 11 KV Conversion substation and control room- Main Hall and auxilliary rooms
INPUT RECEIVED - 22nd DECEMBER (ARCHITECTURAL DRAWING YET TO BE RECEIVED- EXPECTED ON 10.01.2026)
FALSE | 2.1 | CV-192-STR-CSC-STD-0001 | STAAD ANALYSIS AND DESIGN |  | 2025-12-04 | 2025-12-08 | 1900-01-05 | 1900-01-10
FALSE | 2.2 | CV-192-STR-CSC-DRW-0002 | LAYOUT AND R/F DETAILS OF PEDESTAL AND ANCHOR BOLT |  | 2025-12-22 | 2025-12-25 | 2026-01-21 | 2026-01-26
FALSE | 2.3 | CV-192-STR-CSC-DRW-0003 | LAYOUT AND R/F DETAILS OF PLINTH BEAM |  | 2025-12-22 | 2025-12-25 | 2026-01-21 | 2026-01-26
FALSE | 2.4 | CV-192-STR-CSC-DRW-0004 | R/F DETAILS OF PLINTH BEAM |  | 2025-12-22 | 2025-12-25 | 2026-01-21 | 2026-01-26
FALSE | 2.5 | CV-192-STR-CSC-DRW-0005 | G.A. AND R/F DETAIL OF STEEL COLUMNS |  | 2025-12-19 | 2025-01-14 | 2026-01-21 | 2026-01-26
FALSE | 2.6 | CV-192-STR-CSC-DRW-0006 | CONNECTION DETAIL OF STEEL COLUMNS |  | 2025-12-21 |  | 2026-01-27 | 2026-01-30
FALSE | 2.7 | CV-192-STR-CSC-DRW-0007 | G.A. LAYOUT AND DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 3.9 (T.O.C OF DECK SLAB) |  | 2025-12-23 |  | 2026-01-29 | 2026-02-03
FALSE | 2.8 | CV-192-STR-CSC-DRW-0008 | CONNECTION DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 3.9 (T.O.C OF DECK SLAB) |  | 2025-12-25 |  | 2026-02-02 | 2026-02-05
FALSE | 2.9 | CV-192-STR-CSC-DRW-0009 | G.A. LAYOUT AND DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL.9.7 & 13.7 (T.O.C OF DECK SLAB) |  | 2025-12-27 |  | 2026-02-04 | 2026-02-09
FALSE | 2.10 | CV-192-STR-CSC-DRW-0010 | CONNECTION DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL.9.7 & 13.7 (T.O.C OF DECK SLAB) |  | 2025-12-29 |  | 2026-02-06 | 2026-02-11
FALSE | 2.11 | CV-192-STR-CSC-DRW-0011 | G.A. LAYOUT AND DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 15.2 & 17.7 (T.O.C OF DECK SLAB) |  | 2025-12-31 |  | 2026-02-10 | 2026-02-13
FALSE | 2.12 | CV-192-STR-CSC-DRW-0012 | CONNECTION DETAILS OF ROOF STEEL BEAMS AND SLAB @EL. 15.2 & 17.7 (T.O.C OF DECK SLAB) |  | 2026-01-02 |  | 2026-02-12 | 2026-02-17
FALSE | 2.13 | CV-192-STR-CSC-DRW-0013 | G.A. LAYOUT AND DETAILS OF STAIRS |  | 2026-01-04 |  | 2026-02-17 | 2026-02-20
FALSE | 2.14 | CV-192-STR-CSC-DRW-0014 | CONNECTION DETAILS OF STAIRS |  | 2026-01-06 |  | 2026-02-19 | 2026-02-24
FALSE | 2.15 | CV-192-STR-CSC-DRW-0015 | G.A. ELEVATION AND DETAILS |  | 2026-01-09 |  | 2026-02-24 | 2026-02-27
FALSE | 2.16 |  | SHOP DRAWINGS |  | 2026-02-09 | NA | 2026-03-19 | NA
| 1 | GTC Substation and control room
TRUE | 1.1 | CV-192-STR-GTC-STD-0001 | STAAD ANALYSIS AND DESIGN | NA | 2025-12-08 | 2025-12-11 | 2025-12-31 | 2026-01-06 | 2025-12-26 | 2025-12-29 | R
TRUE | 1.2 | CV-192-STR-GTC-DRW-0001 | LAYOUT AND R/F DETAILS OF FOUNDATION |  | 2025-12-24 | 2025-12-29 | 2026-01-07 | 2026-01-12 | 2026-01-02 | 2026-01-09 | 2 | 2026-01-12 | 2026-01-15 | V | 2026-01-14 | 2026-01-15 | 1 | 2026-01-23 | 2026-02-06 | V | 2026-01-23 | 2026-02-06 | 1 | 2026-02-19 | 2026-02-23 | 1
TRUE | 1.3 | CV-192-STR-GTC-DRW-0002 | LAYOUT AND R/F DETAILS OF PEDESTAL AND ANCHOR BOLT |  | 2025-12-24 | 2025-12-29 | 2026-01-07 | 2026-01-12 | 2026-01-02 | 2026-01-09 | 2 | 2026-01-12 | 2026-01-15 | V | 2026-01-14 | 2026-01-15 | 1 | 2026-01-23 | 2026-02-06 | V | 2026-01-23 | 2026-02-06 | 1 | 2026-02-19 | 2026-02-23 | 1
TRUE | 1.4 | CV-192-STR-GTC-DRW-0002-SHEET2 |  |  |  |  | 2026-01-07 | 2026-01-12 | - | - | V | 2026-01-12 | 2026-01-15 | V | 2026-01-14 | 2026-01-15 | 1 | 2026-01-23 | 2026-02-06 | 1 | 2026-02-19 | 2026-02-23 | 1
TRUE | 1.5 | CV-192-STR-GTC-DRW-0003 | LAYOUT AND R/F DETAILS OF PLINTH BEAM |  | 2025-12-24 | 2025-12-29 | 2026-01-07 | 2026-01-12 | 2026-01-02 | 2026-01-09 | 2 | 2026-01-12 | 2026-01-15 | V | 2026-01-14 | 2026-01-15 | 1 | 2026-01-23 | 2026-02-06 | 1 | 2026-02-19 | 2026-02-23 | 1
TRUE | 1.6 | CV-192-STR-GTC-DRW-0004 | R/F DETAILS OF PLINTH BEAM |  | 2025-12-24 | 2025-12-29 | 2026-01-07 | 2026-01-12 | 2026-01-02 | 2026-01-09 | 2 | 2026-01-12 | 2026-01-15 | V | 2026-01-14 | 2026-01-15 | 1 | 2026-01-23 | 2026-02-06 | 1 | 2026-02-19 | 2026-02-23 | 1
TRUE | 1.7 | CV-192-STR-GTC-DRW-0005 | G.A. AND R/F DETAIL OF STEEL COLUMNS |  | 2025-12-22 | 2026-01-15 | 2026-01-14 | 2026-01-19 | 2026-01-31 | 2026-02-09 | 2 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 1.8 | CV-192-STR-GTC-DRW-0006 | CONNECTION DETAIL OF STEEL COLUMNS |  | 2025-12-24 |  | 2026-01-16 | 2026-01-21 | 2026-01-31 | 2026-02-09 | 2 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 1.9 | CV-192-STR-GTC-DRW-0007 | G.A. LAYOUT AND DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65 (T.O.C OF DECK SLAB) | 1:100 | 2025-12-26 |  | 2026-01-20 | 2026-01-23 | 2026-01-31 | 2026-02-09 | 2 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 1.10 | CV-192-STR-GTC-DRW-0008 | CONNECTION DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65 (T.O.C OF DECK SLAB) |  | 2025-12-28 |  | 2026-01-22 | 2026-01-27 | 2026-01-31 | 2026-02-09 | 2 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 1.11 | CV-192-STR-GTC-DRW-0009 | G.A. LAYOUT AND DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL. 111.55 (T.O.C OF DECK SLAB) | 1:100 | 2025-12-30 |  | 2026-01-27 | 2026-01-30 | 2026-01-31 | 2026-02-09 | 2 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 1.12 | CV-192-STR-GTC-DRW-0010 | CONNECTION DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL. 111.55 (T.O.C OF DECK SLAB) |  | 2026-01-02 |  | 2026-01-29 | 2026-02-03 | 2026-01-31 | 2026-02-09 | 2 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 1.13 | CV-192-STR-GTC-DRW-0011 | G.A. LAYOUT AND DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 118.3 (T.O.C OF DECK SLAB) | 1:100 | 2026-01-04 |  | 2026-02-02 | 2026-02-05 | 2026-01-31 | 2026-02-09 | 2 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 1.14 | CV-192-STR-GTC-DRW-0012 | CONNECTION DETAILS OF ROOF STEEL BEAMS AND SLAB @EL. 118.3 (T.O.C OF DECK SLAB) |  | 2026-01-06 |  | 2026-02-04 | 2026-02-09 | 2026-01-31 | 2026-02-09 | 2 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 1.15 | CV-192-STR-GTC-DRW-0013 | G.A. LAYOUT AND DETAILS OF STAIRS | 1:100,1:50 | 2026-01-08 |  | 2026-02-06 | 2026-02-11 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 1.16 | CV-192-STR-GTC-DRW-0014 | CONNECTION DETAILS OF STAIRS |  | 2026-01-10 |  | 2026-02-10 | 2026-02-13 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 1.17 | CV-192-STR-GTC-DRW-0015 | G.A. ELEVATION AND DETAILS OF GIRTS | 1:100 | 2026-01-12 |  | 2026-02-12 | 2026-02-17 | 2026-01-31 | 2026-02-09 | 2 | 2026-02-16 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-20 | 1
FALSE | 1.18 |  | SHOP DRAWINGS | NA | 2026-02-10 | NA | 2026-03-09 | NA
| 2 | PTA SUBSTATION
TRUE | 2.1 | CV-192-STR-PTA-STD-0001 | STAAD ANALYSIS AND DESIGN | NA | 2025-12-08 | 2025-12-11 | 2025-12-31 | 2026-01-06 | 2025-12-26 | 2026-01-02 | R
TRUE | 2.2 | CV-192-STR-PTA-DRW-0001 | LAYOUT AND R/F DETAILS OF FOUNDATION |  | 2025-12-24 | 2025-12-29 | 2026-01-07 | 2026-01-12
TRUE | 2.3 | CV-192-STR-PTA-DRW-0002 | LAYOUT AND R/F DETAILS OF PEDESTAL AND ANCHOR BOLT |  | 2025-12-24 | 2025-12-29 | 2026-01-07 | 2026-01-12 | 2025-12-26 | 2026-01-02 | 2 | 2026-01-07 | 2026-01-08 | 2 | 2026-01-09 | 2026-01-14 | V | 2026-01-14 | 2026-01-14 | 1 | 2026-01-23 | 2026-01-27 | 1
TRUE | 2.4 | CV-192-STR-PTA-DRW-0003 | LAYOUT AND R/F DETAILS OF PLINTH BEAM |  | 2025-12-24 | 2025-12-29 | 2026-01-07 | 2026-01-12 | 2025-12-26 | 2026-01-02 | 2 | 2026-01-07 | 2026-01-08 | 2 | 2026-01-14 | 2026-01-14 | 1 | 2026-01-23 | 2026-01-27 | 1
TRUE | 2.5 | CV-192-STR-PTA-DRW-0004 | R/F DETAILS OF PLINTH BEAM |  | 2025-12-24 | 2025-12-29 | 2026-01-07 | 2026-01-12 | 2025-12-26 | 2026-01-14 | 1 | 2026-01-23 | 2026-01-27 | 1
TRUE | 2.6 | CV-192-STR-PTA-DRW-0005 | G.A. AND R/F DETAIL OF STEEL COLUMNS |  | 2025-12-22 | 2026-01-15 | 2026-01-14 | 2026-01-19 | 2026-01-22 | 2026-02-02 | 2 | 2026-02-10 | 2026-02-17 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 2.7 | CV-192-STR-PTA-DRW-0006 | CONNECTION DETAIL OF STEEL COLUMNS |  | 2025-12-24 |  | 2026-01-19 | 2026-01-22 | 2026-01-22 | 2026-02-02 | 2 | 2026-02-10 | 2026-02-17 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 2.8 | CV-192-STR-PTA-DRW-0007 | G.A. LAYOUT AND DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65(T.O.C OF DECK SLAB) | 1:100 | 2025-12-27 |  | 2026-01-22 | 2026-01-27 | 2026-01-22 | 2026-02-03 | 2 | 2026-02-10 | 2026-02-17 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 2.9 | CV-192-STR-PTA-DRW-0008 | CONNECTION DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65(T.O.C OF DECK SLAB) |  | 2025-12-30 |  | 2026-01-28 | 2026-02-02 | 2026-01-22 | 2026-02-04 | 2 | 2026-02-10 | 2026-02-17 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 2.10 | CV-192-STR-PTA-DRW-0009 | G.A. LAYOUT AND DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 110.35 & E.L.113.35 (T.O.C OF DECK SLAB) | 1:100 | 2026-01-02 |  | 2026-02-02 | 2026-02-05 | 2026-01-22 | 2026-02-02 | R | 2026-02-10 | 2026-02-17 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 2.11 | CV-192-STR-PTA-DRW-0010 | CONNECTION DETAILS OF ROOF STEEL BEAMS AND SLAB @EL. 110.35 & E.L.113.35 (T.O.C OF DECK SLAB) |  | 2026-01-05 |  | 2026-02-04 | 2026-02-09 | 2026-01-22 | 2026-02-04 | 2 | 2026-02-10 | 2026-02-17 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 2.12 | CV-192-STR-PTA-DRW-0011 | G.A. LAYOUT AND DETAILS OF STAIRS | 1:100,1:50 | 2026-01-08 |  | 2026-02-06 | 2026-02-11 | 2026-02-10 | 2026-02-17 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 2.13 | CV-192-STR-PTA-DRW-0012 | CONNECTION DETAILS OF STAIRS |  | 2026-01-11 |  | 2026-02-10 | 2026-02-13 | 2026-02-10 | 2026-02-17 | 1 | 2026-04-09 | 2026-04-20 | 1
TRUE | 2.14 | CV-192-STR-PTA-DRW-0013 | G.A. ELEVATION AND DETAILS OF GIRTS | 1:100 | 2026-01-12 |  | 2026-02-12 | 2026-02-17 | 2026-01-22 | 2026-02-04 | 2 | 2026-02-10 | 2026-02-17 | 1 | 2026-04-09 | 2026-04-20 | 1
FALSE | 2.15 |  | SHOP DRAWINGS | NA | 2026-02-10 | NA | 2026-03-09 | NA
| 3 | ABF Substation & Control Room
TRUE | 3.1 | CV-192-STR-ABF-STD-0001 | STAAD ANALYSIS AND DESIGN | NA | 2025-12-09 | 2025-12-14 | 2025-12-31 | 2026-01-06 | 2025-12-08 | 2025-12-16 | V | 2026-12-19 | 2026-12-22 | R | 2025-12-26 | 2026-01-02 | R
TRUE | 3.2 | CV-192-STR-ABF-DRW-0001 | LAYOUT AND R/F DETAILS OF FOUNDATION |  | 2025-12-26 | 2025-12-31 | 2026-01-07 | 2026-01-12 | 2026-01-02 | 2026-01-13 | 2 | 2026-01-15 | 2026-01-22 | 1 | 2026-01-23 | 2026-02-06 | 1
TRUE | 3.3 | CV-192-STR-ABF-DRW-0002 | LAYOUT AND R/F DETAILS OF PEDESTAL AND ANCHOR BOLT |  | 2025-12-26 | 2025-12-31 | 2026-01-07 | 2026-01-12 | 2026-01-02 | 2026-01-13 | 2 | 2026-01-15 | 2026-01-22 | 1 | 2026-01-23 | 2026-02-06 | 1
TRUE | 3.4 | CV-192-STR-ABF-DRW-0003 | LAYOUT AND R/F DETAILS OF PLINTH BEAM |  | 2025-12-26 | 2025-12-31 | 2026-01-07 | 2026-01-12 | 2026-01-02 | 2026-01-13 | 2 | 2026-01-15 | 2026-01-22 | 1 | 2026-01-23 | 2026-02-06 | 1
TRUE | 3.5 | CV-192-STR-ABF-DRW-0004 | R/F DETAILS OF PLINTH BEAM |  | 2025-12-26 | 2025-12-31 | 2026-01-07 | 2026-01-12 | 2026-01-02 | 2026-01-13 | 2 | 2026-01-15 | 2026-01-22 | 1 | 2026-01-23 | 2026-02-06 | 1
TRUE | 3.6 | CV-192-STR-ABF-DRW-0005 | G.A. AND R/F DETAIL OF STEEL COLUMNS |  | 2025-12-23 | 2026-01-16 | 2026-01-14 | 2026-01-19 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
TRUE | 3.7 | CV-192-STR-ABF-DRW-0006 | CONNECTION DETAIL OF STEEL COLUMNS | 1:100 | 2025-12-26 |  | 2026-01-16 | 2026-01-21 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
TRUE | 3.8 | CV-192-STR-ABF-DRW-0007 | G.A. LAYOUT AND DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65 (T.O.C OF DECK SLAB) | 1:100 | 2025-12-28 |  | 2026-01-20 | 2026-01-23 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
TRUE | 3.9 | CV-192-STR-ABF-DRW-0008 | CONNECTION DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65 (T.O.C OF DECK SLAB) |  | 2025-12-30 |  | 2026-01-22 | 2026-01-27 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
TRUE | 3.10 | CV-192-STR-ABF-DRW-0009 | G.A. LAYOUT AND DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL. 110.35 (T.O.C OF DECK SLAB) | 1:100 | 2026-01-01 |  | 2026-01-27 | 2026-01-30 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
TRUE | 3.11 | CV-192-STR-ABF-DRW-0010 | CONNECTION DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL. 110.35 (T.O.C OF DECK SLAB) |  | 2026-01-03 |  | 2026-01-29 | 2026-02-03 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
TRUE | 3.12 | CV-192-STR-ABF-DRW-0011 | G.A. LAYOUT AND DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 116.95 & @EL 119.9 (T.O.C OF DECK SLAB) | 1:100 | 2026-01-05 |  | 2026-02-02 | 2026-02-05 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
TRUE | 3.13 | CV-192-STR-ABF-DRW-0012 | CONNECTION DETAILS OF ROOF STEEL BEAMS AND SLAB @EL. 116.95 & @EL 119.9 (T.O.C OF DECK SLAB) |  | 2026-01-07 |  | 2026-02-04 | 2026-02-09 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
TRUE | 3.14 | CV-192-STR-ABF-DRW-0013 | G.A. LAYOUT AND DETAILS OF STAIRS | 1:100,1:50 | 2026-01-09 |  | 2026-02-06 | 2026-02-11 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
TRUE | 3.15 | CV-192-STR-ABF-DRW-0014 | CONNECTION DETAILS OF STAIRS |  | 2026-01-11 |  | 2026-02-10 | 2026-02-13 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
TRUE | 3.16 | CV-192-STR-ABF-DRW-0015 | G.A. ELEVATION AND DETAILS OF GIRTS | 1:100 | 2026-01-13 |  | 2026-02-12 | 2026-02-17 | 2026-02-13 | 2026-02-19 | 1 | 2026-04-09 | 2026-04-21 | 1
FALSE | 3.17 |  | SHOP DRAWINGS | NA | 2026-02-11 | NA | 2026-03-09 | NA
Formulas:
PLANNED DATE OF ISSUE (NEW) = WORKDAY([PLANNED DATE OF ISSUE (NEW), row above],2)
PLANNED DATE OF ISSUE (NEW) = WORKDAY([PLANNED DATE OF APPROVAL (NEW), row above],14)
PLANNED DATE OF APPROVAL (NEW) = WORKDAY([PLANNED DATE OF ISSUE (NEW)],3)
PLANNED DATE OF APPROVAL (ORIGINAL) = WORKDAY([PLANNED DATE OF ISSUE (ORIGINAL)],3)
Note on H2: Saksham Singh: Base date of Input changed from 14.11.2025 due to decision regarding wall provided by EIL on 11.12
Note on I2: Saksham Singh: Base date of Input changed from 14.11.2025 to 11.12.2025 due to decision regarding wall provided by EIL on 11.12
Note on D7: Saksham Singh:
Note on H54: Saksham Singh: Final cutout details are expected on 12.01.2025
Note on H73: Saksham Singh: Final cutout details are expected on 12.01.2025
Note on H90: Saksham Singh: Final cutout details are expected on 12.01.2025

## Sheet2 (hidden)
Building | No. of devilerable | Submitted | Approved | Revision
GTC Substation | 17 | 16 | 16 | R0 | =
|  |  |  | R1 | =
|  |  |  | R2 | =
|  |  |  | R3 | =
|  |  |  | R4 | =
PTA Substation | 15 | 14 | 14 | R0 | =
|  |  |  | R1 | =
|  |  |  | R2 | =
|  |  |  | R3 | =
|  |  |  | R4 | =
|  |  |  | R5 | =
ABF Substation | 17 | 16 | 16 | R0 | = | 12
|  |  |  | R1 | =
|  |  |  | R2 | = | 4
|  |  |  | R3 | =
|  |  |  | R4 | =
Net

## Sheet3 (hidden)
Proposal 2
| PTA |  | 192 |  | 9.5808 |  | 3832335.3293 | Complete
| GTC |  | 477 |  | 23.8024 |  | 9520958.0838 | Complete
| ABF |  | 400 |  | 19.9601 |  | 7984031.9361 | Complete
| 220 kV GIS |  | 451 |  | 22.505 |  | 9001996.008 | Complete
| 11 KV |  | 484 |  | 24.1517 |  | 9660678.6427 | Complete
40000000
2004
Proposal 1
[9 empty] | Civil | Arch | Stru
Building Description | Civil | Approval Code | Architectural | Approval Code | Structural | Approval Code |  |  | 30 | 10 | 60
| Completion % |  | Completion % |  | Completion %
PTA | 100 | 1 | 90 | 2 | 100 | 1
GTC | 100 | 1 | 90 | 2 | 100 | 1
ABF | 100 | 1 | 90 | 2 | 100 | 1 |  |  | 12000000 | 4000000 | 21600000 | 37600000
220 kV GIS | 100 | 2 | 90 | 2 | 100 | 2 | [5 empty] | 94
11 KV | 100 | 2 | 90 | 2 | 100 | 2