## Floor-wise
Row Labels | Total Drgs | Submitted | Approved
STAAD ANALYSIS AND DESIGN | 1 | 1 | 1
LAYOUT AND R/F DETAILS OF FOUNDATION | 1 | 1 | 1
LAYOUT AND R/F DETAILS OF PEDESTAL AND ANCHOR BOLT | 1 | 1 | 1
LAYOUT AND R/F DETAILS OF PLINTH BEAM | 1 | 1 | 1
R/F DETAILS OF PLINTH BEAM | 1 | 1 | 1
G.A. AND R/F DETAIL OF STEEL COLUMNS | 1 | 1 | 1
CONNECTION DETAIL OF STEEL COLUMNS | 1 | 1 | 1
G.A. LAYOUT AND DETAILS OF STAIRS | 1 | 1 | 1
CONNECTION DETAILS OF STAIRS | 1 | 1 | 1
G.A. ELEVATION AND DETAILS OF GIRTS | 1 | 1 | 1
G.A. LAYOUT AND DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65 (T.O.C OF DECK SLAB) | 1 | 1 | 1
CONNECTION DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65 (T.O.C OF DECK SLAB) | 1 | 1 | 1
G.A. LAYOUT AND DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL. 110.35 (T.O.C OF DECK SLAB) | 1 | 1 | 1
CONNECTION DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL. 110.35 (T.O.C OF DECK SLAB) | 1 | 1 | 1
G.A. LAYOUT AND DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 116.95 & @EL 119.9 (T.O.C OF DECK SLAB) | 1 | 1 | 1
CONNECTION DETAILS OF ROOF STEEL BEAMS AND SLAB @EL. 116.95 & @EL 119.9 (T.O.C OF DECK SLAB) | 1 | 1 | 1
Grand Total | 16 | 16 | 16
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## S-Curve Wkly
[10 empty] | Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals
Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | 2025-05-05 | #N/A | #N/A | #N/A | #N/A
2025-12-01 | 0% | 0% | 0% | 0% | 2026-01-05 | 0% |  | 0% | 0% | 2025-05-12 | #N/A | #N/A | #N/A | #N/A
2025-12-08 | 0% | 0% | 0% | 0% | 2026-01-12 | 0% |  | 0% | 0% | 2025-05-19 | #N/A | #N/A | #N/A | #N/A
2025-12-15 | 0% | 0% | 0% | 0% | 2026-01-19 | 25% |  | 0% | 0% | 2025-05-26 | #N/A | #N/A | #N/A | #N/A
2025-12-22 | 0% | 6.25% | 0% | 0% | 2026-01-26 | 100% |  | 50% | 0% | 2025-06-02 | #N/A | #N/A | #N/A | #N/A
2025-12-29 | 6.25% | 6.25% | 0% | 6.25% | 2026-02-02 | 100% |  | 100% | 0% | 2025-06-09 | #N/A | #N/A | #N/A | #N/A
2026-01-05 | 31.25% | 6.25% | 6.25% | 6.25% | 2026-02-09 | 100% |  | 100% | 0% | 2025-06-16 | #N/A | #N/A | #N/A | #N/A
2026-01-12 | 43.75% | 6.25% | 31.25% | 6.25% | 2026-02-16 | 100% |  | 100% | 0% | 2025-06-23 | #N/A | #N/A | #N/A | #N/A
2026-01-19 | 56.25% | 31.25% | 50% | 6.25% | 2026-02-23 | 100% |  | 100% | 0% | 2025-06-30 | #N/A | #N/A | #N/A | #N/A
2026-01-26 | 68.75% | 31.25% | 62.5% | 6.25% | 2026-03-02 | 100% |  | 100% | 0% | 2025-07-07 | #N/A | #N/A | #N/A | #N/A
2026-02-02 | 87.5% | 31.25% | 75% | 31.25% | 2026-03-09 | 100% |  | 100% | 0% | 2025-07-14 | #N/A | #N/A | #N/A | #N/A
2026-02-09 | 100% | 31.25% | 93.75% | 31.25% | 2026-03-16 | 100% |  | 100% | 0% | 2025-07-21 | #N/A | #N/A | #N/A | #N/A
2026-02-16 | 100% | 31.25% | 100% | 31.25% | 2026-03-23 | 100% |  | 100% | 0% | 2025-07-28 | #N/A | #N/A | #N/A | #N/A
2026-02-23 | 100% | 31.25% | 100% | 31.25% | 2026-03-30 | 100% |  | 100% | 0% | 2025-08-04 | #N/A | #N/A | #N/A | #N/A
2026-03-02 | 100% | 31.25% | 100% | 31.25% | 2026-04-06 | 100% |  | 100% | 0% | 2025-08-11 | #N/A | #N/A | #N/A | #N/A
2026-03-09 | 100% | 31.25% | 100% | 31.25% | 2026-04-13 | 100% |  | 100% | 0% | 2025-08-18 | #N/A | #N/A | #N/A | #N/A
2026-03-16 | 100% | 31.25% | 100% | 31.25% | 2026-04-20 | 100% |  | 100% | 0% | 2025-08-25 | #N/A | #N/A | #N/A | #N/A
2026-03-23 | 100% | 31.25% | 100% | 31.25% | 2026-04-27 | 100% |  | 100% | 0% | 2025-09-01 | #N/A | #N/A | #N/A | #N/A
2026-03-30 | 100% | 31.25% | 100% | 31.25% | 2026-05-04 | 100% |  | 100% | 100% | 2025-09-08 | #N/A | #N/A | #N/A | #N/A
2026-04-06 | 100% | 100% | 100% | 31.25% | 2026-05-11 | 100% |  | 100% | 100% | 2025-09-15 | #N/A | #N/A | #N/A | #N/A
2026-04-13 | 100% | 100% | 100% | 31.25% | 2026-05-18 | 100% |  | 100% | 100% | 2025-09-22 | #N/A | #N/A | #N/A | #N/A
2026-04-20 | 100% | 100% | 100% | 100% | 2026-05-25 | 100% |  | 100% | 100% | 2025-09-29 | #N/A | #N/A | #N/A | #N/A
2026-04-27 | 100% | 100% | 100% | 100% | Grand Total |  |  |  |  | 2025-10-06 | #N/A | #N/A | #N/A | #N/A
Grand Total | [9 empty] | 2025-10-13 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-10-20 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-10-27 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-11-03 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-11-10 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-11-17 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-11-24 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-12-01 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-12-08 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-12-15 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-12-22 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-12-29 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-01-05 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-01-12 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-01-19 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-01-26 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-02-02 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-02-09 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-02-16 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-02-23 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-03-02 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-03-09 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-03-16 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-03-23 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-03-30 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-04-06 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-04-13 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-04-20 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2026-04-27 | #N/A | #N/A | #N/A | #N/A
[10 empty] | Grand Total | #N/A | #N/A | #N/A | #N/A
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.

## S-Curve Monthly
Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Row Labels | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals
2025-11-01 | 0% | 0% | 0% | 0% | 2025-11-01 | 0% | 0% | 0% | 0% | 2025-02-01 | #N/A | #N/A | #N/A | #N/A
2025-12-01 | 6.25% | 6.25% | 0% | 0% | 2025-12-01 | 0% | 0% | 0% | 0% | 2025-03-01 | #N/A | #N/A | #N/A | #N/A
2026-01-01 | 68.75% | 31.25% | 62.5% | 6.25% | 2026-01-01 | 100% | 0% | 50% | 0% | 2025-04-01 | #N/A | #N/A | #N/A | #N/A
2026-02-01 | 100% | 31.25% | 100% | 31.25% | 2026-02-01 | 100% | 0% | 100% | 0% | 2025-05-01 | #N/A | #N/A | #N/A | #N/A
2026-03-01 | 100% | 31.25% | 100% | 31.25% | 2026-03-01 | 100% | 0% | 100% | 0% | 2025-06-01 | #N/A | #N/A | #N/A | #N/A
2026-04-01 | 100% | 100% | 100% | 100% | 2026-04-01 | 100% | 0% | 100% | 0% | 2025-07-01 | #N/A | #N/A | #N/A | #N/A
Grand Total |  |  |  |  | 2026-05-01 | 100% | 0% | 100% | 100% | 2025-08-01 | #N/A | #N/A | #N/A | #N/A
[5 empty] | 2026-06-01 | 100% | 100% | 100% | 100% | 2025-09-01 | #N/A | #N/A | #N/A | #N/A
[5 empty] | Grand Total |  |  |  |  | 2025-10-01 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-11-01 | #N/A | #N/A | #N/A | #N/A
[10 empty] | 2025-12-01 | #N/A | #N/A | #N/A | #N/A
[10 empty] | Grand Total | #N/A | #N/A | #N/A | #N/A
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.

## DB
Row Labels | Count of DRG ID
Architecture | 4
Structural | 16
(blank)
Grand Total | 20
Row Labels | Count of DRG ID | Count of Actual Submission to Client | Count of Actual Approval Date | Discipline | Submission Status | Approval Status
Architecture | 4 | 4 | 4 | Architecture | 100% | 100%
Structural | 16 | 16 | 16 | Structural | 100% | 100%
Grand Total | 20 | 20 | 20 | Grand Total | 100% | 100%
Speedometer | Value | Pointer | Value
Start | 0 | Value | 100
Initial | 30 | Pointer | 2
Mid | 40 | End | 98
End | 30
Max | 100
Discipline | Structural
Row Labels | Total DRG ID | Submitted | Approved
Structural | 16 | 16 | 16
Grand Total | 16 | 16 | 16
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Master_Data
S.no | Discipline | Category | DRG ID | Description | MDL Title | Responsible Person | 1st Submission Plan | 1st Submission Plan (Before changes in scope) | Actual Submission to Client | Revised Submission date (Plan) | Actual Revised submission | Planned Approval Date | Actual Approval Date | Planned Hard copy Sub.dates | Actual Hard copy sub.dates | Dependency | Approval Code | Approval Status
1 | Structural | Structural | CV-192-STR-ABF-STD-0001 | STAAD ANALYSIS AND DESIGN | STAAD ANALYSIS AND DESIGN | Smita/Praful/Sonal | 2025-12-31 |  | 2025-12-26 |  |  | 2026-01-06 | 2026-01-02 |  |  |  | V | Void
2 | Structural | Structural | CV-192-STR-ABF-DRW-0001 | LAYOUT AND R/F DETAILS OF FOUNDATION | LAYOUT AND R/F DETAILS OF FOUNDATION | Smita/Praful/Sonal | 2026-01-07 |  | 2026-01-23 |  |  | 2026-01-12 | 2026-02-06 |  |  |  | 2 | Approved with comments
3 | Structural | Structural | CV-192-STR-ABF-DRW-0002 | LAYOUT AND R/F DETAILS OF PEDESTAL AND ANCHOR BOLT | LAYOUT AND R/F DETAILS OF PEDESTAL AND ANCHOR BOLT | Smita/Praful/Sonal | 2026-01-07 |  | 2026-01-23 |  |  | 2026-01-12 | 2026-02-06 |  |  |  | 2 | Approved with comments
4 | Structural | Structural | CV-192-STR-ABF-DRW-0003 | LAYOUT AND R/F DETAILS OF PLINTH BEAM | LAYOUT AND R/F DETAILS OF PLINTH BEAM | Smita/Praful/Sonal | 2026-01-07 |  | 2026-01-23 |  |  | 2026-01-12 | 2026-02-06 |  |  |  | 2 | Approved with comments
5 | Structural | Structural | CV-192-STR-ABF-DRW-0004 | R/F DETAILS OF PLINTH BEAM | R/F DETAILS OF PLINTH BEAM | Smita/Praful/Sonal | 2026-01-07 |  | 2026-01-23 |  |  | 2026-01-12 | 2026-02-06 |  |  |  | 2 | Approved with comments
6 | Structural | Structural | CV-192-STR-ABF-DRW-0005 | G.A. AND R/F DETAIL OF STEEL COLUMNS | G.A. AND R/F DETAIL OF STEEL COLUMNS | Smita/Praful/Sonal | 2026-01-14 |  | 2026-04-09 |  |  | 2026-01-19 | 2026-04-21 |  |  |  | 1 | Approved
7 | Structural | Structural | CV-192-STR-ABF-DRW-0006 | CONNECTION DETAIL OF STEEL COLUMNS | CONNECTION DETAIL OF STEEL COLUMNS | Smita/Praful/Sonal | 2026-01-16 |  | 2026-04-09 |  |  | 2026-01-21 | 2026-04-21 |  |  |  | 1 | Approved
8 | Structural | Structural | CV-192-STR-ABF-DRW-0007 | G.A. LAYOUT AND DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65 (T.O.C OF DECK SLAB) | G.A. LAYOUT AND DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65 (T.O.C OF DECK SLAB) | Smita/Praful/Sonal | 2026-01-20 |  | 2026-04-09 |  |  | 2026-01-23 | 2026-04-21 |  |  |  | 1 | Approved
9 | Structural | Structural | CV-192-STR-ABF-DRW-0008 | CONNECTION DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65 (T.O.C OF DECK SLAB) | CONNECTION DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65 (T.O.C OF DECK SLAB) | Smita/Praful/Sonal | 2026-01-22 |  | 2026-04-09 |  |  | 2026-01-27 | 2026-04-21 |  |  |  | 1 | Approved
10 | Structural | Structural | CV-192-STR-ABF-DRW-0009 | G.A. LAYOUT AND DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL. 110.35 (T.O.C OF DECK SLAB) | G.A. LAYOUT AND DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL. 110.35 (T.O.C OF DECK SLAB) | Smita/Praful/Sonal | 2026-01-27 |  | 2026-04-09 |  |  | 2026-01-30 | 2026-04-21 |  |  |  | 1 | Approved
11 | Structural | Structural | CV-192-STR-ABF-DRW-0010 | CONNECTION DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL. 110.35 (T.O.C OF DECK SLAB) | CONNECTION DETAILS OF 2nd FLOOR STEEL BEAMS AND SLAB @EL. 110.35 (T.O.C OF DECK SLAB) | Smita/Praful/Sonal | 2026-01-29 |  | 2026-04-09 |  |  | 2026-02-03 | 2026-04-21 |  |  |  | 1 | Approved
12 | Structural | Structural | CV-192-STR-ABF-DRW-0011 | G.A. LAYOUT AND DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 116.95 & @EL 119.9 (T.O.C OF DECK SLAB) | G.A. LAYOUT AND DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 116.95 & @EL 119.9 (T.O.C OF DECK SLAB) | Smita/Praful/Sonal | 2026-02-02 |  | 2026-04-09 |  |  | 2026-02-05 | 2026-04-21 |  |  |  | 1 | Approved
13 | Structural | Structural | CV-192-STR-ABF-DRW-0012 | CONNECTION DETAILS OF ROOF STEEL BEAMS AND SLAB @EL. 116.95 & @EL 119.9 (T.O.C OF DECK SLAB) | CONNECTION DETAILS OF ROOF STEEL BEAMS AND SLAB @EL. 116.95 & @EL 119.9 (T.O.C OF DECK SLAB) | Smita/Praful/Sonal | 2026-02-04 |  | 2026-04-09 |  |  | 2026-02-09 | 2026-04-21 |  |  |  | 1 | Approved
14 | Structural | Structural | CV-192-STR-ABF-DRW-0013 | G.A. LAYOUT AND DETAILS OF STAIRS | G.A. LAYOUT AND DETAILS OF STAIRS | Smita/Praful/Sonal | 2026-02-06 |  | 2026-04-09 |  |  | 2026-02-11 | 2026-04-21 |  |  |  | 1 | Approved
15 | Structural | Structural | CV-192-STR-ABF-DRW-0014 | CONNECTION DETAILS OF STAIRS | CONNECTION DETAILS OF STAIRS | Smita/Praful/Sonal | 2026-02-10 |  | 2026-04-09 |  |  | 2026-02-13 | 2026-04-21 |  |  |  | 1 | Approved
16 | Structural | Structural | CV-192-STR-ABF-DRW-0015 | G.A. ELEVATION AND DETAILS OF GIRTS | G.A. ELEVATION AND DETAILS OF GIRTS | Smita/Praful/Sonal | 2026-02-12 |  | 2026-04-09 |  |  | 2026-02-17 | 2026-04-21 |  |  |  | 1 | Approved
17 | Architecture | Architecture | CV-192-ARC-ABF-DRW-0001 | GROUND AND FIRST FLOOR PLAN @ E.L. 100.45 & 104.65 (DOOR - WINDOW AND FINISHES SCHEDULE) | GROUND AND FIRST FLOOR PLAN @ E.L. 100.45 & 104.65 (DOOR - WINDOW AND FINISHES SCHEDULE) | Aakarsh | 2026-01-21 |  | 2026-06-10 |  |  | 2026-01-26 | 2026-05-05 |  |  |  | 2 | Approved with comments
18 | Architecture | Architecture | CV-192-ARC-ABF-DRW-0002 | SECOND AND TERRACE FLOOR PLAN @ E.L. 110.35 & 116.95 | SECOND AND TERRACE FLOOR PLAN @ E.L. 110.35 & 116.95 | Aakarsh | 2026-01-27 |  | 2026-06-10 |  |  | 2026-01-30 | 2026-05-05 |  |  |  | 2 | Approved with comments
19 | Architecture | Architecture | CV-192-ARC-ABF-DRW-0003 | ELEVATION | ELEVATION | Aakarsh | 2026-01-30 |  | 2026-06-10 |  |  | 2026-02-04 | 2026-05-05 |  |  |  | 2 | Approved with comments
20 | Architecture | Architecture | CV-192-ARC-ABF-DRW-0004 | SECTION | SECTION | Aakarsh | 2026-01-30 |  | 2026-06-10 |  |  | 2026-02-04 | 2026-05-05 |  |  |  | 2 | Approved with comments

## DRG_Status
DRG ID | Discipline | 1st Submission Plan_wk | Actual Submission to Client_wk | Planned Approval_wk | Actual Approval_wk | 1st Submission Plan_mth | Actual Submission to Client_mth | Planned Approval_mth | Actual Approval_mth
CV-192-STR-ABF-STD-0001 | Structural | 2025-12-29 | 2025-12-22 | 2026-01-05 | 2025-12-29 | 2025-12-01 | 2025-12-01 | 2026-01-01 | 2026-01-01
CV-192-STR-ABF-DRW-0001 | Structural | 2026-01-05 | 2026-01-19 | 2026-01-12 | 2026-02-02 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-02-01
CV-192-STR-ABF-DRW-0002 | Structural | 2026-01-05 | 2026-01-19 | 2026-01-12 | 2026-02-02 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-02-01
CV-192-STR-ABF-DRW-0003 | Structural | 2026-01-05 | 2026-01-19 | 2026-01-12 | 2026-02-02 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-02-01
CV-192-STR-ABF-DRW-0004 | Structural | 2026-01-05 | 2026-01-19 | 2026-01-12 | 2026-02-02 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-02-01
CV-192-STR-ABF-DRW-0005 | Structural | 2026-01-12 | 2026-04-06 | 2026-01-19 | 2026-04-20 | 2026-01-01 | 2026-04-01 | 2026-01-01 | 2026-04-01
CV-192-STR-ABF-DRW-0006 | Structural | 2026-01-12 | 2026-04-06 | 2026-01-19 | 2026-04-20 | 2026-01-01 | 2026-04-01 | 2026-01-01 | 2026-04-01
CV-192-STR-ABF-DRW-0007 | Structural | 2026-01-19 | 2026-04-06 | 2026-01-19 | 2026-04-20 | 2026-01-01 | 2026-04-01 | 2026-01-01 | 2026-04-01
CV-192-STR-ABF-DRW-0008 | Structural | 2026-01-19 | 2026-04-06 | 2026-01-26 | 2026-04-20 | 2026-01-01 | 2026-04-01 | 2026-01-01 | 2026-04-01
CV-192-STR-ABF-DRW-0009 | Structural | 2026-01-26 | 2026-04-06 | 2026-01-26 | 2026-04-20 | 2026-01-01 | 2026-04-01 | 2026-01-01 | 2026-04-01
CV-192-STR-ABF-DRW-0010 | Structural | 2026-01-26 | 2026-04-06 | 2026-02-02 | 2026-04-20 | 2026-01-01 | 2026-04-01 | 2026-02-01 | 2026-04-01
CV-192-STR-ABF-DRW-0011 | Structural | 2026-02-02 | 2026-04-06 | 2026-02-02 | 2026-04-20 | 2026-02-01 | 2026-04-01 | 2026-02-01 | 2026-04-01
CV-192-STR-ABF-DRW-0012 | Structural | 2026-02-02 | 2026-04-06 | 2026-02-09 | 2026-04-20 | 2026-02-01 | 2026-04-01 | 2026-02-01 | 2026-04-01
CV-192-STR-ABF-DRW-0013 | Structural | 2026-02-02 | 2026-04-06 | 2026-02-09 | 2026-04-20 | 2026-02-01 | 2026-04-01 | 2026-02-01 | 2026-04-01
CV-192-STR-ABF-DRW-0014 | Structural | 2026-02-09 | 2026-04-06 | 2026-02-09 | 2026-04-20 | 2026-02-01 | 2026-04-01 | 2026-02-01 | 2026-04-01
CV-192-STR-ABF-DRW-0015 | Structural | 2026-02-09 | 2026-04-06 | 2026-02-16 | 2026-04-20 | 2026-02-01 | 2026-04-01 | 2026-02-01 | 2026-04-01
CV-192-ARC-ABF-DRW-0001 | Architecture | 2026-01-19 | 2026-06-08 | 2026-01-26 | 2026-05-04 | 2026-01-01 | 2026-06-01 | 2026-01-01 | 2026-05-01
CV-192-ARC-ABF-DRW-0002 | Architecture | 2026-01-26 | 2026-06-08 | 2026-01-26 | 2026-05-04 | 2026-01-01 | 2026-06-01 | 2026-01-01 | 2026-05-01
CV-192-ARC-ABF-DRW-0003 | Architecture | 2026-01-26 | 2026-06-08 | 2026-02-02 | 2026-05-04 | 2026-01-01 | 2026-06-01 | 2026-02-01 | 2026-05-01
CV-192-ARC-ABF-DRW-0004 | Architecture | 2026-01-26 | 2026-06-08 | 2026-02-02 | 2026-05-04 | 2026-01-01 | 2026-06-01 | 2026-02-01 | 2026-05-01

## Sheet3
Row Labels | Sum of Submission_1 Plan | Sum of Submission_1 Actuals
2025-11-01 | 0% | 0%
2025-12-01 | 6.25% | 6.25%
2026-01-01 | 68.75% | 31.25%
2026-02-01 | 100% | 31.25%
2026-03-01 | 100% | 31.25%
2026-04-01 | 100% | 100%
Grand Total

## S_Curve_Data
| Column Labels |  | Structural | 16 |  |  |  | Architecture | 4 |  |  |  | MEP | #N/A |  |  |  | Structural | 16 |  |  |  | Architecture | 4 |  |  |  | MEP | #N/A
| Architecture | Structural | Rpt_Week | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Rpt_Week | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Rpt_Week | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Rpt_Month | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Rpt_Month | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals | Rpt_Month | Submission_1 Plan | Submission_1 Actuals | Approval Plan | Approval Actuals
Total DRG ID | 4 | 16 | 2025-01-06 | 0% | 0% | 0% | 0% | 2025-01-06 | 0% | 0% | 0% | 0% | 2025-01-06 | #N/A | #N/A | #N/A | #N/A | 2025-01-01 | 0% | 0% | 0% | 0% | 2025-01-01 | 0% | 0% | 0% | 0% | 2025-01-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-01-13 | 0% | 0% | 0% | 0% | 2025-01-13 | 0% | 0% | 0% | 0% | 2025-01-13 | #N/A | #N/A | #N/A | #N/A | 2025-02-01 | 0% | 0% | 0% | 0% | 2025-02-01 | 0% | 0% | 0% | 0% | 2025-02-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-01-20 | 0% | 0% | 0% | 0% | 2025-01-20 | 0% | 0% | 0% | 0% | 2025-01-20 | #N/A | #N/A | #N/A | #N/A | 2025-03-01 | 0% | 0% | 0% | 0% | 2025-03-01 | 0% | 0% | 0% | 0% | 2025-03-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-01-27 | 0% | 0% | 0% | 0% | 2025-01-27 | 0% | 0% | 0% | 0% | 2025-01-27 | #N/A | #N/A | #N/A | #N/A | 2025-04-01 | 0% | 0% | 0% | 0% | 2025-04-01 | 0% | 0% | 0% | 0% | 2025-04-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-02-03 | 0% | 0% | 0% | 0% | 2025-02-03 | 0% | 0% | 0% | 0% | 2025-02-03 | #N/A | #N/A | #N/A | #N/A | 2025-05-01 | 0% | 0% | 0% | 0% | 2025-05-01 | 0% | 0% | 0% | 0% | 2025-05-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-02-10 | 0% | 0% | 0% | 0% | 2025-02-10 | 0% | 0% | 0% | 0% | 2025-02-10 | #N/A | #N/A | #N/A | #N/A | 2025-06-01 | 0% | 0% | 0% | 0% | 2025-06-01 | 0% | 0% | 0% | 0% | 2025-06-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-02-17 | 0% | 0% | 0% | 0% | 2025-02-17 | 0% | 0% | 0% | 0% | 2025-02-17 | #N/A | #N/A | #N/A | #N/A | 2025-07-01 | 0% | 0% | 0% | 0% | 2025-07-01 | 0% | 0% | 0% | 0% | 2025-07-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-02-24 | 0% | 0% | 0% | 0% | 2025-02-24 | 0% | 0% | 0% | 0% | 2025-02-24 | #N/A | #N/A | #N/A | #N/A | 2025-08-01 | 0% | 0% | 0% | 0% | 2025-08-01 | 0% | 0% | 0% | 0% | 2025-08-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-03-03 | 0% | 0% | 0% | 0% | 2025-03-03 | 0% | 0% | 0% | 0% | 2025-03-03 | #N/A | #N/A | #N/A | #N/A | 2025-09-01 | 0% | 0% | 0% | 0% | 2025-09-01 | 0% | 0% | 0% | 0% | 2025-09-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-03-10 | 0% | 0% | 0% | 0% | 2025-03-10 | 0% | 0% | 0% | 0% | 2025-03-10 | #N/A | #N/A | #N/A | #N/A | 2025-10-01 | 0% | 0% | 0% | 0% | 2025-10-01 | 0% | 0% | 0% | 0% | 2025-10-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-03-17 | 0% | 0% | 0% | 0% | 2025-03-17 | 0% | 0% | 0% | 0% | 2025-03-17 | #N/A | #N/A | #N/A | #N/A | 2025-11-01 | 0% | 0% | 0% | 0% | 2025-11-01 | 0% | 0% | 0% | 0% | 2025-11-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-03-24 | 0% | 0% | 0% | 0% | 2025-03-24 | 0% | 0% | 0% | 0% | 2025-03-24 | #N/A | #N/A | #N/A | #N/A | 2025-12-01 | 6.25% | 6.25% | 0% | 0% | 2025-12-01 | 0% | 0% | 0% | 0% | 2025-12-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-03-31 | 0% | 0% | 0% | 0% | 2025-03-31 | 0% | 0% | 0% | 0% | 2025-03-31 | #N/A | #N/A | #N/A | #N/A | 2026-01-01 | 62.5% | 25% | 62.5% | 6.25% | 2026-01-01 | 100% | 0% | 50% | 0% | 2026-01-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-04-07 | 0% | 0% | 0% | 0% | 2025-04-07 | 0% | 0% | 0% | 0% | 2025-04-07 | #N/A | #N/A | #N/A | #N/A | 2026-02-01 | 31.25% | 0% | 37.5% | 25% | 2026-02-01 | 0% | 0% | 50% | 0% | 2026-02-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-04-14 | 0% | 0% | 0% | 0% | 2025-04-14 | 0% | 0% | 0% | 0% | 2025-04-14 | #N/A | #N/A | #N/A | #N/A | 2026-03-01 | 0% | 0% | 0% | 0% | 2026-03-01 | 0% | 0% | 0% | 0% | 2026-03-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-04-21 | 0% | 0% | 0% | 0% | 2025-04-21 | 0% | 0% | 0% | 0% | 2025-04-21 | #N/A | #N/A | #N/A | #N/A | 2026-04-01 | 0% | 68.75% | 0% | 68.75% | 2026-04-01 | 0% | 0% | 0% | 0% | 2026-04-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-04-28 | 0% | 0% | 0% | 0% | 2025-04-28 | 0% | 0% | 0% | 0% | 2025-04-28 | #N/A | #N/A | #N/A | #N/A | 2026-05-01 | 0% | 0% | 0% | 0% | 2026-05-01 | 0% | 0% | 0% | 100% | 2026-05-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-05-05 | 0% | 0% | 0% | 0% | 2025-05-05 | 0% | 0% | 0% | 0% | 2025-05-05 | #N/A | #N/A | #N/A | #N/A | 2026-06-01 | 0% | 0% | 0% | 0% | 2026-06-01 | 0% | 100% | 0% | 0% | 2026-06-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-05-12 | 0% | 0% | 0% | 0% | 2025-05-12 | 0% | 0% | 0% | 0% | 2025-05-12 | #N/A | #N/A | #N/A | #N/A | 2026-07-01 | 0% | 0% | 0% | 0% | 2026-07-01 | 0% | 0% | 0% | 0% | 2026-07-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-05-19 | 0% | 0% | 0% | 0% | 2025-05-19 | 0% | 0% | 0% | 0% | 2025-05-19 | #N/A | #N/A | #N/A | #N/A | 2026-08-01 | 0% | 0% | 0% | 0% | 2026-08-01 | 0% | 0% | 0% | 0% | 2026-08-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-05-26 | 0% | 0% | 0% | 0% | 2025-05-26 | 0% | 0% | 0% | 0% | 2025-05-26 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-06-02 | 0% | 0% | 0% | 0% | 2025-06-02 | 0% | 0% | 0% | 0% | 2025-06-02 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-06-09 | 0% | 0% | 0% | 0% | 2025-06-09 | 0% | 0% | 0% | 0% | 2025-06-09 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-06-16 | 0% | 0% | 0% | 0% | 2025-06-16 | 0% | 0% | 0% | 0% | 2025-06-16 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-06-23 | 0% | 0% | 0% | 0% | 2025-06-23 | 0% | 0% | 0% | 0% | 2025-06-23 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-06-30 | 0% | 0% | 0% | 0% | 2025-06-30 | 0% | 0% | 0% | 0% | 2025-06-30 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-07-07 | 0% | 0% | 0% | 0% | 2025-07-07 | 0% | 0% | 0% | 0% | 2025-07-07 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-07-14 | 0% | 0% | 0% | 0% | 2025-07-14 | 0% | 0% | 0% | 0% | 2025-07-14 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-07-21 | 0% | 0% | 0% | 0% | 2025-07-21 | 0% | 0% | 0% | 0% | 2025-07-21 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-07-28 | 0% | 0% | 0% | 0% | 2025-07-28 | 0% | 0% | 0% | 0% | 2025-07-28 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-08-04 | 0% | 0% | 0% | 0% | 2025-08-04 | 0% | 0% | 0% | 0% | 2025-08-04 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-08-11 | 0% | 0% | 0% | 0% | 2025-08-11 | 0% | 0% | 0% | 0% | 2025-08-11 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-08-18 | 0% | 0% | 0% | 0% | 2025-08-18 | 0% | 0% | 0% | 0% | 2025-08-18 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-08-25 | 0% | 0% | 0% | 0% | 2025-08-25 | 0% | 0% | 0% | 0% | 2025-08-25 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-09-01 | 0% | 0% | 0% | 0% | 2025-09-01 | 0% | 0% | 0% | 0% | 2025-09-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-09-08 | 0% | 0% | 0% | 0% | 2025-09-08 | 0% | 0% | 0% | 0% | 2025-09-08 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-09-15 | 0% | 0% | 0% | 0% | 2025-09-15 | 0% | 0% | 0% | 0% | 2025-09-15 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-09-22 | 0% | 0% | 0% | 0% | 2025-09-22 | 0% | 0% | 0% | 0% | 2025-09-22 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-09-29 | 0% | 0% | 0% | 0% | 2025-09-29 | 0% | 0% | 0% | 0% | 2025-09-29 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-10-06 | 0% | 0% | 0% | 0% | 2025-10-06 | 0% | 0% | 0% | 0% | 2025-10-06 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-10-13 | 0% | 0% | 0% | 0% | 2025-10-13 | 0% | 0% | 0% | 0% | 2025-10-13 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-10-20 | 0% | 0% | 0% | 0% | 2025-10-20 | 0% | 0% | 0% | 0% | 2025-10-20 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-10-27 | 0% | 0% | 0% | 0% | 2025-10-27 | 0% | 0% | 0% | 0% | 2025-10-27 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-11-03 | 0% | 0% | 0% | 0% | 2025-11-03 | 0% | 0% | 0% | 0% | 2025-11-03 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-11-10 | 0% | 0% | 0% | 0% | 2025-11-10 | 0% | 0% | 0% | 0% | 2025-11-10 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-11-17 | 0% | 0% | 0% | 0% | 2025-11-17 | 0% | 0% | 0% | 0% | 2025-11-17 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-11-24 | 0% | 0% | 0% | 0% | 2025-11-24 | 0% | 0% | 0% | 0% | 2025-11-24 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-12-01 | 0% | 0% | 0% | 0% | 2025-12-01 | 0% | 0% | 0% | 0% | 2025-12-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-12-08 | 0% | 0% | 0% | 0% | 2025-12-08 | 0% | 0% | 0% | 0% | 2025-12-08 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-12-15 | 0% | 0% | 0% | 0% | 2025-12-15 | 0% | 0% | 0% | 0% | 2025-12-15 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-12-22 | 0% | 6.25% | 0% | 0% | 2025-12-22 | 0% | 0% | 0% | 0% | 2025-12-22 | #N/A | #N/A | #N/A | #N/A
|  |  | 2025-12-29 | 6.25% | 0% | 0% | 6.25% | 2025-12-29 | 0% | 0% | 0% | 0% | 2025-12-29 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-01-05 | 25% | 0% | 6.25% | 0% | 2026-01-05 | 0% | 0% | 0% | 0% | 2026-01-05 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-01-12 | 12.5% | 0% | 25% | 0% | 2026-01-12 | 0% | 0% | 0% | 0% | 2026-01-12 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-01-19 | 12.5% | 25% | 18.75% | 0% | 2026-01-19 | 25% | 0% | 0% | 0% | 2026-01-19 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-01-26 | 12.5% | 0% | 12.5% | 0% | 2026-01-26 | 75% | 0% | 50% | 0% | 2026-01-26 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-02-02 | 18.75% | 0% | 12.5% | 25% | 2026-02-02 | 0% | 0% | 50% | 0% | 2026-02-02 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-02-09 | 12.5% | 0% | 18.75% | 0% | 2026-02-09 | 0% | 0% | 0% | 0% | 2026-02-09 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-02-16 | 0% | 0% | 6.25% | 0% | 2026-02-16 | 0% | 0% | 0% | 0% | 2026-02-16 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-02-23 | 0% | 0% | 0% | 0% | 2026-02-23 | 0% | 0% | 0% | 0% | 2026-02-23 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-03-02 | 0% | 0% | 0% | 0% | 2026-03-02 | 0% | 0% | 0% | 0% | 2026-03-02 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-03-09 | 0% | 0% | 0% | 0% | 2026-03-09 | 0% | 0% | 0% | 0% | 2026-03-09 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-03-16 | 0% | 0% | 0% | 0% | 2026-03-16 | 0% | 0% | 0% | 0% | 2026-03-16 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-03-23 | 0% | 0% | 0% | 0% | 2026-03-23 | 0% | 0% | 0% | 0% | 2026-03-23 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-03-30 | 0% | 0% | 0% | 0% | 2026-03-30 | 0% | 0% | 0% | 0% | 2026-03-30 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-04-06 | 0% | 68.75% | 0% | 0% | 2026-04-06 | 0% | 0% | 0% | 0% | 2026-04-06 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-04-13 | 0% | 0% | 0% | 0% | 2026-04-13 | 0% | 0% | 0% | 0% | 2026-04-13 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-04-20 | 0% | 0% | 0% | 68.75% | 2026-04-20 | 0% | 0% | 0% | 0% | 2026-04-20 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-04-27 | 0% | 0% | 0% | 0% | 2026-04-27 | 0% | 0% | 0% | 0% | 2026-04-27 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-05-04 | 0% | 0% | 0% | 0% | 2026-05-04 | 0% | 0% | 0% | 100% | 2026-05-04 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-05-11 | 0% | 0% | 0% | 0% | 2026-05-11 | 0% | 0% | 0% | 0% | 2026-05-11 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-05-18 | 0% | 0% | 0% | 0% | 2026-05-18 | 0% | 0% | 0% | 0% | 2026-05-18 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-05-25 | 0% | 0% | 0% | 0% | 2026-05-25 | 0% | 0% | 0% | 0% | 2026-05-25 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-06-01 | 0% | 0% | 0% | 0% | 2026-06-01 | 0% | 0% | 0% | 0% | 2026-06-01 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-06-08 | 0% | 0% | 0% | 0% | 2026-06-08 | 0% | 100% | 0% | 0% | 2026-06-08 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-06-15 | 0% | 0% | 0% | 0% | 2026-06-15 | 0% | 0% | 0% | 0% | 2026-06-15 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-06-22 | 0% | 0% | 0% | 0% | 2026-06-22 | 0% | 0% | 0% | 0% | 2026-06-22 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-06-29 | 0% | 0% | 0% | 0% | 2026-06-29 | 0% | 0% | 0% | 0% | 2026-06-29 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-07-06 | 0% | 0% | 0% | 0% | 2026-07-06 | 0% | 0% | 0% | 0% | 2026-07-06 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-07-13 | 0% | 0% | 0% | 0% | 2026-07-13 | 0% | 0% | 0% | 0% | 2026-07-13 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-07-20 | 0% | 0% | 0% | 0% | 2026-07-20 | 0% | 0% | 0% | 0% | 2026-07-20 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-07-27 | 0% | 0% | 0% | 0% | 2026-07-27 | 0% | 0% | 0% | 0% | 2026-07-27 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-08-03 | 0% | 0% | 0% | 0% | 2026-08-03 | 0% | 0% | 0% | 0% | 2026-08-03 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-08-10 | 0% | 0% | 0% | 0% | 2026-08-10 | 0% | 0% | 0% | 0% | 2026-08-10 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-08-17 | 0% | 0% | 0% | 0% | 2026-08-17 | 0% | 0% | 0% | 0% | 2026-08-17 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-08-24 | 0% | 0% | 0% | 0% | 2026-08-24 | 0% | 0% | 0% | 0% | 2026-08-24 | #N/A | #N/A | #N/A | #N/A
|  |  | 2026-08-31 | 0% | 0% | 0% | 0% | 2026-08-31 | 0% | 0% | 0% | 0% | 2026-08-31 | #N/A | #N/A | #N/A | #N/A

## Mappings
Date | Rpt_Week | Approval Code | Desc
| 2025-01-06 | 1 | Approved
| 2025-01-13 | 2 | Approved with comments
| 2025-01-20 | 3 | Not Approved
| 2025-01-27 | R | Retained for info
| 2025-02-03 | V | Void
2025-02-10
2025-02-17
2025-02-24
2025-03-03
2025-03-10
2025-03-17
2025-03-24
2025-03-31
2025-04-07
2025-04-14
2025-04-21
2025-04-28
2025-05-05
2025-05-12
2025-05-19
2025-05-26
2025-06-02
2025-06-09
2025-06-16
2025-06-23
2025-06-30
2025-07-07
2025-07-14
2025-07-21
2025-07-28
2025-08-04
2025-08-11
2025-08-18
2025-08-25
2025-09-01
2025-09-08
2025-09-15
2025-09-22
2025-09-29
2025-10-06
2025-10-13
2025-10-20
2025-10-27
2025-11-03
2025-11-10
2025-11-17
2025-11-24
2025-12-01
2025-12-08
2025-12-15
2025-12-22
2025-12-29
2026-01-05
2026-01-12
2026-01-19
2026-01-26
2026-02-02
2026-02-09
2026-02-16
2026-02-23
2026-03-02
2026-03-09
2026-03-16
2026-03-23
2026-03-30
2026-04-06
2026-04-13
2026-04-20
2026-04-27
2026-05-04
2026-05-11
2026-05-18
2026-05-25
2026-06-01
2026-06-08
2026-06-15
2026-06-22
2026-06-29
2026-07-06
2026-07-13
2026-07-20
2026-07-27
2026-08-03
2026-08-10
2026-08-17
2026-08-24
2026-08-31
2026-09-07
2026-09-14
2026-09-21
2026-09-28
2026-10-05
2026-10-12
2026-10-19
2026-10-26
2026-11-02
2026-11-09
2026-11-16
2026-11-23
2026-11-30
2026-12-07
2026-12-14
2026-12-21
2026-12-28
2027-01-04
2027-01-11
2027-01-18
2027-01-25
2027-02-01
2027-02-08
2027-02-15
2027-02-22
2027-03-01
2027-03-08
2027-03-15
2027-03-22
2027-03-29
2027-04-05
2027-04-12
2027-04-19
2027-04-26
2027-05-03
2027-05-10
2027-05-17
2027-05-24
2027-05-31
2027-06-07
2027-06-14
2027-06-21
2027-06-28
2027-07-05
2027-07-12
2027-07-19
2027-07-26
2027-08-02
2027-08-09
2027-08-16
2027-08-23
2027-08-30
2027-09-06
2027-09-13
2027-09-20
2027-09-27
2027-10-04
2027-10-11
2027-10-18
2027-10-25
2027-11-01
2027-11-08
2027-11-15
2027-11-22
2027-11-29
2027-12-06
2027-12-13
2027-12-20
2027-12-27
2028-01-03
2028-01-10
2028-01-17
2028-01-24
2028-01-31
2028-02-07
2028-02-14
2028-02-21
2028-02-28
2028-03-06
2028-03-13
2028-03-20
2028-03-27
2028-04-03
2028-04-10
2028-04-17
2028-04-24
2028-05-01
2028-05-08
2028-05-15
2028-05-22
2028-05-29
2028-06-05
2028-06-12
2028-06-19
2028-06-26
2028-07-03
2028-07-10
2028-07-17
2028-07-24
2028-07-31
2028-08-07
2028-08-14
2028-08-21
2028-08-28
2028-09-04
2028-09-11
2028-09-18
2028-09-25
2028-10-02
2028-10-09
2028-10-16
2028-10-23
2028-10-30
2028-11-06
2028-11-13
2028-11-20
2028-11-27
2028-12-04
2028-12-11
2028-12-18
2028-12-25
2029-01-01
2029-01-08
2029-01-15
2029-01-22
2029-01-29
2029-02-05
2029-02-12
2029-02-19
2029-02-26
2029-03-05
2029-03-12
2029-03-19
2029-03-26
2029-04-02
2029-04-09
2029-04-16
2029-04-23
2029-04-30
2029-05-07
2029-05-14
2029-05-21
2029-05-28
2029-06-04
2029-06-11
2029-06-18
2029-06-25
2029-07-02
2029-07-09
2029-07-16
2029-07-23
2029-07-30
2029-08-06
2029-08-13
2029-08-20
2029-08-27
2029-09-03
2029-09-10
2029-09-17
2029-09-24
2029-10-01
2029-10-08
2029-10-15
2029-10-22
2029-10-29
2029-11-05
2029-11-12
2029-11-19
2029-11-26
2029-12-03
2029-12-10
2029-12-17
2029-12-24
2029-12-31
2030-01-07
2030-01-14
2030-01-21
2030-01-28
2030-02-04
2030-02-11
2030-02-18
2030-02-25
2030-03-04
2030-03-11
2030-03-18
2030-03-25
2030-04-01
2030-04-08
2030-04-15
2030-04-22
2030-04-29
2030-05-06
2030-05-13
2030-05-20
2030-05-27
2030-06-03
2030-06-10
2030-06-17
2030-06-24
2030-07-01
2030-07-08
2030-07-15
2030-07-22
2030-07-29
2030-08-05
2030-08-12
2030-08-19
2030-08-26
2030-09-02
2030-09-09
2030-09-16
2030-09-23
2030-09-30
2030-10-07
2030-10-14
2030-10-21
2030-10-28
2030-11-04
2030-11-11
2030-11-18
2030-11-25
2030-12-02
2030-12-09
2030-12-16
2030-12-23
2030-12-30
2031-01-06
2031-01-13
2031-01-20
2031-01-27
2031-02-03
2031-02-10
2031-02-17
2031-02-24
2031-03-03
2031-03-10
2031-03-17
2031-03-24
2031-03-31
2031-04-07
2031-04-14
2031-04-21
2031-04-28
2031-05-05
2031-05-12
2031-05-19
2031-05-26
2031-06-02
2031-06-09
2031-06-16
2031-06-23
2031-06-30
2031-07-07
2031-07-14
2031-07-21
2031-07-28
2031-08-04
2031-08-11
2031-08-18
2031-08-25
2031-09-01
2031-09-08
2031-09-15
2031-09-22
2031-09-29
2031-10-06
2031-10-13
2031-10-20
2031-10-27
2031-11-03
2031-11-10
2031-11-17
2031-11-24
2031-12-01
2031-12-08
2031-12-15
2031-12-22
2031-12-29
2032-01-05
2032-01-12
2032-01-19
2032-01-26
2032-02-02
2032-02-09
2032-02-16
2032-02-23
2032-03-01
2032-03-08
2032-03-15
2032-03-22
2032-03-29
2032-04-05
2032-04-12
2032-04-19
2032-04-26
2032-05-03
2032-05-10
2032-05-17
2032-05-24
2032-05-31
2032-06-07
2032-06-14
2032-06-21
2032-06-28
2032-07-05
2032-07-12
2032-07-19
2032-07-26
2032-08-02
2032-08-09
2032-08-16
2032-08-23
2032-08-30
2032-09-06
2032-09-13
2032-09-20
2032-09-27
2032-10-04
2032-10-11
2032-10-18
2032-10-25
2032-11-01
2032-11-08
2032-11-15
2032-11-22
2032-11-29
2032-12-06
2032-12-13
2032-12-20
2032-12-27
2033-01-03
2033-01-10
2033-01-17
2033-01-24
2033-01-31
2033-02-07
2033-02-14
2033-02-21
2033-02-28
2033-03-07
2033-03-14
2033-03-21
2033-03-28
2033-04-04
2033-04-11
2033-04-18
2033-04-25
2033-05-02
2033-05-09
2033-05-16
2033-05-23
2033-05-30
2033-06-06
2033-06-13
2033-06-20
2033-06-27
2033-07-04
2033-07-11
2033-07-18
2033-07-25
2033-08-01
2033-08-08
2033-08-15
2033-08-22
2033-08-29
2033-09-05
2033-09-12
2033-09-19
2033-09-26
2033-10-03
2033-10-10
2033-10-17
2033-10-24
2033-10-31
2033-11-07
2033-11-14
2033-11-21
2033-11-28
2033-12-05
2033-12-12
2033-12-19
2033-12-26
2034-01-02
2034-01-09
2034-01-16
2034-01-23
2034-01-30
2034-02-06
2034-02-13
2034-02-20
2034-02-27
2034-03-06
2034-03-13
2034-03-20
2034-03-27
2034-04-03
2034-04-10
2034-04-17
2034-04-24
2034-05-01
2034-05-08
2034-05-15
2034-05-22
2034-05-29
2034-06-05
2034-06-12
2034-06-19
2034-06-26
2034-07-03
2034-07-10
2034-07-17
2034-07-24
2034-07-31
2034-08-07
2034-08-14
2034-08-21
2034-08-28
2034-09-04
2034-09-11
2034-09-18
2034-09-25
2034-10-02
2034-10-09
2034-10-16
2034-10-23
2034-10-30
2034-11-06
2034-11-13
2034-11-20
2034-11-27
2034-12-04
2034-12-11
2034-12-18
2034-12-25
2035-01-01
2035-01-08
2035-01-15
2035-01-22
2035-01-29
2035-02-05
2035-02-12
2035-02-19
2035-02-26
2035-03-05
2035-03-12
2035-03-19
2035-03-26
2035-04-02
2035-04-09
2035-04-16
2035-04-23
2035-04-30
2035-05-07
2035-05-14
2035-05-21
2035-05-28
2035-06-04
2035-06-11
2035-06-18
2035-06-25
2035-07-02
2035-07-09
2035-07-16
2035-07-23
2035-07-30
2035-08-06
2035-08-13
2035-08-20
2035-08-27
2035-09-03
2035-09-10
2035-09-17
2035-09-24
2035-10-01
2035-10-08
2035-10-15
2035-10-22
2035-10-29
2035-11-05
2035-11-12
2035-11-19
2035-11-26
2035-12-03
2035-12-10
2035-12-17
2035-12-24
2035-12-31
2036-01-07
2036-01-14
2036-01-21
2036-01-28
2036-02-04
2036-02-11
2036-02-18
2036-02-25
2036-03-03
2036-03-10
2036-03-17
2036-03-24
2036-03-31
2036-04-07
2036-04-14
2036-04-21
2036-04-28
2036-05-05
2036-05-12
2036-05-19
2036-05-26
2036-06-02
2036-06-09
2036-06-16
2036-06-23
2036-06-30
2036-07-07
2036-07-14
2036-07-21
2036-07-28
2036-08-04
2036-08-11
2036-08-18
2036-08-25
2036-09-01
2036-09-08
2036-09-15
2036-09-22
2036-09-29
2036-10-06
2036-10-13
2036-10-20
2036-10-27
2036-11-03
2036-11-10
2036-11-17
2036-11-24
2036-12-01
2036-12-08
2036-12-15
2036-12-22
2036-12-29
2037-01-05
2037-01-12
2037-01-19
2037-01-26
2037-02-02
2037-02-09
2037-02-16
2037-02-23
2037-03-02
2037-03-09
2037-03-16
2037-03-23
2037-03-30
2037-04-06
2037-04-13
2037-04-20
2037-04-27
2037-05-04
2037-05-11
2037-05-18
2037-05-25
2037-06-01
2037-06-08
2037-06-15
2037-06-22
2037-06-29
2037-07-06
2037-07-13
2037-07-20
2037-07-27
2037-08-03
2037-08-10
2037-08-17
2037-08-24
2037-08-31
2037-09-07
2037-09-14
2037-09-21
2037-09-28
2037-10-05
2037-10-12
2037-10-19
2037-10-26
2037-11-02
2037-11-09
2037-11-16
2037-11-23
2037-11-30
2037-12-07
2037-12-14
2037-12-21
2037-12-28
2038-01-04
2038-01-11
2038-01-18
2038-01-25
2038-02-01
2038-02-08
2038-02-15
2038-02-22
2038-03-01
2038-03-08
2038-03-15
2038-03-22
2038-03-29
2038-04-05
2038-04-12
2038-04-19
2038-04-26
2038-05-03
2038-05-10
2038-05-17
2038-05-24
2038-05-31
2038-06-07
2038-06-14
2038-06-21
2038-06-28
2038-07-05
2038-07-12
2038-07-19
2038-07-26
2038-08-02
2038-08-09
2038-08-16
2038-08-23
2038-08-30
2038-09-06
2038-09-13
2038-09-20
2038-09-27
2038-10-04
2038-10-11
2038-10-18
2038-10-25
2038-11-01
2038-11-08
2038-11-15
2038-11-22
2038-11-29
2038-12-06
2038-12-13
2038-12-20
2038-12-27
2039-01-03
2039-01-10
2039-01-17
2039-01-24
2039-01-31
2039-02-07
2039-02-14
2039-02-21
2039-02-28
2039-03-07
2039-03-14
2039-03-21
2039-03-28
2039-04-04
2039-04-11
2039-04-18
2039-04-25
2039-05-02
2039-05-09
2039-05-16
2039-05-23
2039-05-30
2039-06-06
2039-06-13
2039-06-20
2039-06-27
2039-07-04
2039-07-11
2039-07-18
2039-07-25
2039-08-01
2039-08-08
2039-08-15
2039-08-22
2039-08-29
2039-09-05
2039-09-12
2039-09-19
2039-09-26
2039-10-03
2039-10-10
2039-10-17
2039-10-24
2039-10-31
2039-11-07
2039-11-14
2039-11-21
2039-11-28
2039-12-05
2039-12-12
2039-12-19
2039-12-26
2040-01-02
2040-01-09
2040-01-16
2040-01-23
2040-01-30
2040-02-06
2040-02-13
2040-02-20
2040-02-27
2040-03-05
2040-03-12
2040-03-19
2040-03-26
2040-04-02
2040-04-09
2040-04-16
2040-04-23
2040-04-30
2040-05-07
2040-05-14
2040-05-21
2040-05-28
2040-06-04
2040-06-11
2040-06-18
2040-06-25
2040-07-02
2040-07-09
2040-07-16
2040-07-23
2040-07-30
2040-08-06
2040-08-13
2040-08-20
2040-08-27
2040-09-03
2040-09-10
2040-09-17
2040-09-24
2040-10-01
2040-10-08
2040-10-15
2040-10-22
2040-10-29
2040-11-05
2040-11-12
2040-11-19
2040-11-26
2040-12-03
2040-12-10
2040-12-17
2040-12-24
2040-12-31
2041-01-07
2041-01-14
2041-01-21
2041-01-28
2041-02-04
2041-02-11
2041-02-18
2041-02-25
2041-03-04
2041-03-11
2041-03-18
2041-03-25
2041-04-01
2041-04-08
2041-04-15
2041-04-22
2041-04-29
2041-05-06
2041-05-13
2041-05-20
2041-05-27
2041-06-03
2041-06-10
2041-06-17
2041-06-24
2041-07-01
2041-07-08
2041-07-15
2041-07-22
2041-07-29
2041-08-05
2041-08-12
2041-08-19
2041-08-26
2041-09-02
2041-09-09
2041-09-16
2041-09-23
2041-09-30
2041-10-07
2041-10-14
2041-10-21
2041-10-28
2041-11-04
2041-11-11
2041-11-18
2041-11-25
2041-12-02
2041-12-09
2041-12-16
2041-12-23
2041-12-30
2042-01-06
2042-01-13
2042-01-20
2042-01-27
2042-02-03
2042-02-10
2042-02-17
2042-02-24
2042-03-03
2042-03-10
2042-03-17
2042-03-24
2042-03-31
2042-04-07
2042-04-14
2042-04-21
2042-04-28
2042-05-05
2042-05-12
2042-05-19
2042-05-26
2042-06-02
2042-06-09
2042-06-16
2042-06-23
2042-06-30
2042-07-07
2042-07-14
2042-07-21
2042-07-28
2042-08-04
2042-08-11
2042-08-18
2042-08-25
2042-09-01
2042-09-08
2042-09-15
2042-09-22
2042-09-29
2042-10-06
2042-10-13
2042-10-20
2042-10-27
2042-11-03
2042-11-10
2042-11-17
2042-11-24
2042-12-01
2042-12-08
2042-12-15
2042-12-22
2042-12-29
2043-01-05
2043-01-12
2043-01-19
2043-01-26
2043-02-02
2043-02-09
2043-02-16
2043-02-23
2043-03-02
2043-03-09
2043-03-16
2043-03-23
2043-03-30
2043-04-06
2043-04-13
2043-04-20
2043-04-27
2043-05-04
2043-05-11
2043-05-18
2043-05-25
2043-06-01
2043-06-08
2043-06-15
2043-06-22
2043-06-29
2043-07-06
2043-07-13
2043-07-20
2043-07-27
2043-08-03
2043-08-10
2043-08-17
2043-08-24
2043-08-31
2043-09-07
2043-09-14
2043-09-21
2043-09-28
2043-10-05
2043-10-12
2043-10-19
2043-10-26
2043-11-02
2043-11-09
2043-11-16
2043-11-23
2043-11-30
2043-12-07
2043-12-14
2043-12-21
2043-12-28
2044-01-04
2044-01-11
2044-01-18
2044-01-25
2044-02-01
2044-02-08
2044-02-15
2044-02-22
2044-02-29
2044-03-07
2044-03-14
2044-03-21
2044-03-28
2044-04-04
2044-04-11
2044-04-18
2044-04-25
2044-05-02
2044-05-09
2044-05-16
2044-05-23
2044-05-30
2044-06-06
2044-06-13
2044-06-20
2044-06-27
2044-07-04
2044-07-11
2044-07-18
2044-07-25
2044-08-01
2044-08-08
Formulas:
Rpt_Week = [Rpt_Week, row above]+7-WEEKDAY([Rpt_Week, row above],2)+1