## Sheet1
S.no | Discipline | Category | DRG ID | Description | MDL Title | Responsible Person | 1st Submission Plan | 1st Submission Plan (Before changes in scope) | Actual Submission to Client | Revised Submission date (Plan) | Actual Revised submission | Planned Approval Date | Actual Approval Date | Planned Hard copy Sub.dates | Actual Hard copy sub.dates | Dependency | Approval Code
1 | Structural | Structural | BH-FAB-001 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
2 | Structural | Structural | BH-FAB-002 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
3 | Structural | Structural | BH-FAB-003 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
4 | Structural | Structural | BH-FAB-004 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
5 | Structural | Structural | BH-FAB-005 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
6 | Structural | Structural | BH-FAB-006 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
7 | Structural | Structural | BH-FAB-007 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
8 | Structural | Structural | BH-FAB-008 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
9 | Structural | Structural | BH-FAB-009 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
10 | Structural | Structural | BH-FAB-010 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
11 | Structural | Structural | BH-FAB-011 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
12 | Structural | Structural | BH-FAB-012 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
13 | Structural | Structural | BH-FAB-013 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
14 | Structural | Structural | BH-FAB-014 | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M | BUNKER HOUSE COLUMN UPTO EL+ 10.747 M |  | 2026-03-12 |  | 2026-05-18
15 | Structural | Structural | BH-FAB-015 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-03-16
16 | Structural | Structural | BH-FAB-016 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-03-16
17 | Structural | Structural | BH-FAB-017 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-03-16
18 | Structural | Structural | BH-FAB-018 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-03-16
19 | Structural | Structural | BH-FAB-019 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-03-16
20 | Structural | Structural | BH-FAB-020 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-03-16
21 | Structural | Structural | BH-FAB-021 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
22 | Structural | Structural | BH-FAB-022 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
23 | Structural | Structural | BH-FAB-023 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
24 | Structural | Structural | BH-FAB-024 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
25 | Structural | Structural | BH-FAB-025 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
26 | Structural | Structural | BH-FAB-026 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
27 | Structural | Structural | BH-FAB-027 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
28 | Structural | Structural | BH-FAB-028 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
29 | Structural | Structural | BH-FAB-029 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
30 | Structural | Structural | BH-FAB-030 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
31 | Structural | Structural | BH-FAB-031 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
32 | Structural | Structural | BH-FAB-032 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
33 | Structural | Structural | BH-FAB-033 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
34 | Structural | Structural | BH-FAB-034 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
35 | Structural | Structural | BH-FAB-035 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
36 | Structural | Structural | BH-FAB-036 | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M | BUNKER HOUSE FLOOR BEAM AT EL+ 13.810 M |  | 2026-03-09 |  | 2026-05-20
37 | Structural | Structural | BH-FAB-037 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M |  | 2026-03-18 |  | 2026-05-20
38 | Structural | Structural | BH-FAB-038 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M |  | 2026-03-18 |  | 2026-05-20
39 | Structural | Structural | BH-FAB-039 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M |  | 2026-03-18 |  | 2026-05-20
40 | Structural | Structural | BH-FAB-040 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M |  | 2026-03-18 |  | 2026-05-20
41 | Structural | Structural | BH-FAB-041 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M |  | 2026-03-18 |  | 2026-05-20
42 | Structural | Structural | BH-FAB-042 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M |  | 2026-03-18 |  | 2026-05-20
43 | Structural | Structural | BH-FAB-043 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M |  | 2026-03-18 |  | 2026-05-18
44 | Structural | Structural | BH-FAB-044 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M |  | 2026-03-18 |  | 2026-05-18
45 | Structural | Structural | BH-FAB-045 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M |  | 2026-03-18 |  | 2026-05-18
46 | Structural | Structural | BH-FAB-046 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+0.000 M TO EL+ 13.810 M |  | 2026-03-18 |  | 2026-05-18
47 | Structural | Structural | BH-FAB-047 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
48 | Structural | Structural | BH-FAB-048 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
49 | Structural | Structural | BH-FAB-049 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
50 | Structural | Structural | BH-FAB-050 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
51 | Structural | Structural | BH-FAB-051 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
52 | Structural | Structural | BH-FAB-052 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
53 | Structural | Structural | BH-FAB-053 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
54 | Structural | Structural | BH-FAB-054 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
55 | Structural | Structural | BH-FAB-055 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
56 | Structural | Structural | BH-FAB-056 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
57 | Structural | Structural | BH-FAB-057 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
58 | Structural | Structural | BH-FAB-058 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
59 | Structural | Structural | BH-FAB-059 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
60 | Structural | Structural | BH-FAB-060 | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M | BUNKER HOUSE COLUMN FROM EL+ 10.747 M TO EL+ 22.600 M |  | 2026-03-18 |  | 2026-05-20
61 | Structural | Structural | BH-FAB-061 | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M |  | 2026-03-18 |  | 2026-05-18
62 | Structural | Structural | BH-FAB-062 | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M |  | 2026-03-18 |  | 2026-05-18
63 | Structural | Structural | BH-FAB-063 | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M |  | 2026-03-18 |  | 2026-05-18
64 | Structural | Structural | BH-FAB-064 | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M |  | 2026-03-18 |  | 2026-05-18
65 | Structural | Structural | BH-FAB-065 | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M |  | 2026-03-18 |  | 2026-05-18
66 | Structural | Structural | BH-FAB-066 | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 9.000 M |  | 2026-03-18 |  | 2026-05-18
67 | Structural | Structural | BH-FAB-067 | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M |  | 2026-03-23
68 | Structural | Structural | BH-FAB-068 | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M |  | 2026-03-23
69 | Structural | Structural | BH-FAB-069 | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M |  | 2026-03-23
70 | Structural | Structural | BH-FAB-070 | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M |  | 2026-03-23
71 | Structural | Structural | BH-FAB-071 | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M |  | 2026-03-23
72 | Structural | Structural | BH-FAB-072 | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M |  | 2026-03-23
73 | Structural | Structural | BH-FAB-073 | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M |  | 2026-03-23
74 | Structural | Structural | BH-FAB-074 | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M |  | 2026-03-23
75 | Structural | Structural | BH-FAB-075 | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M |  | 2026-03-23
76 | Structural | Structural | BH-FAB-076 | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M | BUNKER HOUSE FLOOR BEAM AT EL+ 20.000 M |  | 2026-03-23
77 | Structural | Structural | BH-FAB-077 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
78 | Structural | Structural | BH-FAB-078 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
79 | Structural | Structural | BH-FAB-079 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
80 | Structural | Structural | BH-FAB-080 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23 |  | 2026-05-20
81 | Structural | Structural | BH-FAB-081 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23 |  | 2026-05-20
82 | Structural | Structural | BH-FAB-082 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23 |  | 2026-05-20
83 | Structural | Structural | BH-FAB-083 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23 |  | 2026-05-20
84 | Structural | Structural | BH-FAB-084 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23 |  | 2026-05-20
85 | Structural | Structural | BH-FAB-085 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23 |  | 2026-05-20
86 | Structural | Structural | BH-FAB-086 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23 |  | 2026-05-20
87 | Structural | Structural | BH-FAB-087 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23 |  | 2026-05-20
88 | Structural | Structural | BH-FAB-088 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23 |  | 2026-05-20
89 | Structural | Structural | BH-FAB-089 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
90 | Structural | Structural | BH-FAB-090 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
91 | Structural | Structural | BH-FAB-091 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
92 | Structural | Structural | BH-FAB-092 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
93 | Structural | Structural | BH-FAB-093 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
94 | Structural | Structural | BH-FAB-094 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
95 | Structural | Structural | BH-FAB-095 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
96 | Structural | Structural | BH-FAB-096 | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M | BUNKER HOUSE FLOOR BEAM AT EL+ 21.400 M |  | 2026-03-23
97 | Structural | Structural | BH-FAB-097 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-04-18 |  | 2026-05-20
98 | Structural | Structural | BH-FAB-098 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-04-18 |  | 2026-03-18
99 | Structural | Structural | BH-FAB-099 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-04-18 |  | 2026-05-20
100 | Structural | Structural | BH-FAB-100 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-04-18 |  | 2026-03-18
101 | Structural | Structural | BH-FAB-101 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-04-18 |  | 2026-03-18
102 | Structural | Structural | BH-FAB-102 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-04-18 |  | 2026-05-20
103 | Structural | Structural | BH-FAB-103 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-04-18 |  | 2026-03-18
104 | Structural | Structural | BH-FAB-104 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-04-18 |  | 2026-05-20
105 | Structural | Structural | BH-FAB-105 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-04-18 |  | 2026-03-18
106 | Structural | Structural | BH-FAB-106 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-04-18 |  | 2026-05-20
107 | Structural | Structural | BH-FAB-107 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
108 | Structural | Structural | BH-FAB-108 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
109 | Structural | Structural | BH-FAB-109 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
110 | Structural | Structural | BH-FAB-110 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
111 | Structural | Structural | BH-FAB-111 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
112 | Structural | Structural | BH-FAB-112 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
113 | Structural | Structural | BH-FAB-113 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
114 | Structural | Structural | BH-FAB-114 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
115 | Structural | Structural | BH-FAB-115 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
116 | Structural | Structural | BH-FAB-116 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
117 | Structural | Structural | BH-FAB-117 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
118 | Structural | Structural | BH-FAB-118 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
119 | Structural | Structural | BH-FAB-119 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-03-18
120 | Structural | Structural | BH-FAB-120 | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M | BUNKER HOUSE COLUMN FROM EL+ 21.400 M TO EL+ 35.675 M |  | 2026-03-18 |  | 2026-05-20
121 | Structural | Structural | BH-FAB-121 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-05-20
122 | Structural | Structural | BH-FAB-122 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-05-20
123 | Structural | Structural | BH-FAB-123 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-05-20
124 | Structural | Structural | BH-FAB-124 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-05-20
125 | Structural | Structural | BH-FAB-125 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
126 | Structural | Structural | BH-FAB-126 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-05-20
127 | Structural | Structural | BH-FAB-127 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
128 | Structural | Structural | BH-FAB-128 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
129 | Structural | Structural | BH-FAB-129 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
130 | Structural | Structural | BH-FAB-130 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
131 | Structural | Structural | BH-FAB-131 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
132 | Structural | Structural | BH-FAB-132 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
133 | Structural | Structural | BH-FAB-133 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
134 | Structural | Structural | BH-FAB-134 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
135 | Structural | Structural | BH-FAB-135 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
136 | Structural | Structural | BH-FAB-136 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
137 | Structural | Structural | BH-FAB-137 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
138 | Structural | Structural | BH-FAB-138 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
139 | Structural | Structural | BH-FAB-139 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
140 | Structural | Structural | BH-FAB-140 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
141 | Structural | Structural | BH-FAB-141 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
142 | Structural | Structural | BH-FAB-142 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
143 | Structural | Structural | BH-FAB-143 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-04-03
144 | Structural | Structural | BH-FAB-144 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-06
145 | Structural | Structural | BH-FAB-145 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-06
146 | Structural | Structural | BH-FAB-146 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-06
147 | Structural | Structural | BH-FAB-148 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
148 | Structural | Structural | BH-FAB-149 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
149 | Structural | Structural | BH-FAB-150 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
150 | Structural | Structural | BH-FAB-151 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
151 | Structural | Structural | BH-FAB-152 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-05-20
152 | Structural | Structural | BH-FAB-153 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-05-20
153 | Structural | Structural | BH-FAB-154 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
154 | Structural | Structural | BH-FAB-155 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-05-20
155 | Structural | Structural | BH-FAB-156 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
156 | Structural | Structural | BH-FAB-157 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
157 | Structural | Structural | BH-FAB-158 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
158 | Structural | Structural | BH-FAB-159 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
159 | Structural | Structural | BH-FAB-160 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
160 | Structural | Structural | BH-FAB-161 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-03-18
161 | Structural | Structural | BH-FAB-162 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+13.810 M TO EL+ 27.775 M |  | 2026-03-18 |  | 2026-05-20
162 | Structural | Structural | BH-FAB-163 | BUNKER HOUSE FLOOR BRACING EL+ 9 M | BUNKER HOUSE FLOOR BRACING EL+ 9 M |  | 2026-03-18 |  | 2026-05-18
163 | Structural | Structural | BH-FAB-164 | BUNKER HOUSE FLOOR BRACING EL+ 9 M | BUNKER HOUSE FLOOR BRACING EL+ 9 M |  | 2026-03-18 |  | 2026-05-18
164 | Structural | Structural | BH-FAB-165 | BUNKER HOUSE FLOOR BRACING EL+ 9 M | BUNKER HOUSE FLOOR BRACING EL+ 9 M |  | 2026-03-18 |  | 2026-05-18
165 | Structural | Structural | BH-FAB-166 | BUNKER HOUSE FLOOR BRACING EL+ 9 M | BUNKER HOUSE FLOOR BRACING EL+ 9 M |  | 2026-03-18 |  | 2026-05-18
166 | Structural | Structural | BH-FAB-167 | BUNKER HOUSE FLOOR BRACING EL+ 9 M | BUNKER HOUSE FLOOR BRACING EL+ 9 M |  | 2026-03-18 |  | 2026-05-18
167 | Structural | Structural | BH-FAB-168 | BUNKER HOUSE FLOOR BRACING EL+ 9 M | BUNKER HOUSE FLOOR BRACING EL+ 9 M |  | 2026-03-18 |  | 2026-05-18
168 | Structural | Structural | BH-FAB-169 | BUNKER HOUSE FLOOR BRACING EL+ 9 M | BUNKER HOUSE FLOOR BRACING EL+ 9 M |  | 2026-03-18 |  | 2026-05-18
169 | Structural | Structural | BH-FAB-170 | BUNKER HOUSE GIRDER BEAM | BUNKER HOUSE GIRDER BEAM |  | 2026-03-18 |  | 2026-05-18
170 | Structural | Structural | BH-FAB-171 | BUNKER HOUSE GIRDER BEAM | BUNKER HOUSE GIRDER BEAM |  | 2026-03-18 |  | 2026-05-18
171 | Structural | Structural | BH-FAB-172 | BUNKER HOUSE GIRDER BEAM | BUNKER HOUSE GIRDER BEAM |  | 2026-03-18 |  | 2026-05-18
172 | Structural | Structural | BH-FAB-173 | BUNKER HOUSE GIRDER BEAM | BUNKER HOUSE GIRDER BEAM |  | 2026-03-18 |  | 2026-05-18
173 | Structural | Structural | BH-FAB-174 | BUNKER HOUSE GIRDER BEAM | BUNKER HOUSE GIRDER BEAM |  | 2026-03-18 |  | 2026-05-18
174 | Structural | Structural | BH-FAB-175 | BUNKER HOUSE GIRDER BEAM | BUNKER HOUSE GIRDER BEAM |  | 2026-03-18 |  | 2026-05-18
175 | Structural | Structural | BH-FAB-176 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-03
176 | Structural | Structural | BH-FAB-177 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-03
177 | Structural | Structural | BH-FAB-178 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-03
178 | Structural | Structural | BH-FAB-179 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-03
179 | Structural | Structural | BH-FAB-180 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-03
180 | Structural | Structural | BH-FAB-181 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-03
181 | Structural | Structural | BH-FAB-182 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-03
182 | Structural | Structural | BH-FAB-183 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-03
183 | Structural | Structural | BH-FAB-184 | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M | BUNKER HOUSE FLOOR BEAM AT EL+ 35.675 M |  | 2026-04-03
184 | Structural | Structural | BH-FAB-185 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-03-28 |  | 2026-03-28
185 | Structural | Structural | BH-FAB-186 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-03-28 |  | 2026-03-28
186 | Structural | Structural | BH-FAB-187 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-03-28 |  | 2026-03-28
187 | Structural | Structural | BH-FAB-188 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-03-28 |  | 2026-03-28
188 | Structural | Structural | BH-FAB-189 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-03-28 |  | 2026-03-28
189 | Structural | Structural | BH-FAB-190 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-03-28 |  | 2026-03-28
190 | Structural | Structural | BH-FAB-191 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-17
191 | Structural | Structural | BH-FAB-192 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-17
192 | Structural | Structural | BH-FAB-193 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-17
193 | Structural | Structural | BH-FAB-194 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-17
194 | Structural | Structural | BH-FAB-195 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-17
195 | Structural | Structural | BH-FAB-196 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-17
196 | Structural | Structural | BH-FAB-197 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-17
197 | Structural | Structural | BH-FAB-198 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-17
198 | Structural | Structural | BH-FAB-199 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-21
199 | Structural | Structural | BH-FAB-200 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-21
200 | Structural | Structural | BH-FAB-201 | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M | BUNKER HOUSE FLOOR BEAM AT EL+ 27.775 M |  | 2026-03-28 |  | 2026-04-17
201 | Structural | Structural | BH-FAB-202 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-04-28 |  | 2026-03-28
202 | Structural | Structural | BH-FAB-203 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-04-28 |  | 2026-03-28
203 | Structural | Structural | BH-FAB-204 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-04-28 |  | 2026-03-28
204 | Structural | Structural | BH-FAB-205 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-04-28 |  | 2026-03-28
205 | Structural | Structural | BH-FAB-206 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-04-28 |  | 2026-03-28
206 | Structural | Structural | BH-FAB-207 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 27.775 M TO EL+ 41.535 M |  | 2026-04-28 |  | 2026-03-28
207 | Structural | Structural | BH-FAB-208 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
208 | Structural | Structural | BH-FAB-209 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
209 | Structural | Structural | BH-FAB-210 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
210 | Structural | Structural | BH-FAB-211 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
211 | Structural | Structural | BH-FAB-212 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
212 | Structural | Structural | BH-FAB-213 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
213 | Structural | Structural | BH-FAB-214 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
214 | Structural | Structural | BH-FAB-215 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
215 | Structural | Structural | BH-FAB-216 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
216 | Structural | Structural | BH-FAB-217 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
217 | Structural | Structural | BH-FAB-218 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
218 | Structural | Structural | BH-FAB-219 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
219 | Structural | Structural | BH-FAB-220 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
220 | Structural | Structural | BH-FAB-221 | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M | BUNKER HOUSE COLUMN FROM EL+ 44.610 M TO EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
221 | Structural | Structural | BH-FAB-222 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
222 | Structural | Structural | BH-FAB-223 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
223 | Structural | Structural | BH-FAB-224 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
224 | Structural | Structural | BH-FAB-225 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
225 | Structural | Structural | BH-FAB-226 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
226 | Structural | Structural | BH-FAB-227 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
227 | Structural | Structural | BH-FAB-228 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
228 | Structural | Structural | BH-FAB-229 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
229 | Structural | Structural | BH-FAB-230 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
230 | Structural | Structural | BH-FAB-231 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
231 | Structural | Structural | BH-FAB-232 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
232 | Structural | Structural | BH-FAB-233 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
233 | Structural | Structural | BH-FAB-234 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
234 | Structural | Structural | BH-FAB-235 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
235 | Structural | Structural | BH-FAB-236 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
236 | Structural | Structural | BH-FAB-237 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
237 | Structural | Structural | BH-FAB-238 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
238 | Structural | Structural | BH-FAB-239 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
239 | Structural | Structural | BH-FAB-240 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
240 | Structural | Structural | BH-FAB-241 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
241 | Structural | Structural | BH-FAB-242 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
242 | Structural | Structural | BH-FAB-243 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
243 | Structural | Structural | BH-FAB-244 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
244 | Structural | Structural | BH-FAB-245 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
245 | Structural | Structural | BH-FAB-246 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
246 | Structural | Structural | BH-FAB-247 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
247 | Structural | Structural | BH-FAB-248 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
248 | Structural | Structural | BH-FAB-249 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
249 | Structural | Structural | BH-FAB-250 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
250 | Structural | Structural | BH-FAB-251 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
251 | Structural | Structural | BH-FAB-252 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
252 | Structural | Structural | BH-FAB-253 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
253 | Structural | Structural | BH-FAB-254 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
254 | Structural | Structural | BH-FAB-255 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
255 | Structural | Structural | BH-FAB-256 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
256 | Structural | Structural | BH-FAB-257 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
257 | Structural | Structural | BH-FAB-258 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
258 | Structural | Structural | BH-FAB-259 | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M | BUNKER HOUSE FLOOR BEAM AT EL+ 52.650 M |  | 2026-03-28 |  | 2026-03-28
259 | Structural | Structural | BH-FAB-260 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-06
260 | Structural | Structural | BH-FAB-261 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-06
261 | Structural | Structural | BH-FAB-262 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-06
262 | Structural | Structural | BH-FAB-263 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
263 | Structural | Structural | BH-FAB-264 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
264 | Structural | Structural | BH-FAB-265 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
265 | Structural | Structural | BH-FAB-266 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
266 | Structural | Structural | BH-FAB-267 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
267 | Structural | Structural | BH-FAB-268 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
268 | Structural | Structural | BH-FAB-269 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
269 | Structural | Structural | BH-FAB-270 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
270 | Structural | Structural | BH-FAB-271 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
271 | Structural | Structural | BH-FAB-272 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
272 | Structural | Structural | BH-FAB-273 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
273 | Structural | Structural | BH-FAB-274 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
274 | Structural | Structural | BH-FAB-275 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
275 | Structural | Structural | BH-FAB-276 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
276 | Structural | Structural | BH-FAB-277 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
277 | Structural | Structural | BH-FAB-278 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
278 | Structural | Structural | BH-FAB-279 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
279 | Structural | Structural | BH-FAB-280 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
280 | Structural | Structural | BH-FAB-281 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
281 | Structural | Structural | BH-FAB-282 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
282 | Structural | Structural | BH-FAB-283 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
283 | Structural | Structural | BH-FAB-284 | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M | BUNKER HOUSE FLOOR BEAM AT EL+ 41.510 M |  | 2026-04-08
284 | Structural | Structural | BH-FAB-285 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-08
285 | Structural | Structural | BH-FAB-286 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-08
286 | Structural | Structural | BH-FAB-287 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-08
287 | Structural | Structural | BH-FAB-288 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
288 | Structural | Structural | BH-FAB-289 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
289 | Structural | Structural | BH-FAB-290 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
290 | Structural | Structural | BH-FAB-291 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
291 | Structural | Structural | BH-FAB-292 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
292 | Structural | Structural | BH-FAB-293 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
293 | Structural | Structural | BH-FAB-294 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
294 | Structural | Structural | BH-FAB-295 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
295 | Structural | Structural | BH-FAB-296 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
296 | Structural | Structural | BH-FAB-297 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
297 | Structural | Structural | BH-FAB-298 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
298 | Structural | Structural | BH-FAB-299 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
299 | Structural | Structural | BH-FAB-300 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
300 | Structural | Structural | BH-FAB-301 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
301 | Structural | Structural | BH-FAB-302 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
302 | Structural | Structural | BH-FAB-303 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
303 | Structural | Structural | BH-FAB-304 | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M | BUNKER HOUSE VERTICAL BRACING BETWEEN EL+ 41.510 M TO EL+ 52.650 M |  | 2026-04-12
304 | Structural | Structural | BH-FAB-305 | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M |  | 2026-04-12
305 | Structural | Structural | BH-FAB-306 | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M |  | 2026-04-12
306 | Structural | Structural | BH-FAB-307 | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M |  | 2026-04-12
307 | Structural | Structural | BH-FAB-308 | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M |  | 2026-04-12
308 | Structural | Structural | BH-FAB-309 | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M |  | 2026-04-12
309 | Structural | Structural | BH-FAB-310 | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M |  | 2026-04-12
310 | Structural | Structural | BH-FAB-311 | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M |  | 2026-04-12
311 | Structural | Structural | BH-FAB-312 | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M |  | 2026-04-12
312 | Structural | Structural | BH-FAB-313 | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M |  | 2026-04-12
313 | Structural | Structural | BH-FAB-314 | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M | BUNKER HOUSE HORIZONTAL BRACING BETWEEN AT EL+ 52.650 M |  | 2026-04-12
314 | Structural | Structural | BH-FAB-315 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
315 | Structural | Structural | BH-FAB-316 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
316 | Structural | Structural | BH-FAB-317 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
317 | Structural | Structural | BH-FAB-318 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
318 | Structural | Structural | BH-FAB-319 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
319 | Structural | Structural | BH-FAB-320 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
320 | Structural | Structural | BH-FAB-321 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
321 | Structural | Structural | BH-FAB-322 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
322 | Structural | Structural | BH-FAB-323 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
323 | Structural | Structural | BH-FAB-324 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
324 | Structural | Structural | BH-FAB-325 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
325 | Structural | Structural | BH-FAB-326 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
326 | Structural | Structural | BH-FAB-327 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
327 | Structural | Structural | BH-FAB-328 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
328 | Structural | Structural | BH-FAB-329 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
329 | Structural | Structural | BH-FAB-330 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
330 | Structural | Structural | BH-FAB-331 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
331 | Structural | Structural | BH-FAB-332 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
332 | Structural | Structural | BH-FAB-333 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
333 | Structural | Structural | BH-FAB-334 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
334 | Structural | Structural | BH-FAB-335 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
335 | Structural | Structural | BH-FAB-336 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
336 | Structural | Structural | BH-FAB-337 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
337 | Structural | Structural | BH-FAB-338 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
338 | Structural | Structural | BH-FAB-339 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
339 | Structural | Structural | BH-FAB-340 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
340 | Structural | Structural | BH-FAB-341 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
341 | Structural | Structural | BH-FAB-342 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
342 | Structural | Structural | BH-FAB-343 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
343 | Structural | Structural | BH-FAB-344 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
344 | Structural | Structural | BH-FAB-345 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
345 | Structural | Structural | BH-FAB-346 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
346 | Structural | Structural | BH-FAB-347 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
347 | Structural | Structural | BH-FAB-348 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
348 | Structural | Structural | BH-FAB-349 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
349 | Structural | Structural | BH-FAB-350 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
350 | Structural | Structural | BH-FAB-351 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
351 | Structural | Structural | BH-FAB-352 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
352 | Structural | Structural | BH-FAB-353 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
353 | Structural | Structural | BH-FAB-354 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
354 | Structural | Structural | BH-FAB-355 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
355 | Structural | Structural | BH-FAB-356 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
356 | Structural | Structural | BH-FAB-357 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
357 | Structural | Structural | BH-FAB-358 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
358 | Structural | Structural | BH-FAB-359 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
359 | Structural | Structural | BH-FAB-360 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
360 | Structural | Structural | BH-FAB-361 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
361 | Structural | Structural | BH-FAB-362 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
362 | Structural | Structural | BH-FAB-363 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
363 | Structural | Structural | BH-FAB-364 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
364 | Structural | Structural | BH-FAB-365 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
365 | Structural | Structural | BH-FAB-366 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
366 | Structural | Structural | BH-FAB-367 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
367 | Structural | Structural | BH-FAB-368 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
368 | Structural | Structural | BH-FAB-369 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
369 | Structural | Structural | BH-FAB-370 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
370 | Structural | Structural | BH-FAB-371 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
371 | Structural | Structural | BH-FAB-372 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
372 | Structural | Structural | BH-FAB-373 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
373 | Structural | Structural | BH-FAB-374 | BUNKER HOUSE-HOPPER | BUNKER HOUSE-HOPPER |  | 2026-04-12
374 | Structural | Structural | BH-FAB-375 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
375 | Structural | Structural | BH-FAB-376 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
376 | Structural | Structural | BH-FAB-377 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
377 | Structural | Structural | BH-FAB-378 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
378 | Structural | Structural | BH-FAB-379 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
379 | Structural | Structural | BH-FAB-380 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
380 | Structural | Structural | BH-FAB-381 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
381 | Structural | Structural | BH-FAB-382 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
382 | Structural | Structural | BH-FAB-383 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
383 | Structural | Structural | BH-FAB-384 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
384 | Structural | Structural | BH-FAB-385 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
385 | Structural | Structural | BH-FAB-386 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
386 | Structural | Structural | BH-FAB-387 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
387 | Structural | Structural | BH-FAB-388 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
388 | Structural | Structural | BH-FAB-389 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
389 | Structural | Structural | BH-FAB-390 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
390 | Structural | Structural | BH-FAB-391 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
391 | Structural | Structural | BH-FAB-392 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
392 | Structural | Structural | BH-FAB-393 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
393 | Structural | Structural | BH-FAB-394 | BUNKER HOUSE-STAIR | BUNKER HOUSE-STAIR |  | 2026-04-12
394 | Structural | Structural | BH-FAB-395 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
395 | Structural | Structural | BH-FAB-396 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
396 | Structural | Structural | BH-FAB-397 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
397 | Structural | Structural | BH-FAB-398 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
398 | Structural | Structural | BH-FAB-399 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
399 | Structural | Structural | BH-FAB-400 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
400 | Structural | Structural | BH-FAB-401 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
401 | Structural | Structural | BH-FAB-402 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
402 | Structural | Structural | BH-FAB-403 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
403 | Structural | Structural | BH-FAB-404 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
404 | Structural | Structural | BH-FAB-405 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
405 | Structural | Structural | BH-FAB-406 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-06-24
406 | Structural | Structural | BH-FAB-407 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-04-06
407 | Structural | Structural | BH-FAB-408 | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M | BUNKER HOUSE COLUMN FROM EL+ 33.530 M TO EL+ 44.608 M |  | 2026-04-07 |  | 2026-04-06
408 | Structural | Structural | BH-FAB-409 |  |  |  | 2026-07-03 |  | 2026-07-03
409 | Structural | Structural | BH-FAB-410 |  |  |  | 2026-07-03 |  | 2026-07-03
410 | Structural | Structural | BH-FAB-411 |  |  |  | 2026-07-03 |  | 2026-07-03
411 | Structural | Structural | BH-FAB-412 |  |  |  | 2026-07-03 |  | 2026-07-03
412 | Structural | Structural | BH-FAB-413 |  |  |  | 2026-07-03 |  | 2026-07-03
413 | Structural | Structural | BH-FAB-414 |  |  |  | 2026-07-03 |  | 2026-07-03
414 | Structural | Structural | BH-FAB-415 |  |  |  | 2026-07-03 |  | 2026-07-03
415 | Structural | Structural | BH-FAB-416 |  |  |  | 2026-07-03 |  | 2026-07-03
416 | Structural | Structural | BH-FAB-417 |  |  |  | 2026-07-03 |  | 2026-07-03
417 | Structural | Structural | BH-FAB-418 |  |  |  | 2026-07-03 |  | 2026-07-03
418 | Structural | Structural | BH-FAB-419 |  |  |  | 2026-07-03 |  | 2026-07-03
419 | Structural | Structural | BH-FAB-420 |  |  |  | 2026-07-03 |  | 2026-07-03
420 | Structural | Structural | BH-FAB-421 |  |  |  | 2026-07-03 |  | 2026-07-03
421 | Structural | Structural | BH-FAB-422 |  |  |  | 2026-07-03 |  | 2026-07-03
422 | Structural | Structural | BH-FAB-423 |  |  |  | 2026-07-03 |  | 2026-07-03
423 | Structural | Structural | BH-FAB-424 |  |  |  | 2026-07-03 |  | 2026-07-03
424 | Structural | Structural | BH-FAB-425 |  |  |  | 2026-07-03 |  | 2026-07-03
425 | Structural | Structural | BH-FAB-426 |  |  |  | 2026-07-03 |  | 2026-07-03
426 | Structural | Structural | BH-FAB-427 |  |  |  | 2026-07-03 |  | 2026-07-03
427 | Structural | Structural | BH-FAB-428 |  |  |  | 2026-07-03 |  | 2026-07-03
428 | Structural | Structural | BH-FAB-429 |  |  |  | 2026-07-03 |  | 2026-07-03
429 | Structural | Structural | BH-FAB-430 |  |  |  | 2026-07-03 |  | 2026-07-03
430 | Structural | Structural | BH-FAB-431 |  |  |  | 2026-07-03 |  | 2026-07-03
431 | Structural | Structural | BH-FAB-432 |  |  |  | 2026-07-03 |  | 2026-07-03
432 | Structural | Structural | BH-FAB-433 |  |  |  | 2026-07-03 |  | 2026-07-03
433 | Structural | Structural | BH-FAB-434 |  |  |  | 2026-07-03 |  | 2026-07-03
434 | Structural | Structural | BH-FAB-435 |  |  |  | 2026-07-03 |  | 2026-07-03
435 | Structural | Structural | BH-FAB-436 |  |  |  | 2026-07-03 |  | 2026-07-03
436 | Structural | Structural | BH-FAB-437 |  |  |  | 2026-07-03 |  | 2026-07-03
437 | Structural | Structural | BH-FAB-438 |  |  |  | 2026-07-03 |  | 2026-07-03
438 | Structural | Structural | BH-FAB-439 |  |  |  | 2026-07-03 |  | 2026-07-03
439 | Structural | Structural | BH-FAB-440 |  |  |  | 2026-07-03 |  | 2026-07-03
440 | Structural | Structural | BH-FAB-441 |  |  |  | 2026-07-03 |  | 2026-07-03
441 | Structural | Structural | BH-FAB-442 |  |  |  | 2026-07-03 |  | 2026-07-03
442 | Structural | Structural | BH-FAB-443 |  |  |  | 2026-07-03 |  | 2026-07-03
443 | Structural | Structural | BH-FAB-444 |  |  |  | 2026-07-03 |  | 2026-07-03
444 | Structural | Structural | BH-FAB-445 |  |  |  | 2026-07-03 |  | 2026-07-03
445 | Structural | Structural | BH-FAB-446 |  |  |  | 2026-07-03 |  | 2026-07-03
446 | Structural | Structural | BH-FAB-447 |  |  |  | 2026-07-03 |  | 2026-07-03
447 | Structural | Structural | BH-FAB-448 |  |  |  | 2026-07-03 |  | 2026-07-03
448 | Structural | Structural | BH-FAB-449 |  |  |  | 2026-07-03 |  | 2026-07-03
449 | Structural | Structural | BH-FAB-450 |  |  |  | 2026-07-03 |  | 2026-07-03
450 | Structural | Structural | BH-FAB-451 |  |  |  | 2026-07-03 |  | 2026-07-03
451 | Structural | Structural | BH-FAB-452 |  |  |  | 2026-07-03 |  | 2026-07-03
452 | Structural | Structural | BH-FAB-453 |  |  |  | 2026-07-03 |  | 2026-07-03
453 | Structural | Structural | BH-FAB-454 |  |  |  | 2026-07-03 |  | 2026-07-03
454 | Structural | Structural | BH-FAB-455 |  |  |  | 2026-07-03 |  | 2026-07-03
455 | Structural | Structural | BH-FAB-456 |  |  |  | 2026-07-03 |  | 2026-07-03
456 | Structural | Structural | BH-FAB-457 |  |  |  | 2026-07-03 |  | 2026-07-03
457 | Structural | Structural | BH-FAB-458 |  |  |  | 2026-07-03 |  | 2026-07-03
458 | Structural | Structural | BH-FAB-459 |  |  |  | 2026-07-03 |  | 2026-07-03
459 | Structural | Structural | BH-FAB-460 |  |  |  | 2026-07-03 |  | 2026-07-03
460 | Structural | Structural | BH-FAB-461 |  |  |  | 2026-07-03 |  | 2026-07-03
461 | Structural | Structural | BH-FAB-462 |  |  |  | 2026-07-03 |  | 2026-07-03
462 | Structural | Structural | BH-FAB-463 |  |  |  | 2026-07-03 |  | 2026-07-03
463 | Structural | Structural | BH-FAB-464 |  |  |  | 2026-07-03 |  | 2026-07-03
464 | Structural | Structural | BH-FAB-465 |  |  |  | 2026-07-03 |  | 2026-07-03
465 | Structural | Structural | BH-FAB-466 |  |  |  | 2026-07-03 |  | 2026-07-03
466 | Structural | Structural | BH-FAB-467 |  |  |  | 2026-07-03 |  | 2026-07-03
467 | Structural | Structural | BH-FAB-468 |  |  |  | 2026-07-03 |  | 2026-07-03
468 | Structural | Structural | BH-FAB-469 |  |  |  | 2026-07-03 |  | 2026-07-03
469 | Structural | Structural | BH-FAB-470 |  |  |  | 2026-07-03 |  | 2026-07-03
470 | Structural | Structural | BH-FAB-471 |  |  |  | 2026-07-03 |  | 2026-07-03
471 | Structural | Structural | BH-FAB-472 |  |  |  | 2026-07-03 |  | 2026-07-03
472 | Structural | Structural | BH-FAB-473 |  |  |  | 2026-07-03 |  | 2026-07-03
473 | Structural | Structural | BH-FAB-474 |  |  |  | 2026-07-03 |  | 2026-07-03
474 | Structural | Structural | BH-FAB-475 |  |  |  | 2026-07-03 |  | 2026-07-03
475 | Structural | Structural | BH-FAB-476 |  |  |  | 2026-07-03 |  | 2026-07-03
476 | Structural | Structural | BH-FAB-477 |  |  |  | 2026-07-03 |  | 2026-07-03
477 | Structural | Structural | BH-FAB-478 |  |  |  | 2026-07-03 |  | 2026-07-03
478 | Structural | Structural | BH-FAB-479 |  |  |  | 2026-07-03 |  | 2026-07-03
479 | Structural | Structural | BH-FAB-480 |  |  |  | 2026-07-03 |  | 2026-07-03
480 | Structural | Structural | BH-FAB-481 |  |  |  | 2026-07-03 |  | 2026-07-03