## Sheet1
S.no | Discipline | Category | DRG ID | Description | MDL Title | Responsible Person | 1st Submission Plan | 1st Submission Plan (Before changes in scope) | Actual Submission to Client | Revised Submission date (Plan) | Actual Revised submission | Planned Approval Date | Actual Approval Date | Planned Hard copy Sub.dates | Actual Hard copy sub.dates | Dependency | Approval Code
1 | Structural | Structural | CV-192-STR-PTA-STD-0001 | STAAD ANALYSIS AND DESIGN | STAAD ANALYSIS AND DESIGN | Smita/Praful/Sonal | 2025-12-31 |  | 2026-01-07 |  |  | 2026-01-06 | 2026-01-08 |  |  |  | R
2 | Structural | Structural | CV-192-STR-PTA-DRW-0001 | LAYOUT AND R/F DETAILS OF FOUNDATION | LAYOUT AND R/F DETAILS OF FOUNDATION | Smita/Praful/Sonal | 2026-01-07 |  | 2026-01-07 |  |  | 2026-01-12 | 2026-01-08 |  |  |  | V
3 | Structural | Structural | CV-192-STR-PTA-DRW-0002 | LAYOUT AND R/F DETAILS OF PEDESTAL AND ANCHOR BOLT | LAYOUT AND R/F DETAILS OF PEDESTAL AND ANCHOR BOLT | Smita/Praful/Sonal | 2026-01-07 |  | 2026-01-23 |  |  | 2026-01-12 | 2026-01-27 |  |  |  | 2
4 | Structural | Structural | CV-192-STR-PTA-DRW-0003 | LAYOUT AND R/F DETAILS OF PLINTH BEAM | LAYOUT AND R/F DETAILS OF PLINTH BEAM | Smita/Praful/Sonal | 2026-01-07 |  | 2026-01-23 |  |  | 2026-01-12 | 2026-01-27 |  |  |  | 2
5 | Structural | Structural | CV-192-STR-PTA-DRW-0004 | R/F DETAILS OF PLINTH BEAM | R/F DETAILS OF PLINTH BEAM | Smita/Praful/Sonal | 2026-01-07 |  | 2026-01-23 |  |  | 2026-01-12 | 2026-01-27 |  |  |  | 1
6 | Structural | Structural | CV-192-STR-PTA-DRW-0005 | G.A. AND R/F DETAIL OF STEEL COLUMNS | G.A. AND R/F DETAIL OF STEEL COLUMNS | Smita/Praful/Sonal | 2026-01-14 |  | 2026-04-09 |  |  | 2026-01-19 | 2026-04-20 |  |  |  | 2
7 | Structural | Structural | CV-192-STR-PTA-DRW-0006 | CONNECTION DETAIL OF STEEL COLUMNS | CONNECTION DETAIL OF STEEL COLUMNS | Smita/Praful/Sonal | 2026-01-19 |  | 2026-04-09 |  |  | 2026-01-22 | 2026-04-20 |  |  |  | 2
8 | Structural | Structural | CV-192-STR-PTA-DRW-0007 | G.A. LAYOUT AND DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65(T.O.C OF DECK SLAB) | G.A. LAYOUT AND DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65(T.O.C OF DECK SLAB) | Smita/Praful/Sonal | 2026-01-22 |  | 2026-04-09 |  |  | 2026-01-27 | 2026-04-20 |  |  |  | 2
9 | Structural | Structural | CV-192-STR-PTA-DRW-0008 | CONNECTION DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65(T.O.C OF DECK SLAB) | CONNECTION DETAILS OF FIRST FLOOR STEEL BEAMS AND SLAB @EL. 104.65(T.O.C OF DECK SLAB) | Smita/Praful/Sonal | 2026-01-28 |  | 2026-04-09 |  |  | 2026-02-02 | 2026-04-20 |  |  |  | 2
10 | Structural | Structural | CV-192-STR-PTA-DRW-0009 | G.A. LAYOUT AND DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 110.35 & E.L.113.35 (T.O.C OF DECK SLAB) | G.A. LAYOUT AND DETAILS OF OF ROOF STEEL BEAMS AND SLAB @EL. 110.35 & E.L.113.35 (T.O.C OF DECK SLAB) | Smita/Praful/Sonal | 2026-02-02 |  | 2026-04-09 |  |  | 2026-02-05 | 2026-04-20 |  |  |  | R
11 | Structural | Structural | CV-192-STR-PTA-DRW-0010 | CONNECTION DETAILS OF ROOF STEEL BEAMS AND SLAB @EL. 110.35 & E.L.113.35 (T.O.C OF DECK SLAB) | CONNECTION DETAILS OF ROOF STEEL BEAMS AND SLAB @EL. 110.35 & E.L.113.35 (T.O.C OF DECK SLAB) | Smita/Praful/Sonal | 2026-02-04 |  | 2026-04-09 |  |  | 2026-02-09 | 2026-04-20 |  |  |  | 2
12 | Structural | Structural | CV-192-STR-PTA-DRW-0011 | G.A. LAYOUT AND DETAILS OF STAIRS | G.A. LAYOUT AND DETAILS OF STAIRS | Smita/Praful/Sonal | 2026-02-06 |  | 2026-04-09 |  |  | 2026-02-11 | 2026-04-20 |  |  |  | 1
13 | Structural | Structural | CV-192-STR-PTA-DRW-0012 | CONNECTION DETAILS OF STAIRS | CONNECTION DETAILS OF STAIRS | Smita/Praful/Sonal | 2026-02-10 |  | 2026-04-09 |  |  | 2026-02-13 | 2026-04-20 |  |  |  | 1
14 | Structural | Structural | CV-192-STR-PTA-DRW-0013 | G.A. ELEVATION AND DETAILS OF GIRTS | G.A. ELEVATION AND DETAILS OF GIRTS | Smita/Praful/Sonal | 2026-02-12 |  | 2026-04-09 |  |  | 2026-02-17 | 2026-04-20 |  |  |  | 2
15 | Architecture | Architecture | CV-192-ARC-PTA-DRW-0001 | GROUND AND FIRST FLOOR PLAN @ E.L. 100.45 & 104.65 (DOOR - WINDOW AND FINISHES SCHEDULE) | GROUND AND FIRST FLOOR PLAN @ E.L. 100.45 & 104.65 (DOOR - WINDOW AND FINISHES SCHEDULE) | Aakarsh | 2026-01-13 |  | 2026-06-03 |  |  | 2026-01-16 | 2026-03-25 |  |  |  | 2
16 | Architecture | Architecture | CV-192-ARC-PTA-DRW-0002 | ROOF PLAN, ELEVATION & SECTION @ E.L. 110.35 | ROOF PLAN, ELEVATION & SECTION @ E.L. 110.35 | Aakarsh | 2026-01-15 |  | 2026-06-03 |  |  | 2026-01-20 | 2026-03-25 |  |  |  | 2
17 | Architecture | Architecture | CV-192-ARC-PTA-DRW-0003 | ARCHITECTURAL STAIRCASE DETAILS FOR PTA SUBSTATION | ARCHITECTURAL STAIRCASE DETAILS FOR PTA SUBSTATION | Aakarsh | 2026-01-15 |  | 2026-06-03 |  |  | 2026-01-20 | 2026-06-01 |  |  |  | 2